## Sheet1
Optical CRM
S.No | Module Name | Test case Hours | Testing-1 Hours | Bug Verification Hours | Closure Testing Hours | Test Case Status | Testing Status | Bug Verification Status | Start Date | End Date
1 | Add Optical Items | 4 | 5.5 | 1 | 2.5 | Done | Done | YTS
2 | Optical Rate Details | 4 | 5 | 1 | 2.5 | Done | In-Progress | YTS
3 | Optical Rate History | 3.5 | 4 | 1 | 2.5 | Done | YTS | YTS
4 | Add Purchase | 5 | 5.5 | 1 | 2.5 | Done | YTS | YTS
5 | Purchase History | 3.5 | 4 | 1 | 2.5 | Done | YTS | YTS
7 | Add Branch Transfer | 6 | 6.5 | 1 | 2.5 | Done | YTS | YTS
8 | Branch Transfer Approval | 4.5 | 5 | 1 | 2.5 | Done | YTS | YTS
9 | Branch Transfer History | 4 | 4.5 | 1 | 2.5 | Done | YTS | YTS
10 | Branch Inward Status | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
11 | Overall Stock movement Details | 3 | 6 | 1 | 2.5 | Done | YTS | YTS
12 | Warehouse Stock Movement | 3.5 | 4 | 1 | 2.5 | Done | YTS | YTS
13 | Branch Stock Movement | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
14 | Purchase Report | 3.5 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
15 | Transfer Report | 3 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
16 | Sales Report | 2.5 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
| Total | 57 | 71.5 | 15 | 37.5 |  | YTS | YTS
S.No | Module Name | Testing & Bug posting Status | Target to complete Testing & Bug posting | Bugs count | Bug Verifcation
1 | Add Optical Items | Done | 2024-11-12 | 62 | 2024-12-11
2 | Optical Rate Details | Done | 2024-11-13 | 46 | 2024-12-12
3 | Optical Rate History | Done | 2024-11-14 | 31 | 2024-12-12
4 | Add Purchase | Done | 2024-11-15 | 52 | 2024-12-13
5 | Purchase History | Done | 2024-11-16 | 24 | 2024-12-16
6 | Add Branch Transfer | Done | 2024-11-18 | 41 | 2024-12-16
7 | Branch Transfer Approval | Done | 2024-11-19 | 26 | 2024-12-17
8 | Branch Transfer History | Done | 2024-11-20 | 32 | 2024-12-17
9 | Category Wise Stock Movement | YTS | 2024-11-21 |  | 2024-12-18
10 | Warehouse Stock Movement | YTS | 2024-11-22 |  | 2024-12-18
11 | Branch Stock Movement | YTS | 2024-11-23 |  | 2024-12-19
12 | Purchase Report | YTS | 2024-11-25 |  | 2024-12-19
13 | Transfer Report | YTS | 2024-11-26 |  | 2024-12-19
14 | Prescription Entry | YTS | 2024-11-27 |  | 2024-12-20
15 | Prescription List | YTS | 2024-11-28 |  | 2024-12-20
16 | Branch Inward | In-Progress | 2024-12-02 |  | 2024-12-20
17 | Branch Current Stock | YTS | 2024-12-03 |  | 2024-12-23
18 | Stock Movement Details | YTS | 2024-12-05 |  | 2024-12-23
19 | Billing Page or Sales Entry | YTS | 2024-12-06 |  | 2024-12-23
20 | Invoice List and Invoice Print | YTS | 2024-12-09 |  | 2024-12-24
21 | Sales Report | YTS | 2024-12-10 |  | 2024-12-24
Total |  |  |  | 314
Smoke
Functional
Ui spell check
Buttons
Error message
Success message
Broken link
Image
Navigation
Data Validation
Redirect
Compatability
Sign in Page
Automation Testing
Appium