## WBS
Work Breakdown Structure
Testing | Test Case
|  |  |  | Task | Hrs | Status of Task
|  |  |  | Requirement Gathering and Understanding | 2 | In-Progress
0 | 0 |  |  | Test case preparation | 62 | In-Progress
|  |  |  | Configuration | 1 | Yet To Start
|  |  |  | Iteration-1 Testing | 78 | Yet To Start
|  |  |  | Test Document Preparation | 5 | Yet To Start
|  |  |  | Bug Verification | 10 | Yet To Start
|  |  |  | Closure Testing | 40 | Yet To Start
|  |  |  | Total | 198
Optical CRM
|  |  | S.No | Module Name | Test case Hours | Testing-1 Hours | Bug Verification Hours | Closure Testing Hours | Test Case Status | Testing Status | Bug Verification Status | Start Date | End Date
|  |  | 1 | Add Optical Items | 4 | 5.5 | 1 | 2.5 | Done | Done | YTS
|  |  | 2 | Optical Rate Details | 4 | 5 | 1 | 2.5 | Done | In-Progress | YTS
|  |  | 3 | Optical Rate History | 3.5 | 4 | 1 | 2.5 | Done | YTS | YTS
|  |  | 4 | Add Purchase | 5 | 5.5 | 1 | 2.5 | Done | YTS | YTS
|  |  | 5 | Purchase History | 3.5 | 4 | 1 | 2.5 | Done | YTS | YTS
|  |  | 7 | Add Branch Transfer | 6 | 6.5 | 1 | 2.5 | Done | YTS | YTS
|  |  | 8 | Branch Transfer Approval | 4.5 | 5 | 1 | 2.5 | Done | YTS | YTS
|  |  | 9 | Branch Transfer History | 4 | 4.5 | 1 | 2.5 | Done | YTS | YTS
|  |  | 10 | Branch Inward Status | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
|  |  | 11 | Overall Stock movement Details | 3 | 6 | 1 | 2.5 | Done | YTS | YTS
|  |  | 12 | Warehouse Stock Movement | 3.5 | 4 | 1 | 2.5 | Done | YTS | YTS
|  |  | 13 | Branch Stock Movement | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
|  |  | 14 | Purchase Report | 3.5 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
|  |  | 15 | Transfer Report | 3 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
|  |  | 16 | Sales Report | 2.5 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
|  |  |  | Total | 57 | 71.5 | 15 | 37.5 |  | YTS | YTS
|  |  |  | Add Optical Items | Add Optical Items
|  |  |  | Optical Purchase Entry | Add Purchase
|  |  |  | Optical Branch Transfer | Add Branch Transfer
|  |  | S.No | Module Name | Testing & Bug posting Status | Target to complete Testing & Bug posting | Test Case count | Bugs count | Bug Verifcation
|  |  | 1 | Add Optical Items | Done | 2024-11-12 | 100 | 62 | 2024-12-11
|  |  | 2 | Optical Rate Details | Done | 2024-11-13 | 79 | 46 | 2024-12-12
|  |  | 3 | Optical Rate History | Done | 2024-11-14 | 40 | 31 | 2024-12-12
|  |  | 4 | Add Purchase | Done | 2024-11-15 | 100 | 52 | 2024-12-13
|  |  | 5 | Purchase History | Done | 2024-11-16 | 39 | 24 | 2024-12-16
|  |  | 6 | Add Branch Transfer | Done | 2024-11-18 | 70 | 41 | 2024-12-16
|  |  | 7 | Branch Transfer Approval | Done | 2024-11-19 | 46 | 26 | 2024-12-17
|  |  | 8 | Branch Transfer History | Done | 2024-11-20 | 39 | 32 | 2024-12-17
|  |  | 9 | Category Wise Stock Movement | YTS | 2024-11-21 | 41 |  | 2024-12-18
|  |  | 10 | Warehouse Stock Movement | YTS | 2024-11-22 | 40 |  | 2024-12-18
|  |  | 11 | Branch Stock Movement | YTS | 2024-11-23 | 41 |  | 2024-12-19
|  |  | 12 | Purchase Report | YTS | 2024-11-25 |  |  | 2024-12-19 | Tentative Count--50
|  |  | 13 | Transfer Report | YTS | 2024-11-26 |  |  | 2024-12-19 | Tentative Count--55
|  |  | 14 | Prescription Entry | YTS | 2024-11-27 |  |  | 2024-12-20 | Tentative Count--60
|  |  | 15 | Prescription List | YTS | 2024-11-28 |  |  | 2024-12-20 | Tentative Count--40
|  |  | 16 | Branch Inward | In-Progress | 2024-12-02 | 66 |  | 2024-12-20 | Tentative Count--35
|  |  | 17 | Branch Current Stock | YTS | 2024-12-03 |  |  | 2024-12-23 | Tentative Count--40
|  |  | 18 | Stock Movement Details | YTS | 2024-12-05 |  |  | 2024-12-23 | Tentative Count--45
|  |  | 19 | Billing Page or Sales Entry | YTS | 2024-12-06 |  |  | 2024-12-23 | Tentative Count--40
|  |  | 20 | Invoice List and Invoice Print | YTS | 2024-12-09 |  |  | 2024-12-24 | Tentative Count--30
|  |  | 21 | Sales Report | YTS | 2024-12-10 |  |  | 2024-12-24 | Tentative Count--40
|  |  | Total |  |  |  | 1070
Smoke
Functional
Ui spell check
Buttons
Error message
Success message
Broken link
Image
Navigation
Data Validation
Redirect
Compatability
Sign in Page
Automation Testing
Appium
|  |  |  | Work Breakdown Structure for Hr Self service modules |  |  | 8
|  |  |  | Task | Hrs | Status of Task | 7
|  |  |  | Requirement Gathering and Understanding | 5 | YTS | 6
|  |  |  | Test case preparation | 21 | YTS
|  |  |  | Configuration | 1 | YTS
|  |  |  | Iteration-1 Testing | 30 | YTS
|  |  |  | Test Document Preparation | 4 | YTS
|  |  |  | Bug Verification | 5 | YTS
|  |  |  | Closure Testing | 16 | YTS
|  |  |  | Total | 82
|  |  |  | Days | Hrs | Status
|  |  |  | Tuesday(Test start from after 12 Pm) | 4 | In-progress
|  |  |  | Wednesday | 8 | Yet To Start | Release the Thought of the day bug report
|  |  |  | Thursday | 8 | Yet To Start
|  |  |  | Friday | 8 | Yet To Start | Release the Policies
|  |  |  | Saturday | 2 | Yet To Start
|  |  |  | Total | 30
|  |  | S.No | Module Name | Testing & Bug posting Status | Target to complete Testing & Bug posting | Testing & Bug posting | Bugs count | Bug Verifcation | Bug Verifcation Status
|  |  | 1 | Add Optical Items | Done | 2024-11-12 | 2024-11-12 | 62 | 2024-12-11
|  |  | 2 | Optical Rate Details | Done | 2024-11-13 | 2024-11-13 | 46 | 2024-12-12
|  |  | 3 | Optical Rate History | Done | 2024-11-14 | 2024-11-14 | 31 | 2024-12-12
|  |  | 4 | Add Purchase | Done | 2024-11-15 | 2024-11-15 | 52 | 2024-12-13
|  |  | 5 | Purchase History | Done | 2024-11-16 | 2024-11-16 | 24 | 2024-12-16
|  |  | 6 | Add Branch Transfer | Done | 2024-11-18 | 2024-11-18 | 41 | 2024-12-16
|  |  | 7 | Branch Transfer Approval | Done | 2024-11-19 | 2024-11-19 | 26 | 2024-12-17
|  |  | 8 | Branch Transfer History | Done | 2024-11-20 | 2024-11-19 | 32 | 2024-12-17
|  |  | 9 | Branch Inward | Done | 2024-11-21 | 2024-11-20 | 33 | 2024-12-18
|  |  | 10 | Branch Current Stock | Done | 2024-11-22 | 2024-11-21 | 14 | 2024-12-18
|  |  | 11 | Billing Page or Sales Entry | Done | 2024-11-23 | 2024-11-21 | 51 | 2024-12-19
|  |  | 12 | Invoice List | Done | 2024-11-25 | 2024-11-22 | 19 | 2024-12-19
|  |  | 13 | Invoice Print | Done | 2024-11-26 | 2024-11-22 |  | 2024-12-19
|  |  | 14 | Sales Report | Done | 2024-11-26 | 2024-11-22 | 24 | 2024-12-19
|  |  | 15 | Prescription Entry | Done | 2024-11-27 | 2024-11-23 | 10 | 2024-12-20
|  |  | 16 | Prescription List | Done | 2024-11-28 | 2024-11-25 | 24 | 2024-12-20
|  |  | 17 | Category Wise Stock Movement | Done | 2024-12-02 |  | 19 | 2024-12-20
|  |  | 18 | Transfer Report | YTS | 2024-12-03 |  |  | 2024-12-23
|  |  | 19 | Stock Movement Details | YTS | 2024-12-05 |  |  | 2024-12-23
|  |  | 20 | Purchase Report | YTS | 2024-12-06 |  |  | 2024-12-23
|  |  | 21 | Item Wise Stock Movement | YTS | 2024-12-09 |  |  | 2024-12-24
|  |  | 22 | Branch Stock Movement | YTS | 2024-12-10 |  |  | 2024-12-24
|  |  | Total |  |  |  |  | 508
| S.No | Version | System | Main Module | Sub Module | Dev | Build Initiator | Build Status | Test Build Release Date
| 1 | 1.0.0 | ERP | Manage Optical Items | Add Item | Mosik & Indiran | Sai | Ready for Testing | 11th Nov
| 2 | 1.0.0 |  |  | Rate Details | Periyasedhu & Indiran | Sai | Ready for Testing | 11th Nov
| 3 | 1.0.0 |  |  | Rate History | Periyasedhu & Indiran | Sai | Ready for Testing | 11th Nov
| 4 | 1.0.0 |  | Purchase Entry | Add Purchase | Mosik & Indiran | Sai | Ready for Testing | 11th Nov
| 5 | 1.0.0 |  |  | Purchase History | Mosik & Indiran | Sai | Ready for Testing | 11th Nov
| 6 | 1.0.0 |  | Branch Transfer | Add Branch Transfer | Mosik, Sai & Indiran | Sai | Ready for Testing | 11th Nov
| 7 | 1.0.0 |  |  | Branch Transfer Approval | Mosik, Sai & Indiran | Sai | Ready for Testing | 11th Nov
| 8 | 1.0.0 |  |  | Branch Transfer History | Mosik & Indiran | Sai | Ready for Testing | 11th Nov
| 9 | 1.0.0 |  | Stock Movement Details | Category Wise WH Stock Movement | Mosik, Edwin & Indiran | Sai | Ready for Testing | 20th Nov
| 10 | 1.0.0 |  |  | Item Wise WH Stock Movement | Mosik, Edwin & Indiran | Sai | Under Development | -
| 11 | 1.0.0 |  |  | Branch Stock Movement | Mosik, Edwin & Indiran | Sai | Under Development | -
| 12 | 1.0.0 |  | Reports | Purchase Report | Edwin & Mosik | Sai | Review in progress | -
| 13 | 1.0.0 |  |  | Branch Transfer Report | Edwin & Mosik | Sai | Review in progress | -
| 14 | 1.0.0 | PoS | Prescriptions Manage | Prescription Entry | Periyasedhu & Indiran | Sai | Ready for Testing | 12th Nov
| 15 | 1.0.0 |  |  | Prescription List | Periyasedhu & Indiran | Sai | Ready for Testing | 12th Nov
| 16 | 1.0.0 |  | Stock | Branch Inward | Sai | Sai | Ready for Testing | 12th Nov
| 17 | 1.0.0 |  |  | Branch Current Stock | Sai | Sai | Ready for Testing | 12th Nov
| 18 | 1.0.0 |  |  | Stock Movement Details | Mosik & Indiran | Sai | Under Development | -
| 19 | 1.0.0 |  | Sales | Billing Page or Sales Entry | Sai | Sai | Ready for Testing | 12th Nov
| 20 | 1.0.0 |  |  | Invoice List | Sai | Sai | Ready for Testing | 12th Nov
| 21 | 1.0.0 |  |  | Invoice Print | Sai | Sai | Ready for Testing | 20th Nov
| 22 | 1.0.0 |  |  | Sales Report | Sai | Sai | Ready for Testing | 12th Nov
|  |  | S.No | Module Name | Testing & Bug posting Status | Bugs count
|  |  | 1 | Add Optical Items | Done | 62
|  |  | 2 | Optical Rate Details | Done | 46
|  |  | 3 | Optical Rate History | Done | 31
|  |  | 4 | Add Purchase | Done | 52
|  |  | 5 | Purchase History | Done | 24
|  |  | 6 | Add Branch Transfer | Done | 41
|  |  | 7 | Branch Transfer Approval | Done | 26
|  |  | 8 | Branch Transfer History | Done | 32
|  |  | 9 | Branch Inward | Done | 33
|  |  | 10 | Branch Current Stock | Done | 14
|  |  | 11 | Billing Page or Sales Entry | Done | 51
|  |  | 12 | Invoice List | Done | 19
|  |  | 13 | Invoice Print | Done
|  |  | 14 | Sales Report | Done | 24
|  |  | 15 | Prescription Entry | Done | 10
|  |  | 16 | Prescription List | Done | 24
|  |  | 17 | Category Wise Stock Movement | Done | 19
|  |  | 18 | Transfer Report | YTS
|  |  | 19 | Stock Movement Details | YTS
|  |  | 20 | Purchase Report | YTS
|  |  | 21 | Item Wise Stock Movement | YTS
|  |  | 22 | Branch Stock Movement | YTS
|  |  | Total |  |  | 508

## Sheet3
| S.No | Module Name | SS
| 1 | Add Optical Items | Yes
| 2 | Optical Rate Details | Yes
| 3 | Optical Rate History | Yes
| 4 | Add Purchase | Yes
| 5 | Purchase History | No
| 6 | Add Branch Transfer | Yes
| 7 | Branch Transfer History | Yes
| 8 | Overall Stock movement Details | Yes
| 9 | Warehouse Stock Movement | Yes
| 10 | Branch Stock Movement | Yes
| 11 | Purchase Report | Yes
| 12 | Transfer Report | Yes
| 13 | Add Suplier | Remove
| 14 | Branch Transfer Approval | No
| 15 | Branch Inward Status | No
| 16 | Sales Report | No
| 17 | Purchase History | No
| S.No | Module Name | Test Case Status
| 1 | Add Optical Items | Done
| 2 | Optical Rate Details | Done
| 3 | Optical Rate History | Done
| 4 | Add Purchase | Done
| 5 | Purchase History | Done
| 6 | Add Branch Transfer | Done
| 7 | Branch Transfer Approval | Done
| 8 | Branch Transfer History | Done
| 9 | Overall Stock movement Details | Done
| 10 | Warehouse Stock Movement | Done
| 11 | Branch Inward Status | 3.5
| 12 | Branch Stock Movement | 3.5
| 13 | Purchase Report | 3.5
| 14 | Transfer Report | 3
| 15 | Sales Report | 2.5
|  | Total | 16
CateRPTgory Wise Stock Movement
S.No | Bug ID | Bug Title | Severity
1 |  | Unable to generate the report details for all categories | High
2 |  | Even with an empty list grid, the downloaded Excel file shows certain values | High
3 |  | The system takes a long time to load when the "Get" button is clicked | Critical
4 | OC-595 | OptCrm-PrsLst- No record available message not display in list grid | Low
5 | OC-366 | OptCrm-BranchHis- Refresh icon not available to clear the search filter values | Medium
6 | OC-372 | Download options display in bottom of the list grid | Medium
8 | OC-373 | OptCrm-BranchHis- The history grid displays values after clearing the selected filter | High
9 | OC-374 | OptCrm-BranchHis- Search filter and Pagination not display | Medium
10 | OC-45 | OptCrm-AddItem- An unwanted page is being opened when clicking the Home button | Critical
11 |  | The button name is not displayed as "Get Details" or "Generate Report | Low
12 | OC-179 | OptCrm-RateHis- Model No. value display as empty in History list grid | Low
13 | OC-239 | OptCrm-AddPur- Placeholder/Inner Text not display in search field | Low
14 |  | Mismatch values display in Category Wise list grid while update the records | Critical
15 |  | The export button and scrollbar are misaligned | Low
17 | OC-46 | OptCrm-AddItem- Improper alignment display in list grid | Low
16 |  | Group by column header not display middle of the column | Low
18 |  | Menu name not display properly | Medium
19 |  | "Not Transfer Approved" appears in the Category Wise Stock Movement Details list grid | High
20 |  | Mismatch column order alignment display in export excel
Test Case Status
| S.No | Module Name | Test Case Status | Bug Verification Status
| 1 | Add Optical Items | Done
| 2 | Optical Rate Details | Done
| 3 | Optical Rate History | Done
| 4 | Add Purchase | Done
| 5 | Purchase History | Done
| 6 | Add Branch Transfer | Done
| 7 | Branch Transfer Approval | Done
| 8 | Branch Transfer History | Done
| 9 | Branch Inward | Done
| 10 | Branch Current Stock | Done
| 11 | Billing Page or Sales Entry | Done | 2024-12-04
| 12 | Invoice List | Done
| 13 | Invoice Print | Done
| 14 | Sales Report | Done
| 15 | Prescription Entry | Done
| 16 | Prescription List | Done
| 17 | Category Wise Stock Movement | Done
| 18 | Item Wise Stock Movement | Done
| 19 | Branch Stock Movement | Done
| 20 | Stock Movement Details | Done
| 21 | Purchase Report | Done
| 22 | Transfer Report | Done
Bug Verification Status
| S.No | Module Name | Bug Verification Status | Bug count
| 1 | Add Optical Items | Done | 15
| 2 | Optical Rate Details | Done | 11
| 3 | Optical Rate History | Done | 8
| 4 | Add Purchase | In-progress | 14
| 5 | Purchase History | YTS
| 6 | Add Branch Transfer | YTS
| 7 | Branch Transfer Approval | YTS
| 8 | Branch Transfer History | YTS
| 9 | Branch Inward | YTS
| 10 | Branch Current Stock | YTS
| 11 | Billing Page or Sales Entry | YTS
| 12 | Invoice List | YTS
| 13 | Invoice Print | YTS
| 14 | Sales Report | YTS
| 15 | Prescription Entry | YTS
| 16 | Prescription List | YTS
| 17 | Category Wise Stock Movement | YTS
| 18 | Item Wise Stock Movement
| 19 | Branch Stock Movement
| 20 | Stock Movement Details
| 21 | Purchase Report
| 22 | Transfer Report
|  | Total |  | 48
2024-12-11
[5 empty] | Total Bug Details |  |  |  |  | Severity
[5 empty] | Bug Count | Close | Reopen | New |  | High | Critical
[5 empty] | 10 | 7 | 3 | 0 |  | 9 | 1
2024-12-12
[5 empty] | Total Bug Details |  |  |  |  | Severity
[5 empty] | Bug Count | Close | Reopen | New | Hold | High | Critical
[5 empty] | 16 | 6 | 5 | 2 | 3 | 15 | 1

## Bug Verification
Close | Re-open | Not Tested | New | Total
35 | 10 | 3 | 0 | 48
2024-12-26
Close | Re-open | Deferred | New | Total
12 | 3 | 1 | 1 | 17
2024-12-30
Close | Re-open | Deferred | New | Total
12 | 3 | 1 | 1 | 17
Total Bug Details |  |  |  |  | Severity
Bug Count | Close | Reopen | New | Hold | High | Critical
19 | 14 | 4 | 2 | 0 | 18 | 0
|  |  | S.No | Bug ID | Add Optical Item-Bug Title | Status | Remarks
|  |  | 1 | OC-42 | OptCrm-AddItem- Deleted record display in list grid | Close
|  |  | 2 | OC-43 | OptCrm-AddItem- Column Header, Search filter and Pagination not display | Close
|  |  | 3 | OC-45 | OptCrm-AddItem- An unwanted page is being opened when clicking the Home button | Close
|  |  | 4 | OC-49 | OptCrm-AddItem- Confirmation message display while click close button without change any value | Close
|  |  | 5 | OC-62 | OptCrm-AddItem- Unwanted error message while click submit button with max value | Close
|  |  | 6 | OC-81 | OptCrm-AddItem- Given Contact Lens Base Curves value not display in edit mode | Close
|  |  | 7 | OC-83 | OptCrm-AddItem- Mismatch Solution Packing Type value display in edit mode | Close
|  |  | 8 | OC-85 | OptCrm-AddItem- Unwanted confirmation message display while click the Edit button | Close
|  |  | 9 | OC-106 | OptCrm-AddItem- The system allows file uploads even when the title exceeds 50 characters | Close
|  |  | 10 | OC-107 | OptCrm-AddItem- There is no indication or message showing the format type of the file being uploaded in the upload section | Close
|  |  | 11 | OC-40 | OptCrm-AddItem-Screen header/title name display mismatch content | Close
|  |  | 12 | OC-52 | OptCrm-AddItem- Uploaded file not display in Edit mode | Re-open | Mentioned scenario working, issue in below The file uploaded does not appear to be clear
|  |  | 13 | OC-79 | OptCrm-AddItem- User can able to update the Product Category field in edit mode | re-open | Product Category field display as edit While edit any field
|  |  | 14 | OC-82 | OptCrm-AddItem- Minus value display in all numbers field while click down arrow button | Re-open | Issue re-open for the same steps
|  |  | 15 | OC-104 | OptCrm-AddItem- The data is not displaying correctly; some of it is getting lost | Re-open | Issue re-open for the same steps
[5 empty] | Unable to add new Optical Items record | New | Search any valid value in search section Click the edit icon for seached record Close the pop up Click the Add new button
|  |  | S.No | Bug ID | Rate Details-Bug Title | Status | Remarks
|  |  | 1 | OC-118 | OptCrm-RateDet- HSN Code display as Empty | Close
|  |  | 2 | OC-120 | OptCrm-RateDet- There is improper alignment displayed in the list grid | Close
|  |  | 3 | OC-121 | OptCrm-RateDet- Screen header/title name display mismatch content | Close
|  |  | 4 | OC-126 | OptCrm-RateDet- Non-editable field display required highlight colour | Close
|  |  | 5 | OC-127 | OptCrm-RateDet- Unable to update rate for Other category record | Close
|  |  | 6 | OC-130 | OptCrm-RateDet- An unwanted page is being opened when clicking the Home button | Close
|  |  | 7 | OC-132 | OptCrm-RateDet- Unable to update rate for Solution category record | Close
|  |  | 8 | OC-139 | OptCrm-RateDet- Unwanted content display in Base price field | Close
|  |  | 9 | OC-141 | OptCrm-RateDet- Unwanted error message while click submit button with max value | Close
|  |  | 10 | OC-157 | OptCrm-RateDet- The data is not displaying correctly; some of it is getting lost | Close
|  |  | 11 | OC-144 | OptCrm-RateDet- Base Price value not getting clear/update while update the Purchase Price | Re-open | Issue re-open for the same steps
[5 empty] | OptCrm-RateDet- Users can save rate details even with a 0 rate value in the system | New
|  |  | S.No | Bug ID | Rate History-Bug Title | Status | Remarks
|  |  | 1 | OC-168 | OptCrm-RateHis- Unwanted error message display while click the Get Rate Details button | Close
|  |  | 2 | OC-170 | OptCrm-RateHis- Deleted record display in product dropdown | Close
|  |  | 3 | OC-174 | OptCrm-RateHis- The product value is displayed even when no category is selected | Close
|  |  | 4 | OC-175 | OptCrm-RateHis- History details display without select the Category value | Close
|  |  | 5 | OC-178 | OptCrm-RateHis- The history grid displays values after clearing the selected filter | Close
|  |  | 6 | OC-182 | OptCrm-RateHis- Unnecessary values are appearing in the Date column | Close
|  |  | 7 | OC-187 | OptCrm-RateHis- Unwanted content display in rate values | Close
|  |  | 8 | OC-196 | OptCrm-RateHis- The data is not displaying correctly; some of it is getting lost | Close
|  |  | S.No | Bug ID | Add Purchase-Bug Title | Status | Remarks
|  |  | 1 | OC-216 | OptCrm-AddPur- The "Add New Entry" page does not appear initially when navigating to the page | Close
|  |  | 2 | OC-230 | OptCrm-AddPur- User can create purchase record with future date | Close
|  |  | 3 | OC-234 | OptCrm-AddPur- Mismatch Product name display while select the Product code | Close
|  |  | 4 | OC-237 | OptCrm-AddPur- Existing value display while click the add new button | Close
|  |  | 5 | OC-240 | OptCrm-AddPur- Add Item page getting reload while click Add new product button | Close
|  |  | 6 | OC-266 | OptCrm-AddPur- User can able to create duplicate product | Close
|  |  | 7 | OC-263 | OptCrm-AddPur- Dual Confirmation message display while delete the list grid record | Re-open | Delete message not display
|  |  | 8 | OC-265 | OptCrm-AddPur- Header tab display as not label name | Re-open | Issue re-open for the same steps
|  |  | 9 | OC-267 | OptCrm-AddPur- User can create purchase record without supplier name | Re-open | Issue re-open for the same steps
|  |  | 10 | OC-219 | OptCrm-AddPur- Add Product Detail getting open with the error message | Re-open/Close | Issue re-open for the same steps
|  |  | 11 | OC-224 | OptCrm-AddPur- Required error message display after give the same value | Re-open | There is an issue with the Date field
|  |  | 12 | OC-228 | OptCrm-AddPur- Add product detail pop up getting open without Invoice Amount value | Not Tested | Need to discuss with karthik
|  |  | 13 | OC-231 | OptCrm-AddPur- The system does not allow the creation of a new record in edit mode | Not Tested | Need to discuss with karthik
|  |  | 14 | OC-258 | OptCrm-AddPur- System display error message while save the record after delete the list grid record | Not Tested | Need to discuss with karthik
[5 empty] | Unable to update the existing record | New
[5 empty] | Unable to add the tax value in add purchase page | New
2024-12-20
|  |  | S.No | Bug ID | Branch Inward-Bug Title | Bug Status | Remarks
|  |  | 1 | OC-395 | OptCrm-BranchInw- The Quantity field permits letters and special symbols | Close
|  |  | 2 | OC-397 | OptCrm-BranchInw- Unwanted error message display while update the record with max value | Close
|  |  | 3 | OC-398 | OptCrm-BranchInw- No error message appears in the system if the received quantity is greater than the total quantity | Close
|  |  | 4 | OC-400 | OptCrm-BranchInw- No error message appears in the system if the damaged quantity is greater than the total quantity | Close
|  |  | 5 | OC-402 | OptCrm-BranchInw- Error message display while click the edit button | Close
|  |  | 6 | OC-405 | OptCrm-BranchInw- There is a mismatch between the screen title and the menu name | Close
|  |  | 7 | OC-408 | OptCrm-BranchInw- Mismatch column name display in list grid | Close
|  |  | 8 | OC-411 | OptCrm-BranchInw- The sorting feature is not functioning for any column except S.No. | Close
|  |  | 9 | OC-417 | OptCrm-BranchInw- The list grid presents one type of data, while the downloaded document shows another | Close
|  |  | 10 | OC-412 | OptCrm-BranchInw- The search filter doesn't work in the list grid view | Re-open | Search filter results are showing unrelated records in the list grid
|  |  | 11 | OC-424 | OptCrm-BranchInw- Verified/Completed records not display | Deffered | Verified/Completed records are not required to be displayed as per the existing process; bug severity updated.
|  |  | 12 | OC-399 | OptCrm-BranchInw- Pop up Title not display as Title header | Deffered | Bug severity updated based on review and analysis.
|  |  | 13 | OC-415 | OptCrm-BranchInw- Duplicate records display in Inward list grid | Deffered | Confirmed the records are not duplicates; bug severity updated accordingly.
|  |  | 14 | OC-649 | OptCrm-BranchInw- Downloaded file is not showing records corresponding to the search filter | New
|  |  | S.No | Bug ID | Branch Current -Bug Title | Status | Remarks
|  |  | 1 | OC-475 | OptCrm-BrcCur- Mismatch column name display in list grid | Close
|  |  | 2 | OC-484 | OptCrm-BrcCur- The list grid presents one type of data, while the downloaded document shows another | Close
|  |  | 3 | OC-478 | OptCrm-BrcCur- Improper alignment display in list grid | Deffered | Alignment confirmed to be proper. Table adjusts automatically based on value size; bug severity updated.
|  |  | S.No | Bug ID | Invoice List -Bug Title | Status | Remarks
|  |  | 1 | OC-544 | OptCrm-InvList- Mismatch column name display in list grid | Re-open | Issue re-open for the same steps
|  |  | 2 | OC-545 | OptCrm-InvList- Invoice list grid not display based on the date range | Re-open | Issue re-open for the same steps
|  |  | 3 | OC-552 | OptCrm-InvList- The amount in words does not reflect Indian Rupees | Re-open | Issue re-open for the same steps
|  |  | 4 | OC-536 | OptCrm-InvList- Unable to edit the invoice record | Deffered | User story is on hold. Development of the edit invoice feature will proceed once the billing page is approved, as it is tied to multiple enhancements.
|  |  | 5 | OC-553 | OptCrm-InvList- Different date format display in list grid | Deffered | Comments and status not updated
|  |  | 6 | OC-539 | OptCrm-InvList- Error message not display while invalid date range | Deffered | Comments and status not updated
2024-12-24
|  |  | S.No | Bug ID | Billing Page -Bug Title | Bug Status | Remarks
|  |  | 1 | OC-489 | OptCrm-Billing- The validation for the maximum character count is missing in the "Register New Customer" pop-up | Close
|  |  | 2 | OC-490 | OptCrm-Billing- The dropdown in the "Created By" field does not allow selection beyond two values | Close
|  |  | 3 | OC-494 | OptCrm-Billing- Unwanted error message display while update the record with max value | Close
|  |  | 4 | OC-497 | OptCrm-Billing-Error message display while click the edit button | Close
|  |  | 5 | OC-500 | OptCrm-Billing- When the Check user button is pressed, existing values appear | Close
|  |  | 6 | OC-508 | OptCrm-Billing- Exiting value display while click Add Count button | Close
|  |  | 7 | OC-510 | OptCrm-Billing- New register page not getting open | Close
|  |  | 8 | OC-512 | OptCrm-Billing- Model No. value display as empty | Close
|  |  | 9 | OC-519 | OptCrm-Billing- Mismatch column name display in list grid | Close
|  |  | 10 | OC-528 | OptCrm-Billing- Balance amount display mismatch value | Close
|  |  | 11 | OC-531 | OptCrm-Billing- Balance amount display minus value | Close
|  |  | 12 | OC-495 | OptCrm-Billing- Pop up Title not display as Title header | Deffered | Bug Severity Updated.
|  |  | 13 | OC-499 | OptCrm-Billing- Walk In count getting increase without register user | Deferred | Need to discuss with karthik
|  |  | 14 | OC-517 | OptCrm-Billing- Unable to update the added item | Deferred | Need to discuss with karthik
|  |  | 15 | OC-535 | OptCrm-Billing- Improper alignment and data not display in Invoice print page | Deferred | Need to discuss with karthik
|  |  | 16 | OC-511 | OptCrm-Billing- Unable to Pre-Sale record | Not Tested | Need to discuss with karthik
|  |  | 17 | OC-650 | OptCrm-Billing- Register New customer pop up getting open without any mobile no | New
2024-12-26
|  |  | S.No | Bug ID | Sales Report-Bug Title | Bug Status | Remarks
|  |  | 1 | OC-556 | OptCrm-SalesRpt- The print button is not functioning | Close
|  |  | 2 | OC-559 | OptCrm-SalesRpt- UPI Wallet display as empty | Close
|  |  | 3 | OC-562 | OptCrm-SalesRpt- Quantity value display as empty | Close
|  |  | 4 | OC-566 | OptCrm-SalesRpt- Error message not display while invalid date range | Close
|  |  | 5 | OC-571 | OptCrm-SalesRpt- Different date format display in list grid | Close
|  |  | 6 | OC-563 | OptCrm-SalesRpt- Unwanted Return details section display in sales report page | Deferred | As developing the sales report like as in exsisting system. In further developments Sales Return also will be developed.
|  |  | 7 | OC-555 | OptCrm-SalesRpt- Mismatch walk in count display in sales report | Re-open | Issue re-open for the same steps
2024-12-26
|  |  | S.No | Bug ID | Prescription Entry-Bug Title | Bug Status | Remarks
|  |  | 1 | OC-584 | OptCrm-PrsEtr- Decimal value allows in age field | Close
|  |  | 2 | OC-587 | OptCrm-PrsEtr- The validation for the maximum character count is missing | Close
|  |  | 3 | OC-581 | OptCrm-PrsEtr- Patient Gender value getting clear while create the record | Re-open | Issue re-open for the same steps
|  |  | 4 | OC-651 | OptCrm-PrsLst- Unable to perform copy & past the valid value in Eyewear Prescription section field's | New
2024-12-26
|  |  | S.No | Bug ID | Prescription List-Bug Title | Bug Status | Remarks
|  |  | 1 | OC-601 | OptCrm-PrsLst- Different date format display in list grid | Close
|  |  | 2 | OC-603 | OptCrm-PrsLst- Error message not display while invalid date range | Close
|  |  | 3 | OC-610 | OptCrm-PrsLst- Mobile number field allow more than 100 values | Close
|  |  | 4 | OC-611 | OptCrm-PrsLst- Unable to update with all value in edit pop up | Close
|  |  | 5 | OC-612 | OptCrm-PrsLst- Unable to create the with all values | Close
|  |  | 6 | OC-596 | OptCrm-PrsLst- Invoice list grid not display based on the date range | Re-open | Issue re-open for the same steps
2024-12-30
|  |  | S.No | Bug ID | Branch Transfer Approval-Bug Title | Severity | Bug Status | Remarks
|  |  | 1 | OC-337 | OptCrm-BranchApp- Showing records and Pagination not display in approve list grid | High | Close
|  |  | 2 | OC-338 | OptCrm-BranchApp- Screen header/title name display mismatch content | High | Close
|  |  | 3 | OC-340 | OptCrm-BranchApp- Unable to reject the pending transfer approval records | High | Close
|  |  | 4 | OC-341 | OptCrm-BranchApp- Unwanted Edit and Delete option available in Approval screen | High | Re-open | Issue re-open for the same steps
|  |  | 5 | OC-348 | OptCrm-BranchApp- Column value not display in list grid | High | Re-open | Updated Transfer QTY value not display in list grid
2024-12-30
|  |  | S.No | Bug ID | Branch Transfer History - Bug Title | Severity | Bug Status | Remarks
|  |  | 1 | OC-364 | OptCrm-BranchHis- Product field not display any value when Product Category value has selected | High | Close
|  |  | 2 | OC-370 | OptCrm-BranchHis- Improper alignment display in list grid | High | Close
|  |  | 3 | OC-391 | OptCrm-BranchHis- Branch Transfer History not display record while update the record | Critical | Close
|  |  | 4 | OC-392 | OptCrm-BranchHis- Column value not display in list grid | High | Close
|  |  | 5 | OC-369 | OptCrm-BranchHis- Hash value display while open the downloaded CSV | High | Not Tested | The respective approved comments have not been updated to mark the bug as deferred.
|  |  | 6 | OC-373 | OptCrm-BranchHis- The history grid displays values after clearing the selected filter | High | Not Tested | The respective approved comments have not been updated to mark the bug as deferred.
|  |  | 7 | OC-652 | OptCrm-BranchHis- Unable to select the "All" values in Product Category | High | New
2024-12-31
|  |  | S.No | Bug ID | Category Wise Stock Movement - Bug Title | Severity | Resolution | Remarks
|  |  | 1 | OC-614 | OptCrm-RptCtgWs- Even with an empty list grid, the downloaded Excel file shows certain values | High | Close
|  |  | 2 | OC-621 | OptCrm-RptCtgWs- An unwanted page is being opened when clicking the Home button | Critical | Close
|  |  | 3 | OC-631 | OptCrm-RptCtgWs- Mismatch column order alignment display in export excel | High | Close
|  |  | 4 | OC-625 | OptCrm-RptCtgWs- Mismatch values display in Category Wise list grid while update the records | Critical | Re-open | Issue re-open for the same steps, Mismatch data display in list grid while update the Transfer count
|  |  | 5 | OC-615 | OptCrm-RptCtgWs- The system takes a long time to load when the "Get" button is clicked | Critical | Re-open | Issue re-open for the same steps
|  |  | 6 | OC-613 | OptCrm-RptCtgWs- Unable to generate the report with all categories | High | Not Tested | Currently, the Category Wise report has been developed. Additional features will be included in future updates.
|  |  | 7 | OC-619 | OptCrm-RptCtgWs- The list grid displays values after clearing the selected filter | High | Deferred | The respective approved comments have not been updated to mark the bug as deferred.
|  |  | 8 | OC-630 | OptCrm-RptCtgWs- "Not Transfer Approved" records appears in the Category Wise Stock Movement Details list grid | High | Deferred | The respective approved comments have not been updated to mark the bug as deferred.

## Sheet1
SG
1 | 85%- Client Onboarding
2 | UI Development Need to change the Backend structure
3 | 4 -User story has completed
4 | Another It will done by 11/Dec
1 | Hari asigned for new master API Integration
2 | Ui can change based on clieant review
Optical CRM
1 | Working on resolving bugs in the Optical CRM.
2 | Need to implement feature changes as requested by Parthiban
3 | A tentative completion date for the Optical CRM project will be planned
PMP
1 | The completion of module 3, along with all six of its submodules, has been achieved
2 | Milestone and deadline for the four submodules are currently in progress (WIPG)
3 | The deadline for completing all five submodules of the module is set for December 11, 2024