## WBS
Work Breakdown Structure
| Testing | Test Case | [5 empty] | Hrs
| 10 | 8 |  |  |  | User Pop up |  | 4
| 10 | 7 | Task | Hrs | Status of Task | Lab Test |  | 2
| 10 | 6 | Requirement Gathering and Understanding | 4 | Yet To Start | Patient Details | 3 fields | 2
Total | 30 | 21 | Test case preparation | 18 | Yet To Start | Lab billing | 2 fields | 1
|  |  | Configuration | 3 | Yet To Start | LabTest Details section |  | 3
|  |  | Iteration-1 Testing | 22 | Yet To Start | Amount section |  | 3
|  |  | Test Document Preparation | 3 | Yet To Start | Lab Invoice Print |  | 2
|  |  | Bug Verification | 4 | Yet To Start
|  |  | Closure Testing | 11 | Yet To Start
|  |  | Total | 65
Bug Verification
|  |  |  | Modules | Hours
|  |  | Bug Verification | 3 Modules | 32
|  |  | Module Name | Test case Hours | Test Case Status | Testing Status
|  |  | User Pop up | 4 | Yet To Start | Yet To Start
|  |  | Lab Test | 2 | Yet To Start | Yet To Start
|  |  | Patient Details | 2 | Yet To Start | Yet To Start
|  |  | Lab billing | 4 | Yet To Start | Yet To Start
|  |  | LabTest Details section | 2 | Yet To Start | Yet To Start
|  |  | Amount section | 4 | Yet To Start | Yet To Start
|  |  | Lab Invoice Print | 2 | Yet To Start | Yet To Start
|  |  | Total | 20
Smoke
Functional
Ui spell check
Buttons
Error message
Success message
Broken link
Image
Navigation
Data Validation
Redirect
Compatability
Sign in Page
Automation Testing
Appium
|  |  | Work Breakdown Structure for Hr Self service modules |  |  | 8
|  |  | Task | Hrs | Status of Task | 7
|  |  | Requirement Gathering and Understanding | 5 | Done | 6
|  |  | Test case preparation | 21 | Done
|  |  | Configuration | 1 | Done
|  |  | Iteration-1 Testing | 30 | In-progress
|  |  | Test Document Preparation | 4 | Yet To Start
|  |  | Bug Verification | 5 | Yet To Start
|  |  | Closure Testing | 16 | Yet To Start
|  |  | Total | 82
|  |  | Days | Hrs | Status
|  |  | Tuesday(Test start from after 12 Pm) | 4 | In-progress
|  |  | Wednesday | 8 | Yet To Start | Release the Thought of the day bug report
|  |  | Thursday | 8 | Yet To Start
|  |  | Friday | 8 | Yet To Start | Release the Policies
|  |  | Saturday | 2 | Yet To Start
|  |  | Total | 30

## Sheet4
Work Breakdown Structure
Task | Hrs | Status of Task | 12 Modules
Requirement Gathering and Understanding | 4 | Yet To Start | Test Case | 8 days | 60 Hours
Test case preparation | 18 | Yet To Start | Testing | 13 days | 100 Hours
Configuration | 3 | Yet To Start
Iteration-1 Testing | 22 | Yet To Start
Test Document Preparation | 3 | Yet To Start
Bug Verification | 4 | Yet To Start | Completed Modules | 4
Closure Testing | 11 | Yet To Start | Yet to start | 7
Total | 65 |  | In-progress | 1