## Cover Page
Bug Report_POS_Pre Invoice_Initiate Pay
VERSION NO | RELEASE DATE | CHANGE DETAILS |  | Prepared By
|  | SECTION | DESCRIPTION
1 | 2024-09-08 | Payment | POS_Pre Invoice_Initiate Pay | Lakshmanan.M

## Procument Dashboard_Big list
S.No | Bug Id | Department | LOB | Role | Title | Bug Description | Bug Severity | TCs Impacted | Bug Identified Date | Assigned to DEV | Fixed Provided by DEV | Defect Category | Defect Sub Category | Fix Status | Defect Reopened | Tentative Fix Date | Actual Fix Date | Comments To QA | Additional Remarks
1 | QRPM-80 | Sales | Pharmacy | Pharmacist | Pre Invoice-Initiate Pay | POS-Initiate Pay: By default, Initiate pay button display | Medium | Verify By default, Initiate pay button display | 2024-10-08 | Saikumar
2 | QRPM-88 |  |  |  |  | POS-Initiate Pay: Unable to edit Coupon No value when Payment Type = Cash | High | Verify Unable to edit Coupon No value when Payment Type = Cash | 2024-10-08 | Saikumar
3 | QRPM-90 |  |  |  |  | POS-Initiate Pay: Transaction Reference ID display when Payment Type = Cash | Low | Verify Transaction Reference ID display when Payment Type = Cash | 2024-10-08 | Saikumar
4 | QRPM-92 |  |  |  |  | POS-Initiate Pay: Spelling mistake display Transaction Reference ID | Low | Verify Spelling mistake display Transaction Reference ID | 2024-10-08 | Saikumar
5 | QRPM-93 |  |  |  |  | POS-Initiate Pay: Payment Initiated success message not display properly | Medium | Verify Payment Initiated success message not display properly | 2024-10-08 | Saikumar
6 | QRPM-94 |  |  |  |  | POS-Initiate Pay: User can able to give multiple Initiate pay request | High | Verify User can able to give multiple Initiate pay request | 2024-10-08 | Saikumar
7 | QRPM-95 |  |  |  |  | POS-Initiate Pay: User unable to add new item and delete the existing item when the payment type = Cash | High | Verify User unable to add new item and delete the existing item when the payment type = Cash | 2024-10-08 | Saikumar
8 | QRPM-96 |  |  |  |  | POS-Initiate Pay: The user cannot make payments using both UPI and a credit card simultaneously in the split bill pop-up | High | Verify The user cannot make payments using both UPI and a credit card simultaneously in the split bill pop-up | 2024-10-08 | Saikumar
9 | QRPM-97 |  |  |  |  | POS-Initiate Pay: An error message is displayed after the transaction is cancelled | Critical | Verify An error message is displayed after the transaction is cancelled | 2024-10-08 | Saikumar
10 | QRPM-98 |  |  |  |  | POS-Initiate Pay: Given value and error message not getting clear while click Initiate Pay button | High | Verify Given value and error message not getting clear while click Initiate Pay button | 2024-10-08 | Saikumar
11 | QRPM-99 |  |  |  |  | Unwanted content display in Error message | Low | Verify Unwanted content display in Error message | 2024-10-08 | Saikumar
12 | QRPM-100 |  |  |  |  | POS-Initiate Pay: User can create bill without click Initiate Pay | Critical | Verify User can create bill without click Initiate Pay | 2024-10-08 | Saikumar