## WBS
Work Breakdown Structure
Testing | Test Case
|  |  | Task | Hrs | Status of Task
|  |  | Requirement Gathering and Understanding | 2 | In-Progress
0 | 0 |  | Test case preparation | 62 | In-Progress
|  |  | Configuration | 1 | Yet To Start
|  |  | Iteration-1 Testing | 78 | Yet To Start
|  |  | Test Document Preparation | 5 | Yet To Start
|  |  | Bug Verification | 10 | Yet To Start
|  |  | Closure Testing | 40 | Yet To Start
|  |  | Total | 198
Optical CRM
|  | S.No | Module Name | Test case Hours | Testing-1 Hours | Bug Verification Hours | Closure Testing Hours | Test Case Status | Testing Status | Bug Verification Status | Start Date | End Date
|  | 1 | Add Optical Items | 4 | 5.5 | 1 | 2.5 | YTS | YTS | YTS
|  | 2 | Optical Rate Details | 4 | 5 | 1 | 2.5 | YTS | YTS | YTS
|  | 3 | Optical Rate History | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
|  | 4 | Add Purchase | 5 | 5.5 | 1 | 2.5 | YTS | YTS | YTS
|  | 5 | Purchase History | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
|  | 7 | Add Branch Transfer | 6 | 6.5 | 1 | 2.5 | YTS | YTS | YTS
|  | 8 | Branch Transfer Approval | 4.5 | 5 | 1 | 2.5 | YTS | YTS | YTS
|  | 9 | Branch Transfer History | 4 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
|  | 10 | Branch Inward Status | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
|  | 11 | Overall Stock movement Details | 3 | 6 | 1 | 2.5 | YTS | YTS | YTS
|  | 12 | Warehouse Stock Movement | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
|  | 13 | Branch Stock Movement | 3.5 | 4 | 1 | 2.5 | YTS | YTS | YTS
|  | 14 | Purchase Report | 3.5 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
|  | 15 | Transfer Report | 3 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
|  | 16 | Sales Report | 2.5 | 4.5 | 1 | 2.5 | YTS | YTS | YTS
|  |  | Total | 57 | 71.5 | 15 | 37.5
|  | S.No | Module Name | Testing & Bug posting Status | Target to complete Testing & Bug posting | Test Case count | Bugs count | Bug Verifcation
|  | 1 | Add Optical Items | YTS | 2024-11-12 | 100 | 62 | 2024-12-11
|  | 2 | Optical Rate Details | YTS | 2024-11-13 | 79 | 46 | 2024-12-12
|  | 3 | Optical Rate History | YTS | 2024-11-14 | 40 | 31 | 2024-12-12
|  | 4 | Add Purchase | YTS | 2024-11-15 | 100 | 52 | 2024-12-13
|  | 5 | Purchase History | YTS | 2024-11-16 | 39 | 24 | 2024-12-16
|  | 6 | Add Branch Transfer | YTS | 2024-11-18 | 70 | 41 | 2024-12-16
|  | 7 | Branch Transfer Approval | YTS | 2024-11-19 | 46 | 26 | 2024-12-17
|  | 8 | Branch Transfer History | YTS | 2024-11-20 | 39 | 32 | 2024-12-17
|  | 9 | Category Wise Stock Movement | YTS | 2024-11-21 | 41 |  | 2024-12-18
|  | 10 | Warehouse Stock Movement | YTS | 2024-11-22 | 40 |  | 2024-12-18
|  | 11 | Branch Stock Movement | YTS | 2024-11-23 | 41 |  | 2024-12-19
|  | 12 | Purchase Report | YTS | 2024-11-25 |  |  | 2024-12-19 | Tentative Count--50
|  | 13 | Transfer Report | YTS | 2024-11-26 |  |  | 2024-12-19 | Tentative Count--55
|  | 14 | Prescription Entry | YTS | 2024-11-27 |  |  | 2024-12-20 | Tentative Count--60
|  | 15 | Prescription List | YTS | 2024-11-28 |  |  | 2024-12-20 | Tentative Count--40
|  | 16 | Branch Inward | In-Progress | 2024-12-02 | 66 |  | 2024-12-20 | Tentative Count--35
|  | 17 | Branch Current Stock | YTS | 2024-12-03 |  |  | 2024-12-23 | Tentative Count--40
|  | 18 | Stock Movement Details | YTS | 2024-12-05 |  |  | 2024-12-23 | Tentative Count--45
|  | 19 | Billing Page or Sales Entry | YTS | 2024-12-06 |  |  | 2024-12-23 | Tentative Count--40
|  | 20 | Invoice List and Invoice Print | YTS | 2024-12-09 |  |  | 2024-12-24 | Tentative Count--30
|  | 21 | Sales Report | YTS | 2024-12-10 |  |  | 2024-12-24 | Tentative Count--40
|  | Total |  |  |  | 1070
Smoke
Functional
Ui spell check
Buttons
Error message
Success message
Broken link
Image
Navigation
Data Validation
Redirect
Compatability
Sign in Page
Automation Testing
Appium
|  |  | Work Breakdown Structure for Hr Self service modules |  |  | 8
|  |  | Task | Hrs | Status of Task | 7
|  |  | Requirement Gathering and Understanding | 5 | YTS | 6
|  |  | Test case preparation | 21 | YTS
|  |  | Configuration | 1 | YTS
|  |  | Iteration-1 Testing | 30 | YTS
|  |  | Test Document Preparation | 4 | YTS
|  |  | Bug Verification | 5 | YTS
|  |  | Closure Testing | 16 | YTS
|  |  | Total | 82
|  | S.No | Module Name | Testing & Bug posting Status | Bugs count
|  | 1 | Add Optical Items | Done | 62
|  | 2 | Optical Rate Details | Done | 46
|  | 3 | Optical Rate History | Done | 31
|  | 4 | Add Purchase | Done | 52
|  | 5 | Purchase History | Done | 24
|  | 6 | Add Branch Transfer | Done | 41
|  | 7 | Branch Transfer Approval | Done | 26
|  | 8 | Branch Transfer History | Done | 32
|  | 9 | Branch Inward | Done | 33
|  | 10 | Branch Current Stock | Done | 14
|  | 11 | Billing Page or Sales Entry | Done | 51
|  | 12 | Invoice List | Done | 19
|  | 13 | Invoice Print | Done
|  | 14 | Sales Report | Done | 24
|  | 15 | Prescription Entry | Done | 10
|  | 16 | Prescription List | Done | 24
|  | 17 | Category Wise Stock Movement | Done | 19
|  | 18 | Transfer Report | YTS
|  | 19 | Stock Movement Details | YTS
|  | 20 | Purchase Report | YTS
|  | 21 | Item Wise Stock Movement | YTS
|  | 22 | Branch Stock Movement | YTS
|  | Total |  |  | 508

## Task Status
S.No | Module Name | SS
1 | Project Detail | Yes
2 | Project Scope | Yes
3 | Business Case | Yes
4 | Technical Analysis | Yes
5 | Resource Identification and Planning | No
6 | Project Goals and Deliverables | Yes
7 | Project Backlog | Yes
8 | Initial Release Goals | Yes
9 | Milestone | Yes
10 | Product Backlog Refinement | Yes
11 | Sprint Planning | Yes
12 | Development Cycle | Yes
13 | Spring Review | Yes
14 | Internal Checklist | No
15 | Demo | No
16 | UAT (Sign off) | No
Test Case Status
S.No | Module Name | Test Case Status
1 | Project Detail | Done
2 | Project Scope | Done | In-Progress
3 | Business Case | In-Progress
4 | Technical Analysis | YTS
5 | Resource Identification and Planning | YTS
6 | Project Goals and Deliverables | YTS
7 | Project Backlog | YTS
8 | Initial Release Goals | YTS
9 | Milestone | YTS
10 | Product Backlog Refinement | YTS
11 | Sprint Planning | YTS
12 | Development Cycle | YTS
13 | Spring Review | YTS
14 | Internal Checklist | YTS
15 | Demo | YTS
16 | UAT (Sign off) | YTS
Bug Verification Status
S.No | Module Name | Bug Verification Status | Bug count
1 | Project Detail | YTS | 15
2 | Project Scope | YTS | 11
3 | Business Case | YTS | 8
4 | Technical Analysis | YTS | 14
5 | Resource Identification and Planning | YTS
6 | Project Goals and Deliverables | YTS
7 | Project Backlog | YTS
8 | Initial Release Goals | YTS
9 | Milestone | YTS
10 | Product Backlog Refinement | YTS
11 | Sprint Planning | YTS
12 | Development Cycle | YTS
13 | Spring Review | YTS
14 | Internal Checklist | YTS
15 | Demo | YTS
16 | UAT (Sign off) | YTS
17 | Category Wise Stock Movement | YTS
18 | Item Wise Stock Movement
19 | Branch Stock Movement
20 | Stock Movement Details
21 | Purchase Report
22 | Transfer Report
| Total |  | 48
2024-12-11
|  |  |  | Total Bug Details |  |  |  |  | Severity
|  |  |  | Bug Count | Close | Reopen | New |  | High | Critical
|  |  |  | 10 | 7 | 3 | 0 |  | 9 | 1
2024-12-12
|  |  |  | Total Bug Details |  |  |  |  | Severity
|  |  |  | Bug Count | Close | Reopen | New | Hold | High | Critical
|  |  |  | 16 | 6 | 5 | 2 | 3 | 15 | 1

## Bug Verification
|  | S.No | Bug ID | Add Optical Item-Bug Title | Severity | Status | Remarks
Close | Re-open | Not Tested | Total
S.No | Version | Dev | Main Module | Sub Module | UI Completion Status | KT status
1 | 1.0.0 | Bharathy & Mosik | Project Details | - | Ready for Test Case | Done
4 | 1.0.0 | Mosik & Sedhu | Project Overview | Project Scope | Ready for Test Case | Done
5 | 1.0.0 | Mosik & Sedhu |  | Business Case | Ready for Test Case | Done
6 | 1.0.0 | Mosik & Sedhu | Technical Feasibility and Resource Planning | Technical Analysis | Ready for Test Case | Done
7 | 1.0.0 | Mosik & Sedhu |  | Resource Identification and Planning | Ready for Test Case | Done
8 | 1.0.0 | Bharathy & Mosik |  | Project Goals and Deliverables | Ready for Test Case | Done
9 | 1.0.0 | Bharathy & Mosik | Milestones and Deadline | Project Backlog | Ready for Test Case | Done
10 | 1.0.0 | Bharathy & Mosik |  | Initial Release Goals | Ready for Test Case | Done
11 | 1.0.0 | Bharathy & Mosik |  | Milestone | Ready for Test Case | Done
12 | 1.0.0 | Bharathy & Mosik | Agile Development Plan | Product Backlog Refinement | UI Correction Pending | Pending
13 | 1.0.0 | Bharathy & Mosik |  | Sprint Planning | UI Correction Pending | Pending
13 | 1.0.0 | Bharathy & Mosik |  | Development Cycle | Ready for Test Case | Done
14 | 1.0.0 | Bharathy & Mosik |  | Spring Review | Ready for Test Case | Done
14 | 1.0.0 | Bharathy & Mosik | Demo and UAT (Sign off) | Internal Checklist | Ready for Test Case | Done
15 | 1.0.0 | Bharathy & Mosik |  | Demo | Ready for Test Case | Done
16 | 1.0.0 | Bharathy & Mosik |  | UAT (Sign off) | Ready for Test Case | Done

## SS
Ui | Project Detail
Ui | Project Scope