## Bug Report
S.No | Bug Id | Department | LOB | Role | Title | Bug Description | Steps to Reproduce | Actual Result | Expected Result | Bug Severity | TCs Impacted | Bug Identified Date | Assigned to DEV | Fixed Provided by DEV | Defect Category | Defect Sub Category | Fix Status | Defect Reopened | Tentative Fix Date | Actual Fix Date | Comments To QA | Additional Remarks
1 | 539 |  |  |  | Asset Transfer | Not approved record display in Asset Transfer page | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Click the GP No. filed 3.Search Not approved Gp no. | Not approved record display in Asset Transfer page | Not approved record should not display in Asset Transfer page | Critical | 1.Check whether Not approved record display or not in Asset Transfer page |  | Bharathy
2 | 540 |  |  |  |  | Empty List grid display without any column or information message | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Verify any List grid display or not | Empty List grid display without any column or information message | Empty List grid should not display without any column or information message | High | 1.Check whether the Empty List grid display without any column or information message |  | Bharathy
3 | 541 |  |  |  |  | Screen header/title name not display properly | 1.Open the ERP application 2.Click Asset Transfer menu 3.Check the header/title value in Top of the page | Screen header/title name not display | Header/title name should display as "Asset Transfer" | High | 1.To verify the Screen header/title name display or not properly |  | Bharathy
4 | 542 |  |  |  |  | Mismatch list grid header name display | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Verify any List grid title name | List grid header name display as " Item List" | Respective name should display in List grid header | High | 1.Verfiy the Column header name |  | Bharathy
5 | 543 |  |  |  |  | Navigation section display mismatch value | Precondition: User have record in General Item master 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Verify the Navigation section value | Navigation section display "Home/GDC | Navigation section should display as "Home/ Asset Transfer" | Medium | 1.Verify the Navigation section value |  | Bharathy
6 | 544 |  |  |  |  | Mismatch GPO details display in DC challan entry list grid | Precondition: User have Auto Approval records in GPR PO screen 1.Open the ERP application 2.Navigate to DC challan page 3.Give Warehouse General PO value and click Submit button 3.Verify the item list grid | Mismatch GPO details display in DC challan entry list grid | Respective GPO details should display in DC challan entry list grid | Critical | 1.To verify Mismatch GPO details display in DC challan entry list grid |  | Bharathy
7 | 545 |  |  |  |  | Placeholder or inner text not display in Search filter text box | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No. filed 4.Verify the Placeholder or inner text display or not in Search filter | Placeholder or inner text not display in Search filter | Placeholder or inner text should display in Search filter | Low | 1.To Verify the placeholder for search filed |  | Bharathy
8 | 546 |  |  |  |  | Dot value not getting display for GP No. | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No. filed 34.Verify the GP No. lable name | Dot value not getting display for GP No. | Column name should display as "GP No." | Low | 1.To Verify dot value display for GP No. |  | Bharathy
9 | 547 |  |  |  |  | Too many spaces display between Column header and list grid column | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No. filed 3.Check the space between Column header and list grid column | Too many spaces display between Column header and list grid column | Respective space should display between Column header and list grid column | Medium | 1.To verify spaces display between Column header and list grid column |  | Bharathy
10 | 548 |  |  |  |  | List grid alignment getting collapse while zoom out the web page view | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No. filed 3.Perfoermer zoom out the web page view | List grid alignment getting colapse while zoom out the web page view | List grid alignment should display properly while zoom out the web page view | High | 1.Verify the List grid alignment while zoom out the web page view |  | Bharathy
11 | 549 |  |  |  |  | Column separator highlighted line not display in list grid | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No. filed 4.Check the Column separator highlighted line display or not | Column separator highlighted line not display in list grid | Column separator highlighted line should display in list grid | High | 1.To verify the column separator highlighted line display or not in list grid |  | Bharathy
12 | 550 |  |  |  |  | Sort icon display as too small | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No. filed 4.Verify the sort icon | Sort icon display as too small | Sort icon should display little bit big | Low | 1.Verify the Sort icon size in list grid |  | Bharathy
13 | 551 |  |  |  |  | Mismatch pop up title display | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No.value and Click edit icon in list grid 4.Verify the Pop up title | Pop up title display as Remarks | Pop up title should display as Reason for Rejection | High | 1.Verfiy the Edit and view pop up title values |  | Bharathy
14 | 552 |  |  |  |  | Close icon not display properly | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No.value and Click edit icon in list grid 5.Verify the close icon | Close icon not display properly | Close icon should display properly | Low | 1.To Verfiy Close icon display or not properly |  | Bharathy
15 | 553 |  |  |  |  | Confirmation message not display while close the pop up with all values | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No.value and Click edit icon in list grid 4.Click close button/icon with all values | Confirmation message not display while close the pop up with all values | Confirmation message should display while close the pop up with all values | High | 1.Verfiy the Confirmation message display or not while close the pop up with all values |  | Bharathy
16 | 554 |  |  |  |  | Add Department pop up getting close while click beyond the pop up | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No.value and Click edit icon in list grid 4.Click beyond the pop up | Reject pop up getting close while click beyond the pop up | Reject pop up should not close while click beyond the pop up | Medium | 1.Check whether the update pop up getting close while click beyond the pop up |  | Bharathy
17 | 555 |  |  |  |  | Tool tip not display for Close icon | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No.value and Click edit icon in list grid 4.Check the Tool tip for Close icon | Tool tip not display for Close icon | Tool tip should display as "Close" | Medium | 1.Verfiy Tool tip display or not for Close icon |  | Bharathy
18 | 556 |  |  |  |  | Placeholder or inner text not display in Item Name | 1.Open the ERP application 2.Navigate to Asset Transfer 3.Select any value in GP No.value and Click edit icon in list grid 4.Verify the Placeholder or inner text display or not in Item Name | Placeholder or inner text not display in Item Name | Placeholder or inner text should display in Item Name | Low | 1.Check whether the Placeholder or inner text display or not in Item Name |  | Bharathy
19 | 557 |  |  |  |  | Add department message display mismatch content | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Click submit button with all mandatory values | Update message display mismatch content | Respective message should be display | High | 1.Verfiy the update message content |  | Bharathy
20 | 558 |  |  |  |  | Add department success message display without update any value | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Click submit button without change any value | Updated success message display without update any value | "No changes" message should be display | High | 1.To Verfiy the updated success message display or not without update any value |  | Bharathy
21 | 559 |  |  |  |  | Add department pop up not getting close while create the record | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Click submit button with all mandatory values | Add department pop up not getting close while create the record | Add department pop up should close while create the record | High | 1.To Verfiy the Add department pop up not getting close or not while create the record |  | Bharathy
22 | 560 |  |  |  |  | Required error message not display | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 3.Skip all required filed and click submit button | Required error message not display | System should display required message as " Item Description required, Add Quantity required and Department required" | High | 1.To Verfiy Required error message display or not |  | Bharathy
23 | 561 |  |  |  |  | Mismatch button name display in Add department pop up | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 3.Check the submit button name | Button name display as update | Button name should display as Create | High | 1.To Verfiy the Mismatch button name display in Add department pop up |  | Bharathy
24 | 562 |  |  |  |  | Unit and Department filed display value while click edit icon | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 3.Give required value and click submit button 5.Clikc close icon and and Click edit icon in list grid | Unit and Department filed display value while click edit icon | Button name should display as Create | High | 1.To Verfiy the Unit and Department filed display value while click edit icon |  | Bharathy
25 | 563 |  |  |  |  | Negative number display in Add department pop up | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 3.Click down arrow in Amount and GST filed | Negative number dislay in Add department pop up | Negative number should not dislay in Add department pop up | Medium | 1.Verfiy the negative number allow in Add department pop up |  | Bharathy
26 | 564 |  |  |  |  | Unwanted error message display while click submit button with Net amount as empty | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Give mandatory value 5.click submit button with Net amount as empty | Unwanted error message display while click submit button with Net amount as empty | Required error message should display | High | 1.Verfiy the error message display while click submit button with Net amount as empty |  | Bharathy
27 | 565 |  |  |  |  | Amount field value automatically getting change while update the GST field value | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Give mandatory values and update the Amount value 5.Give GST value and click any other field | Amount field value automatically getting change while update the GST field value | Amount field value should not change | High | 1.To Verfiy Amount field value automatically getting change while update the GST field value |  | Bharathy
28 | 566 |  |  |  |  | Amount field’s allow Alphabets and special characters | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4..Give Alphabets and special characters in Amount, GST and Net Amount filed | Amount filed's allow Alphabets and special characters | Amount filed's should not allow Alphabets and special characters | High | 1.To Verfiy Amount field’s allow Alphabets and special characters |  | Bharathy
29 | 567 |  |  |  |  | Item Description filed allow more than 1000 characters | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4..Give 1000 characters in Item Description | 1.Item Description filed allow more than 1000 characters 2.Issue in all text fileds | Item Description filed should not allow more than 500 characters | High | 1. Check whether the Item Description filed allow more than 1000 characters |  | Bharathy
30 | 568 |  |  |  |  | Mismatch value display in Net Amount filed, which Auto calculation not working properly | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4..Give 1 value in Add Quantity filed 5.Update the Amount filed value | Mismatch value display in Net Amount filed, which Auto calculation not working properly | Respective value should display in Net Amount filed, based on Auto calculation | High | 1.Verfiy Net Amount filed, which Auto calculation working or not |  | Bharathy
31 | 569 |  |  |  |  | Exiting Unit, Department and Sub Department value display while click edit icon | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4..Give Unit, Department and Sub Department value 5.Click close icon 6.Again click edit icon | 1.Exiting Unit, Department and Sub Department value display while click edit icon 2.Issue in upload document also | Unit, Department and Sub Department value should display as empty | High | 1.To Verfiy Exiting value display while click edit icon |  | Bharathy
32 | 570 |  |  |  |  | User can able to upload any document | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Perform upload any document | 1.User can able to upload any document 2.Upload instriction message not display | System should allow to upload only image | High | 1.Verfiy user can able to upload any document |  | Bharathy
33 | 571 |  |  |  |  | System allow to upload 30 mb file | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Perform upload 30 mb file | System allow to upload 30 mb file | System should allow to upload 30 mb file | High | 1.To Verfiy System allow to upload 30 mb file |  | Bharathy
34 | 572 |  |  |  |  | File path display while upload the file | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Perform upload any document | File path display while upload the file | File path should notdisplay while upload the file | High | 1.Verfiy File path display or not while upload the file |  | Bharathy
35 | 573 |  |  |  |  | View button not working in upload section | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Perform upload any document 5.Click view button in upload | View button not working in upload section | View button should be working in upload section | High | 1.To Verfiy View button working or not in upload section |  | Bharathy
36 | 574 |  |  |  |  | Uploaded document not display in edit pop up | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Perform upload any document 5.Give mandatory value and click submit button 6.Click edit icon for same record added list grid | Uploaded document not display in edit pop up | Uploaded document should display in edit pop up | High | 1.Verfiy Uploaded document display or not in edit pop up |  | Bharathy
37 | 575 |  |  |  |  | Mismatch section title display in Add department pop up | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Check the departmnet section title | Mismatch section title display in Add department pop up | Respective section title should display in Add department pop up | High | 1.To Verfiy the title display in Add department pop up |  | Bharathy
38 | 576 |  |  |  |  | Quantity greater than error message display | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Perfrom the add department value with maximum Quantity 5.Again Click edit icon in list grid 5.Give quantity value | Quantity greater than error message display | Quantity greater than error should be message display | Medium | 1.Verfiy the Quantity greater than error message display |  | Bharathy
39 | 577 |  |  |  |  | Unable to update rate value in department pop up | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value and Click edit icon in list grid 4.Perfrom the add department value 5.Click edit icon for same record added list grid | Unable to update rate value in department pop up | System should allow to update rate value in department pop up | High | 1.Verfiy able to update rate value in department pop up |  | Bharathy
40 | 578 | [5 empty] | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click edit icon for same record added list grid 6.Update quantity value and click update button | Amount value display as 0 while update the quantity value | Amount value should display the rescpective value | High | 1.To Verfiy Amount value display as 0 while update the quantity value |  | Bharathy
41 | 579 | [5 empty] | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click edit icon for same record added list grid 6.Perform upload any document | Unable to upload the file in add department edit pop up | System should allow to upload the file in add department edit pop up | High | 1.To Verfiy able to upload the file in add department edit pop up |  | Bharathy
42 | 580 |  |  |  |  | User can able to give values in all field value in view pop up | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click the view button for any record 6.Check the fields display as read-only or editable | User can able to give values in all field when click view button | System should not allow to give values in all field when click view button | Medium | 1.Check whether user can able to give values in all field value in view pop up 2.Verify the all fields display as read-only while open the view pop up |  | Bharathy
43 | 581 |  |  |  |  | First letter display as small letter in tool tip | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 4.Check the Tool tip for view and close icon | First letter display as small letter in tool tip | First letter should display as Capital letter in tool tip | Low | 1.Verfiy tool tip value for edit and view icon |  | Bharathy
44 | 582 |  |  |  |  | System allow to create the duplicate records | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 3.Perfrom add 1 Department and subdepartment record 4.Again create same Department and subdepartment record | System allow to create the duplicate records | System should not allow to create the duplicate records | High | 1.To Verfiy system allow ro approve multiple time for the same record |  | Bharathy
45 | 583 |  |  |  |  | Updated success message display without update any value | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click edit icon for same record added list grid 6.Click update button | Updated success message display without update any value | "No changes" message should be display | High | 1.To Verfiy the updated success message display or not without update any value |  | Bharathy
46 | 584 |  |  |  |  | Mismatch content display for the Delete confirmation pop up | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click Delete icon in list grid | Confirmation message should display as "Are you sure?" | Confirmation message should display as "Are you sure you want to delete this item ?" | Medium | 1.Verfiy Delete confirmation content |  | Bharathy
47 | 585 |  |  |  |  | Delete message display mismatch content | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click Delete icon in Department list grid 6.Click Yes button in confirmation record | Delete message display mismatch content | Delete message should be display as "<Department name > record has been successfully deleted" | Medium | 1.To Verfiy Delete message display mismatch content |  | Bharathy
48 | 586 |  |  |  |  | Mismatch title display in delete pop up | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click Delete icon in Department list grid 6.Check the pop up title | Pop up title display as "app.qnqpharmacy.com" | Pop up title should be display as "Confirmation" | Medium | 1.To Verfiy delete pop up title value |  | Bharathy
49 | 587 |  |  |  |  | Unwanted content display while click delete icon | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click Delete icon in Department list grid 6.Click cancel button in confirmation pop up 7.Again click delete icon and | Below mentioned content display while click delete icon "Don't allow app.qnqpharmacy.com to promt you again" | Error message should not display | Medium | 1.To Verfiy content display while click delete icon |  | Bharathy
50 | 588 |  |  |  |  | Error message display while click Ok button in icon | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add more than 2 department value 5.Perfrorm Delete any one record 6.Again clikc delete icon | Below mentioned content should not display while click delete icon "An error occurred" | Error message should not display | High | 1.Check whether the error message display or not while click Ok button in icon |  | Bharathy
51 | 589 |  |  |  |  | Department details not display in Fixed asset page | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add more than 2 department value 5.Perfrorm move asset 6.Navigate to Fixed Asset page 7.Check the Department details | Department details not display in Fixed asset page | Department details should display in Fixed asset page | High | 1.Verfiy department details display or not in Fixed asset page |  | Bharathy
52 | 590 |  |  |  |  | Purchase cost display as empty while perfrom asset moved | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add more than 2 department value 5.Perfrorm move asset 6.Navigate to Fixed Asset page 7.Check the Purchase cost | Purchase cost display as empty while perfrom asset moved | Respective Purchase cost should display | High | 1.Check whetherPurchase cost display the value |  | Bharathy
53 | 591 |  |  |  |  | Updated message display mismatch content | 1.Open the ERP application 2.Navigate to Asset Transfer page 3.Select any value in GP No.value 4.Perfrom the add department value 5.Click edit icon in Department list grid 6.Perfrom updated record | Delete message display mismatch content | Delete message should be display as "<Department name > record has been successfully deleted" | Medium | 1.Verfiy Updated message mismatch content |  | Bharathy