## WBS
Work Breakdown Structure
| Testing | Test Case
| 10 | 8 | Thought for the day
| 10 | 7 | Policies | Task | Hrs | Status of Task
| 10 | 6 | Training | Requirement Gathering and Understanding | 2.5 | Done
Total | 30 | 21 |  | Test case preparation | 4 | Yet To Start
|  |  |  | Configuration | 1 | Yet To Start
|  |  |  | Iteration-1 Testing | 8 | Yet To Start
|  |  |  | Test Document Preparation | 2 | Yet To Start
|  |  |  | Bug Verification | 1 | Yet To Start
|  |  |  | Closure Testing | 5 | Yet To Start
|  |  |  | Total | 23.5
|  |  |  | Module Name | Test case Hours | Test Case Status | Testing Hours | Testing Status
|  |  |  | Stock Dashboard | 5 | Yet To Start | 6 | Yet To Start
|  |  |  | Po Pending Dashboard | 4 | Yet To Start | 6 | Yet To Start
|  |  |  | Total | 9 |  | 12
|  |  |  | Work Breakdown Structure for RFQ Details |  |  | 8
|  |  |  | Task | Hrs | Status of Task | 7
|  |  |  | Requirement Gathering and Understanding | 2.5 | Done | 6
|  |  |  | Test case preparation | 4 | Yet To Start
|  |  |  | Configuration | 1 | Yet To Start
|  |  |  | Iteration-1 Testing | 8 | Yet To Start
|  |  |  | Test Document Preparation | 2 | Yet To Start
|  |  |  | Bug Verification | 1 | Yet To Start
|  |  |  | Closure Testing | 5 | Yet To Start
|  |  |  | Total | 23.5
|  |  |  | Days | Hrs | Status
|  |  |  | 10/sep(Test start from after 12 Pm) | 4 | Yet To Start
|  |  |  | 11/sep(Wednesday) | 8 | Yet To Start | Release the Thought of the day bug report
|  |  |  | 12/sep(Thursday) | 8 | Yet To Start
|  |  |  | Friday | 8 | Yet To Start | Release the Policies
|  |  |  | Saturday | 2 | Yet To Start
|  |  |  | Total | 30