## WBS
Work Breakdown Structure
| Testing | Test Case
| 10 | 8 | Thought for the day
| 10 | 7 | Policies | Task | Hrs | Status of Task
| 10 | 6 | Training | Requirement Gathering and Understanding | 2.5 | Done
Total | 30 | 21 |  | Test case preparation | 8 | In-Progress
|  |  |  | Configuration | 2 | Yet To Start
|  |  |  | Iteration-1 Testing | 12 | Yet To Start
|  |  |  | Test Document Preparation | 3 | Yet To Start
|  |  |  | Bug Verification | 2 | Yet To Start
|  |  |  | Closure Testing | 7 | Yet To Start
|  |  |  | Total | 36.5
|  |  |  | Module Name | Test case Hours | Test Case Status | Testing Hours | Testing Status
|  |  |  | Stock Dashboard | 5 | Yet To Start | 6 | Yet To Start
|  |  |  | Po Pending Dashboard | 4 | Yet To Start | 6 | Yet To Start
|  |  |  | Total | 9 |  | 12
|  |  |  | Work Breakdown Structure for Hr Self service modules |  |  | 8
|  |  |  | Task | Hrs | Status of Task | 7
|  |  |  | Requirement Gathering and Understanding | 2.5 | Done | 6
|  |  |  | Test case preparation | 8 | In-Progress
|  |  |  | Configuration | 2 | Yet To Start
|  |  |  | Iteration-1 Testing | 12 | Yet To Start
|  |  |  | Test Document Preparation | 3 | Yet To Start
|  |  |  | Bug Verification | 2 | Yet To Start
|  |  |  | Closure Testing | 7 | Yet To Start
|  |  |  | Total | 36.5
|  |  |  | Days | Hrs | Status
|  |  |  | 10/sep(Test start from after 12 Pm) | 4 | In-progress
|  |  |  | 11/sep(Wednesday) | 8 | Yet To Start | Release the Thought of the day bug report
|  |  |  | 12/sep(Thursday) | 8 | Yet To Start
|  |  |  | Friday | 8 | Yet To Start | Release the Policies
|  |  |  | Saturday | 2 | Yet To Start
|  |  |  | Total | 30

## Sheet1
The Federal Bureau of Investigation is the domestic intelligence and security service of the United States and its principal federal law enforcement agency. An agency of the United
Federal Bureau of Investigation
d