## WBS
Work Breakdown Structure
| Testing | Test Case
| 10 | 8 | Thought for the day
| 10 | 7 | Policies | Task | Hrs | Status of Task
| 10 | 6 | Training | Requirement Gathering and Understanding | 5 | Done
Total | 30 | 21 |  | Test case preparation | 21 | Done
|  |  |  | Configuration | 1 | Yet To Start
|  |  |  | Iteration-1 Testing | 30 | In-Progress
|  |  |  | Test Document Preparation | 4 | Yet To Start
|  |  |  | Bug Verification | 5 | Yet To Start
|  |  |  | Closure Testing | 16 | Yet To Start
|  |  |  | Total | 82
|  |  |  | Module Name | Test case Hours | Test Case Status | Testing Status
|  |  |  | Thought for the day | 8 | Yet To Start | Yet To Start
|  |  |  | Policies | 7 | Yet To Start | Yet To Start
|  |  |  | Training | 6 | Yet To Start | Yet To Start
|  |  |  | Total | 21
Smoke
Functional
Ui spell check
Buttons
Error message
Success message
Broken link
Image
Navigation
Data Validation
Redirect
Compatability
Sign in Page
Automation Testing
Appium
|  |  |  | Work Breakdown Structure for Hr Self service modules |  |  | 8
|  |  |  | Task | Hrs | Status of Task | 7
|  |  |  | Requirement Gathering and Understanding | 5 | Done | 6
|  |  |  | Test case preparation | 21 | Done
|  |  |  | Configuration | 1 | Done
|  |  |  | Iteration-1 Testing | 30 | In-progress
|  |  |  | Test Document Preparation | 4 | Yet To Start
|  |  |  | Bug Verification | 5 | Yet To Start
|  |  |  | Closure Testing | 16 | Yet To Start
|  |  |  | Total | 82
|  |  |  | Days | Hrs | Status
|  |  |  | Tuesday(Test start from after 12 Pm) | 4 | In-progress
|  |  |  | Wednesday | 8 | Yet To Start | Release the Thought of the day bug report
|  |  |  | Thursday | 8 | Yet To Start
|  |  |  | Friday | 8 | Yet To Start | Release the Policies
|  |  |  | Saturday | 2 | Yet To Start
|  |  |  | Total | 30