## WBS
Work Breakdown Structure
| Testing | Test Case
[5 empty] | Task | Hrs | Status of Task
[5 empty] | Requirement Gathering and Understanding | 2 | Done
Total | 0 | 0 |  |  | Test case preparation | 18 | In-Progress
[5 empty] | Configuration | 1 | Yet To Start
[5 empty] | Iteration-1 Testing | 25 | Yet To Start
[5 empty] | Test Document Preparation | 3 | Yet To Start
[5 empty] | Bug Verification | 3 | Yet To Start
[5 empty] | Closure Testing | 10 | Yet To Start
[5 empty] | Total | 62
Test Case
|  |  |  | S.No | Module Name | Test case Hours | Test Case Status | Testing Status | Start Date | End Date
|  |  | Existing screen available in ERP | 1 | Leave Form | 5 | Done | Done | 2024-10-01 | 2024-10-03
|  |  | Existing screen available in ERP | 2 | Manager Leave Approval Page | 3 | Done | Done | 2024-10-03 | 2024-10-03
|  |  | Existing screen available in ERP | 3 | HR Leave Approval Page | 2 | Done | Done | 2024-10-03 | 2024-10-04
|  |  | Existing screen available in ERP | 4 | Leave balance tracking | 3 | Done | Done | 2024-10-04 | 2024-10-04
|  |  |  | 5 | Leave Policy |  |  | Done
|  |  | Need to build | 6 | Individual Leave Summary | 3 | Done | In-progress
|  |  |  | 7 | Employee Leave Summary | 3 | Done | YTS
|  |  |  | 8 | Dashboard | 2.5 |  | Done
|  |  | Need to build | 9 | Attendance Verification | 3 | YTS | Done
|  |  |  | 10 | Salary Generator |  |  | Done
[5 empty] | Total | 24.5
Leave application
[5 empty] | VP Approval Page |  | Smoke
[5 empty] | HR Approval Page |  | Functional
[5 empty] | Leave balance tracking |  | Ui spell check
Buttons
Error message
|  |  | Dashboard |  | Reporting and analytics |  | Success message
|  |  | Leave Summary for Reporting Manager |  | Integration with payroll |  | Broken link
|  |  | Leave Summary for Indivdual Employee |  |  |  | Image
Navigation
Data Validation
Redirect
Compatability
Sign in Page
Automation Testing
Appium
[5 empty] | Work Breakdown Structure for Hr Self service modules |  |  | 8
[5 empty] | Task | Hrs | Status of Task | 7
[5 empty] | Requirement Gathering and Understanding | 5 | YTS | 6
[5 empty] | Test case preparation | 21 | YTS
[5 empty] | Configuration | 1 | YTS
[5 empty] | Iteration-1 Testing | 30 | YTS
[5 empty] | Test Document Preparation | 4 | YTS
[5 empty] | Bug Verification | 5 | YTS
[5 empty] | Closure Testing | 16 | YTS
[5 empty] | Total | 82
[5 empty] | Days | Hrs | Status
[5 empty] | Tuesday(Test start from after 12 Pm) | 4 | In-progress
[5 empty] | Wednesday | 8 | Yet To Start | Release the Thought of the day bug report
[5 empty] | Thursday | 8 | Yet To Start
[5 empty] | Friday | 8 | Yet To Start | Release the Policies
[5 empty] | Saturday | 2 | Yet To Start
[5 empty] | Total | 30

## Sheet4
Work Breakdown Structure
Task | Hrs | Status of Task | 12 Modules
Requirement Gathering and Understanding | 4 | Yet To Start | Test Case | 8 days | 60 Hours
Test case preparation | 18 | Yet To Start | Testing | 13 days | 100 Hours
Configuration | 3 | Yet To Start
Iteration-1 Testing | 22 | Yet To Start
Test Document Preparation | 3 | Yet To Start
Bug Verification | 4 | Yet To Start | Completed Modules | 4
Closure Testing | 11 | Yet To Start | Yet to start | 7
Total | 65 |  | In-progress | 1