## Sheet1
S.No | Bug Id | Bug Title | Reproduce Steps | Actual Result | Expected Result | Bug Severity | DEV Status | DEV Remarks | QA Status
1 |  | Sort icon display as already sorted highlighted, when there is no record in list grid | 1.Open the Emp Service Portal application 2.Click policies menu 3.Verify the sort icon | Sort icon display as already sorted highlighted, when there is no record in list grid | Sort icon should display as sorted highlighted | Low | Not Fixed | Data table plugin default feature | Close | Bug closed following the feedback from the development team
2 |  | Policies record getting save without upload valid file | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Give all values 5.Attach file without click upload button 6.Click submit button | Polocies record getting save without upload valid file | Polocies record should not save without upload valid file | High | Fixed | The Document is Optional | Close | It's working exactly as it should
3 |  | Attached document display while click the edit icon, which document not getting upload | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Give all values 5.Attach file without click upload button 6.Click submit button and click the edit icon | Polocies record getting save without upload valid file | Polocies record should not save without upload valid file | High | Fixed | This Option Not available | Close | It's working exactly as it should
4 |  | Created record not display in the policies list grid | 1.Open the Emp Service Portal application 2.Click policies menu and click add policies button 3.Give all values 4.Attach file without click upload button 5.Click submit button and click edit button 6.Close the pop up and Perform delete the record 6.Click add policies button and click submit button | Created record not display in the policies list grid | Created record should display in the policies list grid | High | Fixed |  | Close | It's working exactly as it should
5 |  | Attached File display when upload file in another record | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click edit icon for first record 4.Attach file without click upload button 5.Click submit button 6.Click edit button for 2nd and 3 rd record 6.Verify any file display or not | Attached File display which upload in another record | Attached File should not display which upload in another record | High | Fixed |  | Close | It's working exactly as it should
6 |  | Confirmation message not display while click close with upload file and all values | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 3.Give all values in pop up 4.Attach file and click upload button 5.Click close icon | Confirmation message not display while click close with upload file and all values | Confirmation message should display as "Do you want to close the pop up" | medium | Fixed | Validation And Pop added. | Close | It's working exactly as it should
7 |  | Uploaded file getting vanish open the saved record | 1.Open the Emp Service Portal application 2.Click policies menu and click add policies button 3.Give all values in pop up with uploaded file 4.Click submit button 5.Navigate to Policies Details page 6.Again Navigate to Policies page 7.Click edit icon for same record | Uploaded file getting vanish | Uploaded file should display | High | Not Fixed. | Option not available in admin LTE | Re-open | Issue has been reopen for same mentioned steps
8 |  | File uploaded success message display without upload the file | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 3.Attach file and click upload button 5.Click again upload button | File uploaded success message display without upload the file | File uploaded success message should not display without upload the file | medium | Fixed | Validation added. | Close | It's working exactly as it should
9 |  | File upload required error message not display | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 3.Attach any valid file 5.Click submit button | File upload required error message not display | File upload required error message should be display | medium | Not Fixed | File Upload is Optional | Close | Bug closed based on dev comments
10 |  | System not allow to upload more than 1 file | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 3.Perfrom upload more than 1 file | System not allow to upload more than 1 file | System should allow to upload more than 1 file | High | Fixed | Validation added. | Re-open | Unable to upload more than 1 file
11 |  | System allow to upload more than 50 mb file | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 3.Perfrom upload more than 50 mb file | System allow to upload more than 50 mb file | System should not allow to upload more than 50 mb file | High | Fixed | Validation added. | Re-open | System loading for long time while upload more than 20 mb file
12 |  | System allow to upload any file | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 3.Perfrom any file(Exe, Json) | System allow to upload Exe, Json file | System should not allow to upload any file | High | Fixed | Only PDF file is allowed | Re-open | System should allow PDF, Word, Excel, CSV JPG and PNG
13 |  | Created policy record not display in policy details page | 1.Open the Emp Service Portal application 2.Click policies menu 3.Create policy record with future date 4.Navigate to Policy Details page 5.Verify the created record display in Policy Details page | Created policy record not display in policy details page | Created policy record should display in policy details page | Medium | Not Fixed | Policy details should display less than or equal to current date | Close | Bug closed based on dev comments
14 |  | Screen header/title name not display | 1.Open the Emp Service Portal application 2.Click policies menu 3.Check the header/title value in Top of the page | Screen header/title name not display | Header/title name should display as "policies" | High | Fixed | Title added. | Close | It's working exactly as it should
15 |  | Mismatch menu icon display for policies | 1.Open the Emp Service Portal application 2.Check the policies menu icon | Mismatch menu icon display for policies | Respective menu icon should be display | Low | Fixed |  | Close | It's working exactly as it should
16 |  | Dot value not getting display for S.No. | 1.Open the Emp Service Portal application 2.Click policies menu 3.Check the S.No. spelling | Dot value not getting display for S.No. | Column name should display as "S.No." | Low | Fixed | Dot added | Close | It's working exactly as it should
17 |  | Page Count dropdown not available in policies | 1.Open the Emp Service Portal application 2.Click policies menu 3.Check the Page Count dropdown display or not | Page Count dropdown not available in policies | Page Count dropdown should available in policies | High | Fixed | Length change option added. | Close | It's working exactly as it should
18 |  | Column header name not display in the middle of the column | 1.Open the Emp Service Portal application 2.Click policies menu 3.Check the Column header alignment | Column header name not display in the middle of the column, which display with improper alignment | Column header name should display in the middle of the column, which should display with proper alignment | Low | Fixed | CSS added. | Close | It's working exactly as it should
19 |  | Sort icon not display in the properly | 1.Open the Emp Service Portal application 2.Click policies menu 3.Check the Column header alignment | Sort icon not display properly, which display with improper alignment | Sort icon should display properly, which should display in center alignment | Low | Not Fiexd | Data table plugin default feature | Close | Bug closed based on dev comments
20 |  | Too many space display between Add new button and list grid column | 1.Open the Emp Service Portal application 2.Click policies menu 3.Check the space between Add new button and list grid column | Too many space display between Add new button and list grid column | Respective space should display between Add new button and list grid column | Low | Fixed | CSS added. | Close | It's working exactly as it should
21 |  | Placeholder or inner text not display in Search filter | 1.Open the Emp Service Portal application 2.Click policies menu 3.Verify the Placeholder or inner text display or not in Search filter | Placeholder or inner text not display in Search filter | Placeholder or inner text should display in Search filter | Low | Fixed | Plaseholder added. | Close | It's working exactly as it should
22 |  | Required error message not getting display while click submit button | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button and click submit button 4.Click submit button | Required error message not getting display while click submit button | System should display error message as "Title required", "Description required", "Date of Presentation required" | Medium | Fixed | Validation added. | Close | It's working exactly as it should
23 |  | Required error message not getting display while skip the field | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Click Title field and click any other field in pop up | Required error message not getting display while skip the field | System should display error message as "Title required" | Medium | Fixed | Validation added. | Close | It's working exactly as it should
24 |  | Title field allow more than 50 characters | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Give more than 20 characters in Title field | Title field allow more than 50 characters | Title field should not allow more than 20 characters | Medium | Fixed | Validation added for Allow Maximum 100 characters. | Close | It's working exactly as it should
25 |  | Description field allow more than 100 characters | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Give more than 20 characters in Description field | Description field allow more than 50 characters | Description field should not allow more than 20 characters | Medium | Fixed |  | Close | It's working exactly as it should
26 |  | Date Of Presentation field not allow to perform copy & paste | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Copy & paste the valid value in Date Of Presentation | Date Of Presentation field not allow to perform copy & paste | Date Of Presentation field should allow to perform copy & paste | Medium | Not Fixed |  | Deffered | The fix isn't being accepted by the plugin functionality
27 |  | Title field allow special characters | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Give the valid value in Date Of Presentation | Title field allow special characters | Title field should not allow special characters except(Hyphen, Underscore, open bracket and close bracket) | Medium | Fixed |  | Close | It's working exactly as it should
28 |  | Policies column display improper alignment while give maximum value in Description field | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Give all values in the pop up 5.Click submit button | policies column display improper alignment | Proper alignment should be display in list grid | Medium | Fixed |  | Re-open | Issue has been reopen for same mentioned steps
29 |  | Placeholder or inner text not display in Add policies pop up fields | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Verify the Placeholder or inner text display or not in policies pop up all fields | Placeholder or inner text not display in policies pop up all fields | Placeholder or inner text should display in Search filter | Low | Fixed | Placeholder added. | Close | It's working exactly as it should
30 |  | Description field display resized alignment, while click the add new button | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Alter or realign the Description field 5.Click the close icon and click Add new button | Description field display resized alignment, while click the add new button | Description field should display respective alignment, while click the add new button | Medium | Fixed |  | Close | It's working exactly as it should
31 |  | Red Colour highlight indication not getting clear while give the value in same field | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Click submit button and give all mandatory value | Red Colour highlight indication not getting clear while give the value in same field | Red Colour highlight indication should not display while give the value in same field | Medium | Fixed | Validation added. | Close | It's working exactly as it should
32 |  | Success message display mismatch content | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button 4.Click submit button with all mandatory values | Success message display mismatch content | Success message should be display as "policies <Title name >record has been created successfully" | Medium | Fixed | Validation added. | Re-open | Space not display in success message Title and message
33 |  | Update message display mismatch content | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click edit icon in policies list grid 4.Click submit button with all mandatory values | Update message display mismatch content | Update message should be display as "policies <Title name >record has been Updated successfully" | Medium | Fixed | Validation added. | Re-open | Space not display in success message Title and message
34 |  | Delete message display mismatch content | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Delete icon in policies list grid 4.Click Yes button in confirmation record | Delete message display mismatch content | Delete message should be display as "<Title name > record has been successfully deleted" | Medium | Fixed | Validation added. | Re-open | Space not display in success message Title and message
35 |  | Mismatch title display in delete pop up | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Delete icon in policies list grid 4.Check the pop up title | Pop up title display as "app.qnqpharmacy.com" | Pop up title should be display as "Confirmation" | Medium | Not fixed | Common function | Re-open | Space not display in success message Title and message
36 |  | Unwanted content display while click delete icon | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Delete icon in policies list grid 4.Click cancel button in confirmation pop up 5.Again click delete icon and | Below mentioned content display while click delete icon "Don't allow app.qnqpharmacy.com to promt you again" | Below mentioned content should not display while click delete icon "Don't allow app.qnqpharmacy.com to promt you again" | Medium | Not fixed | discusse with lead | Close | It's working exactly as it should
37 |  | Existing value display while click add new button | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click edit icon in policies list grid 4.Click close icon without change any value 5.Click add new button | Existing value display while click add new button | New page should be display without any value | High | Fixed | Validation added. | Close | It's working exactly as it should
38 |  | Updated success message display without update any value | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click edit icon in policies list grid 4.Click submit button without change any value | Updated success message display without update any value | "No changes" message should be display | Medium | Fixed | With out any change don't all to submit | Close | It's working exactly as it should
39 |  | Given value not getting clear while reopen the record without save the record when 1 st time open the record | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click close icon with give any value - (Issue-1) 5.Again click add new button - (Issue-2) | Given value not getting clear while reopen the record | Issue-1->Confirmation pop up should be display as "Are you want to close the record with changes" Issue-2->Previously given vague should not display, when without save the record | High | Fixed | Validation added. | Close | It's working exactly as it should
40 |  | Unable to create or update any record, while close the Insert Link/Image/video pop up | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click Insert Link/Image/video button in Description field 5.Click close in Link/Image/video pop up 6.Perfrom create the record | Screen getting freeze while click close icon in pop up and all fields and button display as read-only | Screen should to freeze while click the pop up and all fields and button should display as editable | Critical | Removed |  | Close | Bug closed based on dev comments
41 |  | Mismatch tool tip display for screen view mode | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click full screen button in Description field 5.Check the tool tip for minimize screen icon | Tool tip display for "Full screen" | Tool tip should display as "Minimize Full screen / Exist Full screen" | Low | Removed |  | Close | Bug closed based on dev comments
42 |  | New URL not getting load same page when uncheck the open in new window | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click Link URL and give all value 5.Uncheck the Open in new window check box and Click Insert link 6.Click the URL in description field | New URL not getting load same page when uncheck the open in new window | New URL should load in same page when uncheck the open in new window | Medium | Removed |  | Close | Bug closed based on dev comments
43 |  | Given URL not getting clear while unlink the URL | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click Link URL and give all value 5.Click Insert link and click the URL in description field 6.Click again the link value in description field 7.Click unlink icon and click the insert icon in the description field | Given URL not getting clear while unlink the URL | Given URL should not display while unlink the URL | Medium | Removed |  | Close | Bug closed based on dev comments
44 |  | System not display any error message while give less than current date | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Give less than current date in Date of presentation field | System not display any error message while give less than current date | Date of presentation should display error message while give less than current date | Medium | Not Fiexd | Discusse with Lead | Close | Bug closed based on dev comments
45 |  | Callender pop up getting close while click the clear button | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click calendar icon and click the clear button | Callender pop up getting close while click the clear button | Callender pop up should not close while click the clear button | Medium | Not Fixed | Date Picker Plugin functionality so don’t override. Contact to lead. | Close | Bug closed based on dev comments
46 |  | Record save with only space value | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Give space alone for Title and description field and give date value 5.Click submit button | Record save with only space value | Record should not create only with space value | High | Fixed | Validation added. | Close | It's working exactly as it should
47 |  | UI getting collapse while click code view icon | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click Full screen button in Description field 5.Click code view icon and click again code view icon | UI getting collapse while click code view icon | UI should not collapse while click code view icon | High | Removed |  | Close | Bug closed based on dev comments
48 |  | Red Colour highlight indication display clear while click add new button | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click add policies button and click submit button 4.Click close icon without give any value in the pop up 5.Click Again the Add policies button | Red Colour highlight indication not getting clear while click add new button | Red Colour highlight indication should not display | Medium | Fixed | Validation Added. | Close | It's working exactly as it should
49 |  | Mismatch content display for the Delete confirmation pop up | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Delete icon in list grid | Confirmation message should display as "Are sure you want to delete?" | Confirmation message should display as "Are you sure you want to delete this item ?" | Medium | Fixed | Validation Added. | Close | It's working exactly as it should
50 |  | Pop up title display as normal label name, it’s not look like title name | 1.Open the Emp Service Portal application 2.Click policies menu 3.Verify how the pop up title display | Pop up title display as normal label name, it’s not look like title name | Pop up title should display as Bright and big | Low | Fixed | CSS added. | Close | It's working exactly as it should
51 |  | Unwanted icon display in description field | 1.Open the Emp Service Portal application 2.Click policies menu 3.Verify the Code view icon display or not | Code view icon display, which is unwanted icon for the End user | Code view icon should not display | Medium | Removed |  | Close | It's working exactly as it should
52 |  | Created new record not display in list grid | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click any edit icon in list grid 4.Give any new value in Title field, without clear existing value 5.Click close icon and click Add new button 6.Click submit button | Created new record not display in list grid | Created new record should display in list grid | High | Fixed | Validation added. | Close | It's working exactly as it should
53 |  | System allow to create the duplicate records | 1.Open the Emp Service Portal application 2.Click policies menu 3.Perfrom create the record 4.Again click add new button 5.Create record for same existing value | System allow to create the duplicate records | System should not allow to create the duplicate records | High | Fixed | Validation added. | Re-open | Issue has been reopen for same mentioned steps
54 |  | Created success message display but the created record not display in the list grid | 1.Open the Emp Service Portal application 2.Click policies menu 3.Create the Policy record 4.Click Edit icon and click close icon 5.Perfrom delete the same created record 4.Again click add new button 5.Click submit button | Created success message display but the created record not display in the list grid | Created record should display in the list grid | High | Fixed | Validation added. | Close | It's working exactly as it should
55 |  | Link/Image/video pop up getting close without click close icon | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click Insert Link/Image/video button in Description field 5.Click any place, apart from the Insert Link/Image/video pop up | Link/Image/video pop up getting close without click close icon | Link/Image/video pop up should not close | Medium | Removed |  | Close | It's working exactly as it should
56 |  | Tool tip not display for Close icon | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click Add new button in policies list grid 4.Click full screen button in Description field 5.Check the tool tip for minimize screen icon | Tool tip not display for Close icon | Tool tip should display as "Close" | Medium | Fixed | Title added. | Close | It's working exactly as it should
57 |  | Red Colour highlight indication display while click edit icon | 1.Open the Emp Service Portal application 2.Click policies menu 3.Click submit button and click close icon 4.Click edit icon | Red Colour highlight indication display clear while click edit icon | Red Colour highlight indication should not display clear while click edit icon | Medium | Fixed | Validation added. | Close | It's working exactly as it should
58 |  | Mismatch column display in Policy details page | 1.Open the Emp Service Portal application 2.Navigate to Policy details page 3.Verify the Download column name | Column name display as "Action" | Column name should display as "Download" | Low | Fixed |  | Close | It's working exactly as it should