## Cover Page
Test Summary_ERP_Procurement Dashboard
VERSION NO | RELEASE DATE | CHANGE DETAILS |  | Prepared By
|  | SECTION | DESCRIPTION
1 | 2024-09-13 | Dashboard | ERP_Procurement Dashboard | Lakshmanan.M

## Test Case Summary
Test Summary_ERP_Procurement Dashboard
Project/Product : |  | ERP |  |  |  |  | Theme: | ERP/Procurement Dashboard
Prepared By : |  | Lakshmanan.M |  |  |  |  | Prepared Date : | 2024-09-13
Date | Testing Phases | Test Case Summary |  |  |  |  | Bug Summary | [6 empty] | Bug Severity
|  | Total | Not Tested | Rejected | Executed | Execution % | New | Open | Re-Open | Closed | Rejected | Deferred | Total | Critical | High | Medium | Low | Pass % | Fail %
| Smoke Testing | 10 | 0 | 0 | 10 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
2024-09-16 | Functional Testing | 60 | 0 | 0 | 60 | 100% | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 12 | 7 | 6 | 58.33% | 41.67%
TBD | Final Round Testing |  |  |  | 0 | 0%
TBD | Closure/Regression Testing | 56 | 0 | 0 | 10 | 17.86% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0%
Note on H3: Arun Mohan: Theme indicates the Page Name or Module Name