## Cover Page
Bug Report_ERP_Procurement Dashboard
VERSION NO | RELEASE DATE | CHANGE DETAILS |  | Prepared By
|  | SECTION | DESCRIPTION
1 | 2024-09-13 | Dashboard | ERP_Procurement Dashboard | Lakshmanan.M

## Procument Dashboard_Big list
S.No | Bug Id | Department | LOB | Role | Title | Bug Description | Steps to Reproduce | Actual Result | Expected Result | Bug Severity | TCs Impacted | Bug Identified Date | Assigned to DEV | Fixed Provided by DEV | Defect Category | Defect Sub Category | Fix Status | Defect Reopened | Tentative Fix Date | Actual Fix Date | Comments To QA | Additional Remarks
1 | 617 | Sales | Pharmacy |  | Procurement Dashboard | Bill generated invoice not display in Invoice print screen | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value and Select Payment Type = cash 4.Click the Bill button 5.Select any value in Pharmacist dropdown 6.Close the feedback pop up without click submit button 7.Navigate to Invoice Print screen 8.Check the created Invoice display or not in the list grid | Bill generated invoice not display in Invoice print screen | Bill generated invoice shpuld display in Invoice print screen | Critical |  | 2024-10-08 | Periyasedhu
2 | 618 |  |  |  |  | Billing invoice not display while click bill button in Hold Bill | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value and Select Payment Type = cash 4.Click the Hold Bill button 5.Navigate to Hold Bill screen 6.Give mandatory values and click bill button | Billing invoice not display while click bill button in Hold Bill | Billing invoice should display while click bill button in Hold Bill | Critical |  | 2024-10-08 | Periyasedhu
3 | 619 |  |  |  |  | Unable to give decimal value in cash field | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Give any(10.55) value in cash field | Unable to give decimal value in cash field | System should allow decimal value in cash field | High |  | 2024-10-08 | Periyasedhu
4 | 620 |  |  |  |  | Error message display while click Bill button | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Update the Patient Name and click Bill button | Error message display while click Bill button | Error message should not display while click Bill button | High |  | 2024-10-08 | Periyasedhu
5 | 621 |  |  |  |  | Existing mobile number value display while click Add count button | 1.Load the POS Application and Login the app 2.Click Add Count button 3.Give any Mobile number value 4.Click Delete Count button, without change any value 5.Agin click Add Count button | Existing mobile number value display while click Add count button | Existing mobile number value should notdisplay while click Add count button | High |  | 2024-10-08 | Periyasedhu
6 | 622 |  |  |  |  | Balance Amount value display minus value while clear the Cash Handling | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Clear the Cash Handling "0" value | Balance Amount value display minus value while clear the Cash Handling | Balance Amount value should not display minus value while clear the Cash Handling | High |  | 2024-10-08 | Periyasedhu
7 | 623 |  |  |  |  | Image capture success message display without upload any picture | 1.Load the POS Application and Login the app 2.Click Add Count button 3.Give any Mobile number value 4.Click Capture button | Image capture success message display without upload any picture | Image capture success message should not display without upload any picture | High |  | 2024-10-08 | Periyasedhu
8 | 624 |  |  |  |  | Mismatch Invoice number display in Invoice print screen and Generated Invoice | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Give mandatory values and click Bill button 5.Navigate to Invoice Print screen 6.Check the same generated Invoice number | Mismatch Invoice number display in Invoice print screen and Generated Invoice | Respective Invoice number should display in Invoice print screen and Generated Invoice | High |  | 2024-10-08 | Periyasedhu
9 | 625 |  |  |  |  | Net Amount display mismatch value in Invoice print screen | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Give mandatory values and click Bill button 5.Navigate to Invoice Print screen 6.Check the Net Amount value | Net Amount display mismatch value in Invoice print screen | Respective Net Amount should display mismatch value in Invoice print screen | Critical |  | 2024-10-08 | Periyasedhu
10 | 626 |  |  |  |  | Mismatch Total value display in Invoice print page | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Give mandatory values and click Bill button 5.Check the every single Total value in Invoice page | Mismatch Total value display in Invoice print page | Respective Total value should display in Invoice print page | Critical |  | 2024-10-08 | Periyasedhu
11 | 627 |  |  |  |  | Mismatch column header value display in Invoice page | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Give mandatory values and click Bill button 5.Check the column header in Invoice page | Mismatch column header(Rate and Value) value display in Invoice page | Column header value display in Invoice page | Medium |  | 2024-10-08 | Periyasedhu
12 | 628 |  |  |  |  | Mismatch Title display in Print Invoice page | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Give mandatory values and click Bill button 5.Check the Invoice Title | Title value display as "Tax Invoice" | Title value should display as "Invoice" | Critical |  | 2024-10-08 | Periyasedhu
13 | 629 |  |  |  |  | Too many space available in Invoice print page | 1.Load the POS Application and Login the app 2.Click Add Count button and perform check user 3.Perform add any tab value 4.Give mandatory values and click Bill button | Too many space available in Invoice print page | Too many space should not need for Invoice print page | Low |  | 2024-10-08 | Periyasedhu
14 | 630 |  |  |  |  | No record error message is shown after clicking the Add button | 1.Load the POS Application and Login the app 2.Navigate to Invoice print screen 3.Click Edit icon for valid record 4.Click Add new item button 5.Try to add any record, which is not available in the Ro | No record error message is shown after clicking the Add button | No record error message should be display after clicking the Add button | High |  | 2024-10-08 | Periyasedhu
15 | 631 |  |  |  |  | User can able to Edit the Invoice No field in Edit invoice page | 1.Load the POS Application and Login the app 2.Navigate to Invoice print screen 3.Click Edit icon for valid record 4.Click Add new item button 5.Update the Invoice No value | User can able to Edit the Invoice No field in Edit invoice page | System should not allow to Edit the Invoice No field in Edit invoice page | Critical |  | 2024-10-08 | Periyasedhu
16 | 632 |  |  |  |  | The system permits the user to update the invoice date with a future date | 1.Load the POS Application and Login the app 2.Navigate to Invoice print screen 3.Click Edit icon for valid record 4.Update the Invoice No date as Future date | The system permits the user to update the invoice date with a future date | System should not allow to update the invoice date with a future date | High |  | 2024-10-08 | Periyasedhu
17 | 633 |  |  |  |  | Unable to cancel the existing item in Edit invoice page | 1.Load the POS Application and Login the app 2.Navigate to Invoice print screen 3.Click Edit icon for valid record 4.Click Add new item button 5.Add any new record and clear the newly added record |  |  |  |  | 2024-10-08 | Periyasedhu
18 | 634 | [10 empty] | 2024-10-08 | Periyasedhu
19 | 635 | [10 empty] | 2024-10-08 | Periyasedhu
20 | 636 | [10 empty] | 2024-10-08 | Periyasedhu
21 | 637 | [10 empty] | 2024-10-08 | Periyasedhu
22 | 638 | [10 empty] | 2024-10-08 | Periyasedhu
23 | 639 | [10 empty] | 2024-10-08 | Periyasedhu
24 | 640 | [10 empty] | 2024-10-08 | Periyasedhu