## Bug Report
S.No | Bug Id | Department | LOB | Role | Title | Bug Description | Steps to Reproduce | Actual Result | Expected Result | Bug Severity | TCs Impacted | Bug Identified Date | Assigned to DEV | Fixed Provided by DEV | Defect Category | Defect Sub Category | Fix Status | Defect Reopened | Tentative Fix Date | Actual Fix Date | Comments To QA | Additional Remarks
14 | 14 | SCM | Purchase Team | Manager Login | Manager Ledger Approval | Duplicate record display in Ledger Approve list grid | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the duplicate record display in Ledger Approve list grid | Duplicate record display in Ledger Approve list grid | Duplicate record should display in Ledger Approve list grid | High |  |  |  |  | User | Need additional training | WIP YTS Fixed - Please ReTest Bug Closed |  |  |  | 1. 2. 3. | 1. 2. 3.
16 | 16 |  |  |  | Manager Ledger Approval | Values display in remarks fields while click Reject icon | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid and give any value 4.Click the close icon 4.Again click Reject icon in list grid | Values display in remarks fields while click Reject icon | Fresh new page should display while click Reject icon | High |  |  |  |  | Requirements | FRD Updated
24 | 24 |  |  |  |  | Error message display while click submit button with insert image in remarks field | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 3.Perfrom add 1 image in remarks field | Error message display while click submit button with insert image in remarks field | Error message should not display while | High |  |  |  |  | Code Fix
25 | 25 |  |  |  |  | UI getting collapse while click code view button | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click full view button in Remarks field 5.Click code view icon and again click code view icon | UI getting collapse while click code view button | UI should not collapse while click code view button | High
32 | 32 |  |  |  |  | Unwanted field display while drag and drop any value in Remarks field | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Give any value and perform drag and drop the same value in remarks field | Unwanted field display while drag and drop any value in Remarks field | Unwanted field should not display while drag and drop any value in Remarks field | High
34 | 34 |  |  |  |  | User can able to submit the rejection pop up with space value alone | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click submit button with space value alone | System allow to submit the rejection pop up with space value alone | System should not allow to submit the rejection pop up with space value alone | High
38 | 38 |  |  |  |  | System allow to perform reject the same record for multiple time | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Perfrom Reject any record 4.Again perform Reject the same record | System allow to perform reject the same record for multiple time | System should allow to perform reject the same record for multiple time | High
39 | 39 |  |  |  | General Ledger Master | Created record not display in General Ledger master | 1.Open the ERP application 2.Navigate to General Ledger master 3.Perfrom create any new record | Created record not display in General Ledger master | Created record should display in General Ledger master | High
40 | 40 |  |  |  |  | Rejected Ledger record not display in General Ledger master | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Perfrom Reject any record 4.Navigate to General Ledger master 5.Check the rejected record display in list grid | Rejected Ledger record not display in General Ledger master | Rejected Ledger record should display in General Ledger master | High
41 | 41 |  |  |  |  | User unable to update the ledger record while reject the record in Manager Ledger approval | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Perfrom Reject any record 4.Navigate to General Ledger master 5.Perform update the same record | User unable to update the ledger record while reject the record in Manager Ledger approval | System should allow to update the ledger record while reject the record in Manager Ledger approval | High
48 | 48 |  |  |  |  | Given value not display properly in Manager Ledger approval CSV file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the CSV download button and open the file | Given value not display properly in Manager Ledger approval CSV file | Given value should display properly in Manager Ledger approval CSV file | High
4 | 4 |  |  |  |  | Placeholder or inner text not display in Search filter text box | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Verify the Placeholder or inner text display or not in Search filter | Placeholder or inner text not display in Search filter | Placeholder or inner text should display in Search filter | Low
5 | 5 |  |  |  |  | Icon's not display in download option section | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Verify the Icon's display or not in download section | Icon's not display in download option section | Icon's should display in download option section | Low
6 | 6 |  |  |  |  | List grid display Improper border alignment | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the Manager Ledger Approval list column border | List grid border display with Improper alignment | List grid border should display with proper alignment | Low
8 | 8 |  |  |  |  | Icon’s not display in middle of the column | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the Approve and Reject icon's alignment | Approve and Reject icon's not display in middle of the column | Approve and Reject icon's should display in middle of the column | Low
9 | 9 |  |  |  |  | Column separator highlighted line not display in list grid | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the Column separator highlighted line display or not | Column separator highlighted line not display in list grid | Column separator highlighted line should display in list grid | Low
10 | 10 |  |  |  |  | Sort icon display as too small | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Verify the sort icon | Sort icon display as too small | Sort icon should display little bit big | Low
13 | 13 |  |  |  |  | Improper alignment display in list grid while maximum value | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the sort icon for first header column | Improper alignment display in list grid while maximum value | Proper alignment should display in list grid while maximum value | Low
18 | 18 |  |  |  |  | Close icon not display properly | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 5.Verify the close icon | Close icon not display properly | Close icon should display properly | Low
23 | 23 |  |  |  |  | Placeholder or inner text not display in Remarks field | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Verify the Placeholder or inner text display or not in Remarks field | Placeholder or inner text not display in Remarks field | Placeholder or inner text should display in Remarks field | Low
46 | 46 |  |  |  |  | Header column not display properly in Manager Ledger approval CSV file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the CSV download button and open the file | Header column not display properly in Manager Ledger approval CSV file | Header column should display properly in Manager Ledger approval CSV file | Low
47 | 47 |  |  |  |  | Header column display as normal column in Manager Ledger approval CSV file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the CSV download button and open the file | Header column display as normal column in Manager Ledger approval CSV file | Header column should display with bright and big in Manager Ledger approval CSV file | Low
50 | 50 |  |  |  |  | Sheet name display with number in Manager Ledger approval CSV file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the CSV download button and open the file | Sheet name display with number in Manager Ledger approval CSV file | Sheet name should not display any number in Manager Ledger approval CSV file | Low
51 | 51 |  |  |  |  | Improper alignment display in Manager Ledger approval Excel file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the Excel download button and open the file | Improper alignment display in Manager Ledger approval Excel file | Proper alignment should display in Manager Ledger approval Excel file | Low
52 | 52 |  |  |  |  | Mismatch sheet name display in Manager Ledger approval Excel file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the Excel download button and open the file | Mismatch sheet name display in Manager Ledger approval Excel file | Sheet name should display as Manager Ledger approval | Low
53 | 53 |  |  |  |  | Mismatch name display for downloaded file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the CSV/Excel download button and open the file | Mismatch name display for downloaded file | File name should display as Manager Ledger approval | Low
1 | 1 |  |  |  |  | Confirmation message not display while click the approve button | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the Approve icon in the list grid 3.Check the Confirmation message display or not | Confirmation message not display while click the approve button | Confirmation message should display | Medium
2 | 2 |  |  |  |  | Mismatch name display for Menu and Page title | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the header/title value in Top of the page | Mismatch name display for Menu and Page title | Same name should display for Menu and Page title | Medium
3 | 3 |  |  |  |  | Mismatch column header name display | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the column name for "S.NO." | Column header name display as "Id" | Column header name should display as "S.NO." | Medium
7 | 7 |  |  |  |  | Unwanted column display in Item list grid | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the Active column display or not | Unwanted column (Active) display in Item list grid | Unwanted column (Active) should not display in Item list grid | Medium
11 | 11 |  |  |  |  | More info button not working | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the More info icon | More info button not working | More info button should working | Medium
12 | 12 |  |  |  |  | Sorted highlighted display in list grid when there is no data available in list grid | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the sort icon for first header column | Sorted highlighted display in list grid when there is no data available in list grid | Sorted highlighted should not display in list grid when there is no data available in list grid | Medium
15 | 15 |  |  |  |  | Required error message not getting display while skip/click the submit button | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click submit button or skip the field | Required error message not getting display | System should display error message as "Remarks required" | Medium
17 | 17 |  |  |  |  | Mismatch pop up title display | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Verify the Pop up title | Pop up title display as Remarks | Pop up title should display as Reason for Rejection | Medium
19 | 19 |  |  |  |  | Confirmation message not display while close the pop up with all values | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click close button/icon with all values | Confirmation message not display while close the pop up with all values | Confirmation message should display while close the pop up with all values | Medium
20 | 20 |  |  |  |  | Rejection up getting close while click beyond the pop up | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click beyond the pop up | Reject pop up getting close while click beyond the pop up | Reject pop up should not close while click beyond the pop up | Medium
21 | 21 |  |  |  |  | Remarks field display resized alignment, while click the add new button | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Alter or realign the Remarks field 5.Click the close icon and click Reject icon in list grid | Remarks field display resized alignment, while click the add new button | Remarks field should display respective alignment, while click the add new button | Medium
22 | 22 |  |  |  |  | Tool tip not display for Close icon | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Check the Tool tip for Close icon | Tool tip not display for Close icon | Tool tip should display as "Close" | Medium
26 | 26 |  |  |  |  | Reject pop up getting close while close the Video/Image/Link pop up | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click Video/Image/Link icon in Item Remarks field 5.Click close icon in Video/Image/Link pop up | Reject pop up getting close while close the Video/Image/Link pop up | Add Item pop up should not close while close the Video/Image/Link pop up | Medium
27 | 27 |  |  |  |  | New URL not getting load same page when uncheck the open in new window | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click Link URL and give all value 5.Uncheck the Open in new window check box and Click Insert link 6.Click the URL in Item Remarks field | New URL not getting load same page when uncheck the open in new window | New URL should load in same page when uncheck the open in new window | Medium
28 | 28 |  |  |  |  | Given URL not getting clear while unlink the URL | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click Link URL and give all value 5.Click Insert link and click the URL in Item Remarks field 6.Click again the code value in Item Remarks field 7.Click unlink icon and click the insert icon in the Item Remarks field | Given URL not getting clear while unlink the URL | Given URL should not display while unlink the URL | Medium
29 | 29 |  |  |  |  | Video/Image/Link pop up getting close without click close icon | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click Video/Image/Link icon in Item Remarks field 5.Click any place apart from the Video/Image/Link pop up | Video/Image/Link pop up getting close without click close icon | Video/Image/Link pop up should not close without click close icon | Medium
30 | 30 |  |  |  |  | Given video link not display in Item Remarks field | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click Video/Image icon in Item Remarks field 5.Give valid link and click insert link button | Given video link not display in Item Remarks field | Given video link should display in Item Remarks field | Medium
31 | 31 |  |  |  |  | Reject pop up getting close without click close icon | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click Reject icon in list grid 4.Click any place apart from the pop up | Reject pop up getting close without click close icon | Reject pop up should not close without click close icon | Medium
33 | 33 |  |  |  |  | Approved record not display in Manager Ledger Approval list grid | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Perfrom approve any record | Approved record not display in Manager Ledger Approval list grid | Approved record should display in Manager Ledger Approval list grid | Medium
35 | 35 |  |  |  |  | Mismatch column name display in Manager Ledger Approval list grid | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the Approve status column | Column name display as "Verification Status" in Manager Ledger Approval list grid | Column name should display as "Approval Status" in Manager Ledger Approval list grid | Medium
36 | 36 |  |  |  |  | Approved success message display mismatch content | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Perfrom approve any record | Approved success message display mismatch content | Respective success message should be display | Medium
37 | 37 |  |  |  |  | Rejected success message display mismatch content | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Perfrom Reject any record | Rejected success message display mismatch content | Respective rejected success message should be display | Medium
42 | 42 |  |  |  |  | Active status name as Inactive in manager Ledger approval list grid display the record, which is create in Ledger approve with active status | 1.Open the ERP application 2.Navigate to General Ledger master 3.Perfrom create new record, which status toggle button = Yes 4.Navigate to General Ledger master 5.Check the active status | Active status name as Inactive in manager Ledger approval list grid display the record, which is create in Ledger approve with active status | Active status name should display the respective value | Medium
43 | 43 |  |  |  |  | Showing count dropdown not display in in Manager Ledger approval page | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Check the Showing count dropdown display or not | Showing count dropdown not display in in Manager Ledger approval page | Showing count dropdown should display in in Manager Ledger approval page | Medium
44 | 44 |  |  |  |  | Error message display while open the Manager Ledger approval CSV file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the CSV download button and open the file | Error message display while open the Manager Ledger approval CSV file | Error message should not display while open the Manager Ledger approval CSV file | Medium
45 | 45 |  |  |  |  | Null value display while open the Manager Ledger approval CSV file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the CSV download button and open the file | Null value display while open the Manager Ledger approval CSV file | Null value should display while open the Manager Ledger approval CSV file | Medium
49 | 49 |  |  |  |  | Unwanted column display in Manager Ledger approval CSV/Excel file | 1.Open the ERP application 2.Navigate to Manager Ledger Approval 3.Click the CSV download button and open the file | Unwanted column(Approval and Rejection) display in Manager Ledger approval CSV file | Approval and Rejection should not display in Manager Ledger approval CSV file | Medium