## Sheet1
Work Breakdown Structure
Task | Hrs | Status of Task
Requirement Gathering and Understanding | 5
Test case preparation | 30
Mobile Casting Configuration | 0
Iteration-1 Testing | 48
Test Document Preparation | 4
Bug Verification | 5
Closure Testing | 24
Total | 116
| Test case preparation | 0
Module Name | Hours | Test Case Status | Testing Status
Home | 6 | Yet To Start | Yet To Start
Leads | 4 | Yet To Start | Yet To Start
Add Sales orders | 4 | Yet To Start | Yet To Start
Customer Invoice | 3 | Yet To Start | Yet To Start
Accounts | 3 | Yet To Start | Yet To Start
Doctor Visit | 3 | Yet To Start | Yet To Start
Visit Report | 3 | Yet To Start | Yet To Start
Doctor Gift | 3 | Yet To Start | Yet To Start
Gift Report | 3 | Yet To Start | Yet To Start
Franchise Enquiry | 3 | Yet To Start | Yet To Start
Privacy and Policy | 3 | Yet To Start | Yet To Start
Log out | 3 | Yet To Start | Yet To Start
Total | 41
Smoke
Functional
Ui spell check
Buttons
Error message
Success message
Broken link
Image
Navigation
Data Validation
Redirect
Compatability
Sign in Page
Automation Testing
Appium