## Sheet1
Title: Demo |  |  | Location: Google Meet (https://meet.google.com/peq-dzwp-pkc)
Date: 12th May 2025 |  |  | Organizer: Stanley
Time: 6:00 PM – 7:45 PM
Attendees
Dr. Saravanan Sir, Tamizh, Stanley, Karthik, Moorthy, Sai, Bharathy, Lakshmanan, Deepan, Saravanan, Vinoth, Mosik, Sedhu, Edwin, Abiram, Krishnanath, Kezia, Mahalaksmi, Alex
S.No. | Agenda | Discussed | Description | Owners
1 | Demo To Be Provided | Yes | Team provided the demo on the features planned for 12th March.
2 | Engine Enhancements | Yes | Rules Engine: 1. To be change the all frontend end component should be display in rules, user can the entire elements using rules engine because of all the elements code have in Rules Engine To make changes, all frontend components should be shown through the Rules Engine, enabling users to control each element, since all the code resides within the engine. 2. The created node details should be display in Edit/ View mode also 3. The output should be displayed within the same page, and a plug-and-play output feature should also be added to that page. Process BPMN: 1. The delete and edit options must work correctly, and module access should be available in the same way as it is in the other engine. 2. To ensure the module updates automatically, it should reflect changes made in other modules and features of the app. Creation Engine: All bugs and features should be developed and resolved according to the feature checklist and the associated comments. Analytics Engine: The analytics code generation issue must be fixed prior to the upcoming demo.
| General Comments for Simplita.ai ap | Yes | 1.The team should make note of and document all challenges encountered while replicating the SG.HR wireframe and developing the app. 2. The SG.HR app was developed by the team with all 32 pages integrated into one app, replicating the structure based on the provided wireframe. 3.The existing features should be prioritized for end-to-end functionality, with comprehensive testing to verify their performance.
3 | Simplita.ai Code | Yes | 1. The functionality of our Simplita.ai code should align with the features present in the application. 2. Our Simplita.ai code must deliver a stable, error-free application. --Currently, the issue is that the AI-generated code tends to hallucinate scenarios when creating the app. 3. Simplita.ai should perform actions in the same way a human operator would, without generating new code. 4. The development of Simplita.ai should include real-time updates, with every task the AI performs reflected in the history log. The content shown during app creation should directly correspond to backend operations.
4 | Ai Agency builder | Yes | 1. The team should create an AI agent that acts as a commander, managing and directing other AIs to develop applications. This allows users to generate their own AI agent to build apps using AI. 2. A specific AI agent will be assigned the responsibility of building the application.and The key point is that the app-building agent can be created by the user. 4. By using RAG (Retrieval-Augmented Generation), we can simplify the code analysis process and significantly reduce the time it takes for the AI to understand our code.
5 | UI/UX | Yes | UI development should be initiated in parallel as the team builds the SG.HR app with Simplita. | Deepan