## Testing Engine Plan
S.No. | Testing Engine Features | Status | Status for upcoming demo
1 | Test cases can be generated for any scenario by the user | Done | Ready to show the demo for upcoming demo
2 | Create Playwright-based test scripts for any test scenario | Done
3 | Run Playwright test scripts across various scenarios(Within our app) | Done
4 | Users can build test cases specifically for our form | Done
5 | Generate a test report for the executed Playwright script *Initially generate the reports within the Playwright project *Enable report download directly from the Playwright report *Present test results with graphical representation and detailed counts *Provide improvement suggestions in the Test Results section | WIP
6 | Define structured test cases for our developed app functionalities | YTS | I have dependencies on Bharathy, Sedhu, Mosik, and Karthik, so I need to discuss with them.
7 | User can create the Playwrights script for our created app | YTS | Will show the features in next Demo
8 | Run the Playwrights script for our created app | YTS
9 | Prepare Test Report for Playwright script | YTS
US | Generate a test report for the executed Playwright script | Target to Complete task
US-1 | Initially generate the reports within the Playwright project | Today
Us-2 | Enable report download directly from the Playwright report
US-3 | Present test results with graphical representation and detailed counts
US-4 | Provide improvement suggestions in the Test Results section | Tomorrow, before midday
US | Generate a test report for the executed Playwright script | Status
US-1 | Initially generate the reports within the Playwright project | Done
Us-2 | Enable report download directly from the Playwright report | Done
US-3 | Present test results with graphical representation and detailed counts | Done
US-4 | Provide improvement suggestions in the Test Results section | YTS
2025-02-19
Issue
1 | Fix the Top menu icon hiding issue | Done
2 | Button colour change same as globally | Done
3 | Dual Thinking message display when user intract with open ai in Testing engine ai | Done
Testing Engine - US101: As a non-technical user, I need to fix the Testing Engine bugs
S.No. | Iteration-3 | Status
1 | Display the created app menu in Testing Engine | YTS
2 | Display the created app in Testing Engine | YTS
3 | Create the Test scenario for our created app | YTS
4 | Create the Playwright script for our created app | YTS
5 | Run the created Playwright script for our created app | YTS
6 | Display the playwright script in chat history | YTS
Date | 1st Half Task | 2nd Half Task
2025-02-25 | Display the created app menu in Testing Engine | Display the created app in Testing Engine
2025-02-26 | Add the Generate Test Case button in Current app | Prepare Test Case for created app in Test Case section
2025-02-27 | Create the Playwright script for our created app | Export the Playwright script for our created app
2025-02-28 | 1)Run the Playwright script for our created app 2)Enable report download directly from the Playwright report | 1)Present test results with graphical representation and detailed counts 2)Provide improvement suggestions in the Test Results section
Date | 1st Half Task | 2nd Half Task
2025-02-26 | Add the Generate Test Case button in Current app | Prepare Test Case for created app in Test Case section
| lakshmanan.m@qnqhealthcare.in | Lak@2025

## Sheet2
S.No. | Subject | Steps to confirm whether the current function is operational
1 | Prompt Desclaimer | Insert a disclaimer into the given prompt for handling critical functionalities.
2 | Confirm with CursorAi | After every 4 to 5 User Stories, use a prompt to query CursorAI and verify if the existing feature is functioning.
3 | Save the working Prompt | Every developer must gather and save the most recent functioning prompt.
4 | Manual Check list & Manual Testing | Prepare a checklist of completed features and verify it for every 4 to 5 User Stories. And Ensure every critical feature is operational after completing every 4 to 5 User Stories.
6 | Experience Testing | For every new feature, predict upcoming issues and provide the proper disclaimer.

## Auth_Engine
Authen
S.No. | Authentication Engine-Bug Description | Severity
1 | The questionnaire content is shown as a form rather than as an app. | High
2 | The system's guidance is incorrect; it requests app details post-login, even without a project | High
3 | Error message shows up when app required details are entered | Critical
4 | The workspace is not shown as the default screen after login | High
5 | User unable to move the existing project | High
6 | User unable to delete any project | High
7 | The sign-out/log-out button is difficult to access | High
8 | The "Sign up now" button appears unnecessarily after login | High
9 | The search feature is not functioning properly. | High
10 | There is no project list displayed in the left sidebar | High
11 | After switching to the creation engine, users can't move the workspace or navigate back | High
12 | The "Forgot Password" option is not functioning | High
13 | The login page displays unwanted links to Terms of Use and Privacy Policy | High

## Creation_Engine
S.No. | Creation Engine-Bug Description | Severity
1 | Chat option is not display in existing project/new project | Critical
2 | After adding the Left menu via Layers, it doesn’t show up immediately in the preview/editor. The menu only appears after I refresh the page | Critical
3 | Form details are not showing up properly in the linked left menu. Random information is displayed instead. | Critical
We are running out of time

## Thematic_Engine
S.No. | Authentication Engine-Bug Description | Severity
1 | Static Top menu issue still happen in Thematic engine, fix the issue high priority | Critical
2 | When click the Theme tab the system display error message | Critical
3 | When navigating from the Thematic Engine to other engines, none of the engines are loading. Kindly investigate this issue. | Critical
4 | Created input fields is not display in Thematic Engine | High
5 | Thematic function is loading with the error message | High