## Sheet1
S.No | Process Step | Status
1 | Get the KT (Knowledge Transfer) for Respective Engine | Done
2 | Prepare and Finalize Test Case Documents | Done
3 | Configure and Set Up the Testing Environment | Done
4 | Conduct Smoke Testing for the Engine | Done
5 | Basic Functional(Manual) Testing for Respective Engine | Done
6 | Create Playwright Script for Respective Engine | WIP
7 | Run the Playwright Test Scripts | YTS
8 | Prepare Test Report Documents for Respective Engine | YTS
Bug List
S.NO | Bug Title | Severity
1 | Generate with AI button not working | High
2 | Unwanted form getting create while give "Hi" message in Chat field | Critical
3 | Toggle button option is not display in Form Element | Medium
4 | Form Preview Header section not display when there is not data available | Medium
5 | There is a delay in receiving responses from the AI during chat | Medium
6 | Information messages are not shown when form fields are created, updated, or deleted | Medium
7 | No clear/refresh button is visible in the Form Preview section | High
8 | Form header is missing from the display | Medium
9 | The system does not allow copying of the field value and field label name | Medium
10 | AGE/YOF fields are displaying a message indicating they are unsupported | Critical
11 | Newly entered prompt details are not being reflected and continue to display existing form information | High
12 | Mismatched values observed between the Placeholder-Setting configuration and the actual placeholder value displayed | High