## Snapshot
Count of Severity | Column Labels
Row Labels | Critical | High | Low | Medium | Grand Total
Functional | 8 | 67 |  | 8 | 83
Canvas Editor | 5 | 27 |  | 1 | 33
Theme Tab | 2 | 15 |  |  | 17
Components Tab | 1 | 6 |  | 3 | 10
Right panel |  | 7 |  | 2 | 9
Layers Tab |  | 6 |  | 1 | 7
Elements Tab |  | 3 |  | 1 | 4
Canvas Edito |  | 2 |  |  | 2
Left Panel |  | 1 |  |  | 1
UI/UX |  | 1 | 11 | 27 | 39
Canvas Editor/Elements& Layers Tab |  | 1 | 5 | 9 | 15
Component Tab |  |  | 3 | 8 | 11
Theme Tab |  |  | 2 | 4 | 6
Canvas Editor |  |  |  | 3 | 3
Layers Tab |  |  |  | 2 | 2
Right panel |  |  | 1 | 1 | 2
Grand Total | 8 | 68 | 11 | 35 | 122

## Bug List for Creation Engine
S.No | Bug Type | Feature | Description | Severity
1 | Functional | Canvas Editor | Canvas Editor display the existing project details when a new project is created by the user | Critical
2 | Functional | Canvas Editor | The drag and drop function fails when the user creates a new project for the first time. | High
3 | Functional | Canvas Editor | The "Create app using chat" feature doesn't work when a new project is created for the first time. | High
4 | Functional | Canvas Edito | Without the app layout, users cannot view the app in preview mode. | High
5 | Functional | Layers Tab | The deleted menu name continues to display in another screen backend and database. | High
6 | Functional | Canvas Edito | The drag and drop function is not operating smoothly. | High
7 | Functional | Canvas Editor | The user cannot see small and simple words when the inline editing feature is enabled. | High
8 | Functional | Canvas Editor | The resize feature does not meet current market standards. | High
9 | Functional | Canvas Editor | The element drag and drop feature isn't working within the structure of the div. | High
10 | Functional | Canvas Editor | The system auto-saves once an element is resized, but it doesn't complete the auto-save process before the user attempts to resize again. | High
11 | Functional | Elements Tab | Unwanted components are displayed in the Basic Elements section. | High
12 | Functional | Canvas Editor | When a user adds spaces in the Heading div, unwanted and confusing content displays in the canvas. | High
13 | Functional | Canvas Editor | There is no height resize option available for any element. | High
14 | Functional | Right panel | The right-side panel shows two confusing layouts. | High
15 | Functional | Canvas Editor | By default, the font size and color do not display when the user clicks the settings button in any element. | High
16 | Functional | Layers Tab | The menu create field allows more than 500 characters. | High
17 | Functional | Layers Tab | The delete icon is not visible when more than 10 characters are entered in the menu create field. | High
18 | Functional | Layers Tab | The delete icon does not display for a single menu available, and there is no instruction explaining why the delete icon is missing. | Medium
19 | Functional | Layers Tab | Unwanted layers section is displayed in the layers tab. | High
20 | Functional | Canvas Editor | Three save options in the Creation Engine cause confusion for the end user. | High
21 | Functional | Right panel | The unwanted validation section displays in the Creation right panel. | High
22 | Functional | Elements Tab | Multiple top navigation bar elements are displayed in the Layout-Component section. | Medium
23 | Functional | Canvas Editor | The user is unable to create top menus or pages; only side menus or pages are available. | Critical
24 | Functional | Canvas Editor | The user cannot clear or delete multiple elements on one page. | High
25 | Functional | Canvas Editor | The user cannot add new content or words using the container-layout elements. | High
26 | Functional | Canvas Editor | The user cannot add any element after the fixed layout with the sidebar layout element section is added. | High
27 | Functional | Canvas Editor | Two layout sections display when the fixed layout is added to the left panel, which creates confusion. | Critical
28 | Functional | Canvas Editor | The user cannot create any single element for Menu-2 after the fixed layout is added using the left panel. | Critical
29 | Functional | Canvas Editor | The user is unable to update the color after the layout is added. | High
30 | Functional | Canvas Editor | The updated layout does not display in the canvas editor. | High
31 | Functional | Canvas Editor | The user cannot delete layout content that was added using the right panel. | High
32 | Functional | Elements Tab | Only basic master page related fields and elements are displayed in the elements section. | High
33 | Functional | Layers Tab | When the user adds a page, there is no success message displayed. | High
34 | Functional | Left Panel | There is confusion regarding the tab name in the Creation Engine left panel (1.Elements, 2.Layers, 3.Components); the basic logic for the tab name is missing. | High
35 | Functional | Canvas Editor | Deleted pages or menus still display in the Canvas Editor section. | High
36 | Functional | Canvas Editor | There is no option to revert the applied Layout-Right panel. | High
37 | Functional | Canvas Editor | The user is unable to resize or maximize the already minimized field. | High
38 | Functional | Canvas Editor | The user cannot add new pages or menus as the top menu. | Critical
39 | Functional | Canvas Editor | There is no toast message displayed when a page is deleted. | High
40 | Functional | Canvas Editor | The user is unable to change the logo in the layout. | High
41 | Functional | Canvas Editor | The user cannot edit the progress bar or table element in the Canvas Editor. | High
42 | Functional | Layers Tab | The updated menu/page value is not displayed in the Layers section-left panel. | High
43 | Functional | Elements Tab | There is confusion between the Basic Elements and Form sections in the Element tab-left panel. | High
44 | Functional | Canvas Editor | The user is unable to add elements in the second tab (Tabbar components) of the Canvas Editor. | High
45 | Functional | Canvas Editor | The dashboard button is displayed as clicked, but the user cannot change the view mode after adding the Layout-Right panel. | Medium
46 | Functional | Canvas Editor | The user is unable to change the page/menu background color in the canvas editor. | High
47 | Functional | Canvas Editor | Resizing does not work in the page/menu within the canvas editor. | High
48 | Functional | Canvas Editor | The user is unable to view the entire element after adding multiple templates in the canvas editor. | High
49 | Functional | Canvas Editor | The Save & Load section is don't want available in the right-side panel. | High
50 | Functional | Right Panel | The user can link any available page/menu to any field or element. | High
51 | Functional | Components Tab | Unable to save the New component in Componenets tab | Critical
52 | Functional | Components Tab | In the Preview section display the Code also along with element UI(Creat the CircleLoader) | High
53 | Functional | Components Tab | Some of the element not create the by AI(Creat the 10 sort icon) | High
54 | Functional | Components Tab | Unable to perform paste the values in Ai chat field | High
55 | Functional | Components Tab | Create New Components pop up getting close when click appart form the pop up | Medium
56 | Functional | Components Tab | When user send the message as hi then chat field display the Hi related elememnt code | Medium
57 | Functional | Components Tab | The pop up getting close when user click the get help dropdown | High
58 | Functional | Components Tab | Updated existing components is not display the updated code | Medium
59 | Functional | Components Tab | Two different pop up display for Component create and Edit, user can getting confuse a lot of edit the component for existing elemet and create the component using ai | High
60 | Functional | Components Tab | Image Element preview is display with error | High
61 | Functional | Theme Tab | Cancle applied theme functin is not available for Theme tab | High
62 | Functional | Theme Tab | AI generate the Christmass theme but there is any propeper user expect output is not receive | High
63 | Functional | Theme Tab | The secondary coliur is not apply in the canvas editor page | High
64 | Functional | Theme Tab | User unable to delete the cretaed Theme | High
65 | Functional | Theme Tab | There is no success message display when user creat the new theme | High
66 | Functional | Theme Tab | Updated theme name display in Theme tab | High
67 | Functional | Theme Tab | Font edit feature is not working | High
68 | Functional | Theme Tab | Unable to change the text colour | High
69 | Functional | Theme Tab | System not display the updated success message when update the theme | High
70 | Functional | Theme Tab | Added theme colcour is not refelect the middle of the page, it hs refelect only in the side bar | High
71 | Functional | Theme Tab | The background theme is not referelect which is work for only Dashboard layout is applied | Critical
72 | Functional | Theme Tab | User unable toadd the theme based on the menu/page, the theme gong to add all menu/page, even which menu notinclude with layout | High
73 | Functional | Theme Tab | Theme is not override when user add the new along with existing colour for any field/element | High
74 | Functional | Theme Tab | User unable to add the Ai created Theme | Critical
75 | Functional | Theme Tab | System not allow to upload 1 mb file | High
76 | Functional | Theme Tab | System not display proper error message when user upload <> json file | High
77 | Functional | Theme Tab | In that available Edit Theme panel the Background colour only update the app, other that that no feature is not working | High
78 | Functional | Right panel | Drag-and-drop functionality in the Image Library Right Panel is not working | High
79 | Functional | Right panel | No success message is displayed after deleting an uploaded image in the Image Library Right Panel | Medium
80 | Functional | Right panel | A user can upload files larger than 10 MB | High
81 | Functional | Right panel | The system does not present the correct error message when uploading a <> JSON file | Medium
82 | Functional | Right panel | Edit element Basic Styles are not functioning properly | High
83 | Functional | Right panel | An unwanted Export Canvas section is shown in the Right Panel | High
84 | UI/UX | Layers Tab | The Layers Tab appears second, but the system does not clearly explain why it is unable to drag and drop components. | Medium
85 | UI/UX | Layers Tab | No message is shown prompting the user to create Pages/menus first. | Medium
86 | UI/UX | Canvas Editor | When resizing large word content, it collapses, causing display issues. | Medium
87 | UI/UX | Canvas Editor | The H1-heading appears as a pixelated label name. | Medium
88 | UI/UX | Canvas Editor | The system fails to display H2, H3, and other elements. | Medium
89 | UI/UX | Canvas Editor/Elements& Layers Tab | The element category appears confusing, requiring users to rearrange both the element and its name. | Medium
90 | UI/UX | Canvas Editor/Elements& Layers Tab | Unwanted Image Elements are visible in the Basic Elements section. | Low
91 | UI/UX | Canvas Editor/Elements& Layers Tab | The Close/Clear icon is visible in the Layout Components section-right panel, but the section can only be accessed once the user clears it. | Low
92 | UI/UX | Canvas Editor/Elements& Layers Tab | Two instances of the name "Simplita" are shown in the Creation Engine. | Low
93 | UI/UX | Canvas Editor/Elements& Layers Tab | The unwanted Layers section is visible in the Layers tab. | High
94 | UI/UX | Canvas Editor/Elements& Layers Tab | No tooltips or help tips are available for any icons. | Medium
95 | UI/UX | Canvas Editor/Elements& Layers Tab | The "Two columns" element does not display correctly in the Canvas editor. | Medium
96 | UI/UX | Canvas Editor/Elements& Layers Tab | Unwanted double quotes appear when adding any element to the canvas editor. | Medium
97 | UI/UX | Canvas Editor/Elements& Layers Tab | An unnecessary icon is displayed next to the Undo & Redo buttons in the header. | Medium
98 | UI/UX | Canvas Editor/Elements& Layers Tab | An unwanted navigation label appears after adding the Layout-Right panel. | Low
99 | UI/UX | Canvas Editor/Elements& Layers Tab | An empty circle appears before the Sign-In button after adding the Layout-Right panel. | Low
100 | UI/UX | Canvas Editor/Elements& Layers Tab | The top menu is displayed in the middle of the page after adding the Layout-Right panel. | Medium
101 | UI/UX | Canvas Editor/Elements& Layers Tab | When dragging and dropping a button element in the Canvas editor, the button appears as a normal label. | Medium
102 | UI/UX | Canvas Editor/Elements& Layers Tab | The button element appears in two sections in the Components section on the left panel. | Medium
103 | UI/UX | Canvas Editor/Elements& Layers Tab | By default, all page/menu checkboxes are selected after clicking "Apply Layout," but the "Select All" checkbox appears unselected. | Medium
104 | UI/UX | Component Tab | Ai Assistant feature is displayed as a regular label name | Medium
105 | UI/UX | Component Tab | No error message appears when the user leaves the Component name field empty in the Components tab | Medium
106 | UI/UX | Component Tab | The header displays as "Component HTML*" but AI also generates other technologies | Low
107 | UI/UX | Component Tab | The tool/help tip for the Close icon in the Create New Components popup is not visible | Low
108 | UI/UX | Component Tab | The field is labeled as Components Name, but should be labeled as Elements Name | Medium
109 | UI/UX | Component Tab | The chat field icon is missing | Medium
110 | UI/UX | Component Tab | The element edit popup does not show the correct title | Medium
111 | UI/UX | Component Tab | The Click me button code is displayed as a label name | Medium
112 | UI/UX | Component Tab | The multiselect dropdown does not show any values | Low
113 | UI/UX | Component Tab | Multiple sidebar navigation options are displayed in the Navigation Section | Medium
114 | UI/UX | Component Tab | The menu/page dropdown collapses under the dashboard layout header, partially hiding its values | Medium
115 | UI/UX | Theme Tab | The Theme tab is not readily accessible to end users and does not appear by default | Medium
116 | UI/UX | Theme Tab | The first theme setting option’s label name is not visible | Low
117 | UI/UX | Theme Tab | Some themes do not display their name/title | Medium
118 | UI/UX | Theme Tab | The top navbar theme does not change when a new theme is added | Medium
119 | UI/UX | Theme Tab | The tool/help tip is not visible in the Theme tab | Low
120 | UI/UX | Theme Tab | There is a mismatch between the theme name and its color in the Theme tab, showing "Light" but rendering black | Medium
121 | UI/UX | Right panel | All section features are open by default (plus symbol enabled), and only the section header is shown by default. | Medium
122 | UI/UX | Right panel | The Layout Components section header appears in a distinct color | Low
|  | 669 | Creation Engine-Canvas Editor(Functional)- Canvas Editor display the existing project details when a new project is created by the user | PRODUCT BACKLOG | Edwin | 2025-03-26 | critical
|  | 670 | Creation Engine-Canvas Editor(Functional)- The drag and drop function fails when the user creates a new project for the first time | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 672 | Creation Engine-Canvas Editor(Functional)- The "Create app using chat" feature doesn't work when a new project is created for the first time | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 673 | Creation Engine-Canvas Editor(Functional)- Without the app layout, users cannot view the app in preview mode | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 674 | Creation Engine-Layers Tab(Functional)- The deleted menu name continues to display in another screen backend and database | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 675 | Creation Engine-Canvas Editor(Functional)- The drag and drop function is not operating smoothly | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 676 | Creation Engine-Canvas Editor(Functional)- The user cannot see small and simple words when the inline editing feature is enabled | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 677 | Creation Engine-Canvas Editor(Functional)- The resize feature does not meet current market standards | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 678 | Creation Engine-Canvas Editor(Functional)- The element drag and drop feature isn't working within the structure of the div | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 679 | Creation Engine-Canvas Editor(Functional)- The system auto-saves once an element is resized, but it doesn't complete the auto-save process before the user attempts to resize again | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 680 | Creation Engine-Canvas Editor(Functional)- Unwanted components are displayed in the Basic Elements section | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 681 | Creation Engine-Canvas Editor(Functional)- When a user adds spaces in the Heading div, unwanted and confusing content displays in the canvas. | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 682 | Creation Engine-Canvas Editor(Functional)- There is no height resize option available for any element | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 683 | Creation Engine-Right panel(Functional)- The right-side panel shows two confusing layouts section values | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 684 | Creation Engine-Canvas Editor(Functional)- By default, the font size and color do not display when the user clicks the settings button in any element | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 685 | Creation Engine-Layers Tab(Functional)- The menu create field allows more than 500 characters | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 686 | Creation Engine-Layers Tab(Functional)- The delete icon is not visible when more than 10 characters are entered in the menu create field | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 687 | Creation Engine-Layers Tab(Functional)- The delete icon does not display for a single menu available, and there is no instruction explaining why the delete icon is missing | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 688 | Creation Engine-Layers Tab(Functional)- Unwanted layers section is displayed in the layers tab | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 689 | Creation Engine-Canvas Editor(Functional)- Three save options in the Creation Engine cause confusion for the end user | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 690 | Creation Engine-Right panel(Functional)- The unwanted validation section displays in the Creation right panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 691 | Creation Engine-Elements Tab(Functional)- Multiple top navigation bar elements are displayed in the Layout-Component section | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 692 | Creation Engine-Canvas Editor(Functional)- The user is unable to create top menus or pages; only side menus or pages are available | PRODUCT BACKLOG | Edwin | 2025-03-26 | critical
|  | 693 | Creation Engine-Canvas Editor(Functional)- The user cannot clear or delete multiple elements on one page | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 694 | Creation Engine-Canvas Editor(Functional)- The user cannot add new content or words using the container-layout elements | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 695 | Creation Engine-Canvas Editor(Functional)- The user cannot add any element after the fixed layout with the sidebar layout element section is added | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 696 | Creation Engine-Canvas Editor(Functional)- Two layout sections display when the fixed layout is added to the left panel, which creates confusion | PRODUCT BACKLOG | Edwin | 2025-03-26 | critical
|  | 697 | Creation Engine-Canvas Editor(Functional)- The user cannot create any single element for Menu-2 after the fixed layout is added using the left panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | critical
|  | 698 | Creation Engine-Canvas Editor(Functional)- The user is unable to update the color after the layout is added | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 699 | Creation Engine-Canvas Editor(Functional)- The updated layout does not display in the canvas editor | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 700 | Creation Engine-Canvas Editor(Functional)- The user cannot delete layout content that was added using the right panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 701 | Creation Engine-Elements Tab(Functional)- Only basic master page related fields and elements are displayed in the elements section | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 702 | Creation Engine-Layers Tab(Functional)- When the user adds a page, there is no success message displayed | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 703 | Creation Engine-Left Panel(Functional)- There is confusion regarding the tab name in the Creation Engine left panel (1.Elements, 2.Layers, 3.Components); the basic logic for the tab name is missing | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 704 | Creation Engine-Canvas Editor(Functional)- Deleted pages or menus still display in the Canvas Editor section | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 705 | Creation Engine-Canvas Editor(Functional)- There is no option to revert the applied Layout-Right panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 706 | Creation Engine-Canvas Editor(Functional)- The user is unable to resize or maximize the already minimized field | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 707 | Creation Engine-Canvas Editor(Functional)- The user cannot add new pages or menus as the top menu | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 708 | Creation Engine-Canvas Editor(Functional)- There is no toast message displayed when a page is deleted | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 709 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the logo in the | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 710 | Creation Engine-Canvas Editor(Functional)- The user cannot edit the progress bar or table element in the Canvas Editor | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 711 | Creation Engine-Layer Tab(Functional)- The updated menu/page value is not displayed in the Layers section-left panel. | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 712 | Creation Engine-Elements Tab(Functional)- There is confusion between the Basic Elements and Form sections in the Element tab-left panel. | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 713 | Creation Engine-Canvas Editor(Functional)- The user is unable to add elements in the second tab (Tabbar components) of the Canvas Editor | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 714 | Creation Engine-Canvas Editor(Functional)- The dashboard button is displayed as clicked, but the user cannot change the view mode after adding the Layout-Right panel. | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 715 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the page/menu background color in the canvas editor | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 716 | Creation Engine-Canvas Editor(Functional)- Resizing does not work in the page/menu within the canvas editor | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 717 | Creation Engine-Canvas Editor(Functional)- The user is unable to view the entire element after adding multiple templates in the canvas editor | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 718 | Creation Engine-Canvas Editor(Functional)- The Save & Load section is don't want available in the right-side panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 719 | Creation Engine-Right Panel(Functional)- The user can link any available page/menu to any field or element | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 720 | Creation Engine-Components Tab(Functional)- Unable to save the New component in Components tab | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 721 | Creation Engine-Components Tab(Functional)- In the Preview section, display the Code also along with element UI (Create the Circle Loader) | PRODUCT BACKLOG | Edwin | 2025-03-26 | critical
|  | 722 | Creation Engine-Components Tab(Functional)- Some of the element not create the by AI(Createthe 10 sort icon) | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 723 | Creation Engine-Components Tab(Functional)- Unable to perform paste the values in Ai chat field | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 724 | Creation Engine-Components Tab(Functional)- Create New Components pop up getting close when click away from the pop up | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 725 | Creation Engine-Components Tab(Functional)- When user send the message as hi then chat field display the Hi related elememnt code | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 726 | Creation Engine-Components Tab(Functional)- The pop up getting close when user click the get help dropdown | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 727 | Creation Engine-Components Tab(Functional)- Updated existing components is not display the updated code | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 728 | Creation Engine-Components Tab(Functional)- Two different pop up display for Component create and Edit, user can getting confuse a lot of edit the component for existing elemet and create the component using ai | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 729 | Creation Engine-Components Tab(Functional)- Image Element preview is display with error | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 747 | Creation Engine-Right panel(Functional)- Drag-and-drop functionality in the Image Library Right Panel is not working | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 748 | Creation Engine-Right panel(Functional)- No success message is displayed after deleting an uploaded image in the Image Library Right Panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 749 | Creation Engine-Right panel(Functional)- A user can upload files larger than 10 MB | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 750 | Creation Engine-Right panel(Functional)- The system does not present the correct error message when uploading a <> JSON file | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 751 | Creation Engine-Right panel(Functional)- Edit element Basic Styles are not functioning properly | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 752 | Creation Engine-Right panel(Functional)- An unwanted Export Canvas section is shown in the Right Panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 753 | Creation Engine-Layers Tab(UI/UX)- The Layers Tab appears second, but the system does not clearly explain why it is unable to drag and drop components | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 754 | Creation Engine-Layers Tab(UI/UX)- No message is shown prompting the user to create Pages/menus first before add the elements | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 755 | Creation Engine-Canvas Editor(UI/UX)- When resizing large word content, it collapses, causing display issues. | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 756 | Creation Engine-Canvas Editor(UI/UX)- The H1-heading appears as a pixelated label name | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 757 | Creation Engine-Canvas Editor(UI/UX)- The system fails to display H2, H3, and other elements | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 758 | Creation Engine-Canvas Editor(UI/UX)- The element category appears confusing, requiring users to rearrange both the element and its name | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 759 | Creation Engine-Canvas Editor(UI/UX)- Unwanted Image Elements are visible in the Basic Elements section | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 760 | Creation Engine-Canvas Editor(UI/UX)- The Close/Clear icon is visible in the Layout Components section-right panel, but the section can only be accessed once the user clears it | PRODUCT BACKLOG | Edwin | 2025-03-26 | low
|  | 761 | Creation Engine-Canvas Editor(UI/UX)- Two instances of the name "Simplita" are shown in the Creation Engine | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 762 | Creation Engine-Canvas Editor(UI/UX)- The unwanted Layers section is visible in the Layers tab | PRODUCT BACKLOG | Edwin | 2025-03-26 | high
|  | 763 | Creation Engine-Canvas Editor(UI/UX)- No tooltips or help tips are available for any icons | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 764 | Creation Engine-Canvas Editor(UI/UX)- The "Two columns" element does not display correctly in the Canvas editor | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 765 | Creation Engine-Canvas Editor(UI/UX)- Unwanted double quotes appear when adding any element to the canvas editor | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 766 | Creation Engine-Canvas Editor(UI/UX)- An unnecessary icon is displayed next to the Undo & Redo buttons in the header | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 767 | Creation Engine-Canvas Editor(UI/UX)- An unwanted navigation label appears after adding the Layout-Right panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | low
|  | 768 | Creation Engine-Canvas Editor(UI/UX)- An empty circle appears before the Sign-In button after adding the Layout-Right panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 769 | Creation Engine-Canvas Editor(UI/UX)- The top menu is displayed in the middle of the page after adding the Layout-Right panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 770 | Creation Engine-Canvas Editor(UI/UX)- When dragging and dropping a button element in the Canvas editor, the button appears as a normal label | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 771 | Creation Engine-Canvas Editor(UI/UX)- The button element appears in two sections in the Components section on the left panel | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 772 | Creation Engine-Canvas Editor(UI/UX)- By default, all page/menu checkboxes are selected after clicking "Apply Layout," but the "Select All" checkbox appears unselected. | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 773 | Creation Engine-Component Tab(UI/UX)- Ai Assistant feature is displayed as a regular label name | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 774 | Creation Engine-Component Tab(UI/UX)- No error message appears when the user leaves the Component name field empty in the Components tab | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 775 | Creation Engine-Component Tab(UI/UX)- The header displays as "Component HTML*" but AI also generates other technologies | PRODUCT BACKLOG | Edwin | 2025-03-26 | low
|  | 776 | Creation Engine-Component Tab(UI/UX)- The tool/help tip for the Close icon in the Create New Component's popup is not visible | PRODUCT BACKLOG | Edwin | 2025-03-26 | low
|  | 777 | Creation Engine-Component Tab(UI/UX)- The field is labeled as Components Name, but should be labeled as Elements Name | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 778 | Creation Engine-Component Tab(UI/UX)- The chat field icon is missing in existing element pop up | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 779 | Creation Engine-Component Tab(UI/UX)- The element edit popup does not show the correct title | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 780 | Creation Engine-Component Tab(UI/UX)- The Click me button code is displayed as a label name | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 781 | Creation Engine-Component Tab(UI/UX)- The multiselect dropdown does not show any values | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 782 | Creation Engine-Component Tab(UI/UX)- Multiple sidebar navigation options are displayed in the Navigation Section | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 783 | Creation Engine-Header(UI/UX)- The menu/page dropdown collapse under the dashboard layout header, partially hiding its values | PRODUCT BACKLOG | Edwin | 2025-03-26 | medium
|  | 793 | Creation Engine-Right panel(UI/UX)- All section features are open by default (plus symbol enabled), and only the section header is shown by default. | PRODUCT BACKLOG | Edwin | 2025-03-27 | medium
|  | 796 | Creation Engine-Right Tab(UI/UX)- The Layout Components section header appears in a distinct color | PRODUCT BACKLOG | Edwin | 2025-03-27 | low

## Testing Plan & Progress
S.No. | Feature List | Status
1 | Canvas Editor | Done
2 | Elements Tab & Layers tab | Done
3 | Basic layout using Lest Panel | Done
4 | Basic layout using Right Panel | Done
5 | Create, Update and Delete(Cred) | Done
6 | Components tab | Done
7 | Theme Icons | Done
8 | Right Side Panel | Done
9 | Chat with AI | Not Test 1)The current AI chat function is generate the New code have connect with Open Api, 2) But the expected feature is Open ai understand the prompt and assble our existing Elements

## Sheet1
Creation Engine
S.NO | Bug ID. | Description | Severity | Assigned To
1 | 669 | Creation Engine-Canvas Editor(Functional)- Canvas Editor display the existing project details when a new project is created by the user | critical | Edwin
2 | 670 | Creation Engine-Canvas Editor(Functional)- The drag and drop function fails when the user creates a new project for the first time | high | Edwin
3 | 672 | Creation Engine-Canvas Editor(Functional)- The "Create app using chat" feature doesn't work when a new project is created for the first time | high | Edwin
4 | 673 | Creation Engine-Canvas Editor(Functional)- Without the app layout, users cannot view the app in preview mode | high | Edwin
5 | 674 | Creation Engine-Layers Tab(Functional)- The deleted menu name continues to display in another screen backend and database | high | Edwin
6 | 675 | Creation Engine-Canvas Editor(Functional)- The drag and drop function is not operating smoothly | high | Edwin
7 | 676 | Creation Engine-Canvas Editor(Functional)- The user cannot see small and simple words when the inline editing feature is enabled | high | Edwin
8 | 677 | Creation Engine-Canvas Editor(Functional)- The resize feature does not meet current market standards | high | Edwin
9 | 678 | Creation Engine-Canvas Editor(Functional)- The element drag and drop feature isn't working within the structure of the div | high | Edwin
10 | 679 | Creation Engine-Canvas Editor(Functional)- The system auto-saves once an element is resized, but it doesn't complete the auto-save process before the user attempts to resize again | high | Edwin
11 | 680 | Creation Engine-Canvas Editor(Functional)- Unwanted components are displayed in the Basic Elements section | high | Edwin
12 | 681 | Creation Engine-Canvas Editor(Functional)- When a user adds spaces in the Heading div, unwanted and confusing content displays in the canvas. | high | Edwin
13 | 682 | Creation Engine-Canvas Editor(Functional)- There is no height resize option available for any element | high | Edwin
14 | 683 | Creation Engine-Right panel(Functional)- The right-side panel shows two confusing layouts section values | high | Edwin
15 | 684 | Creation Engine-Canvas Editor(Functional)- By default, the font size and color do not display when the user clicks the settings button in any element | high | Edwin
16 | 685 | Creation Engine-Layers Tab(Functional)- The menu create field allows more than 500 characters | high | Edwin
17 | 686 | Creation Engine-Layers Tab(Functional)- The delete icon is not visible when more than 10 characters are entered in the menu create field | high | Edwin
18 | 687 | Creation Engine-Layers Tab(Functional)- The delete icon does not display for a single menu available, and there is no instruction explaining why the delete icon is missing | medium | Edwin
19 | 688 | Creation Engine-Layers Tab(Functional)- Unwanted layers section is displayed in the layers tab | high | Edwin
20 | 689 | Creation Engine-Canvas Editor(Functional)- Three save options in the Creation Engine cause confusion for the end user | high | Edwin
21 | 690 | Creation Engine-Right panel(Functional)- The unwanted validation section displays in the Creation right panel | high | Edwin
22 | 691 | Creation Engine-Elements Tab(Functional)- Multiple top navigation bar elements are displayed in the Layout-Component section | medium | Edwin
23 | 692 | Creation Engine-Canvas Editor(Functional)- The user is unable to create top menus or pages; only side menus or pages are available | critical | Edwin
24 | 693 | Creation Engine-Canvas Editor(Functional)- The user cannot clear or delete multiple elements on one page | high | Edwin
25 | 694 | Creation Engine-Canvas Editor(Functional)- The user cannot add new content or words using the container-layout elements | high | Edwin
26 | 695 | Creation Engine-Canvas Editor(Functional)- The user cannot add any element after the fixed layout with the sidebar layout element section is added | high | Edwin
27 | 696 | Creation Engine-Canvas Editor(Functional)- Two layout sections display when the fixed layout is added to the left panel, which creates confusion | critical | Edwin
28 | 697 | Creation Engine-Canvas Editor(Functional)- The user cannot create any single element for Menu-2 after the fixed layout is added using the left panel | critical | Edwin
29 | 698 | Creation Engine-Canvas Editor(Functional)- The user is unable to update the color after the layout is added | high | Edwin
30 | 699 | Creation Engine-Canvas Editor(Functional)- The updated layout does not display in the canvas editor | high | Edwin
31 | 700 | Creation Engine-Canvas Editor(Functional)- The user cannot delete layout content that was added using the right panel | high | Edwin
32 | 701 | Creation Engine-Elements Tab(Functional)- Only basic master page related fields and elements are displayed in the elements section | high | Edwin
33 | 702 | Creation Engine-Layers Tab(Functional)- When the user adds a page, there is no success message displayed | high | Edwin
34 | 703 | Creation Engine-Left Panel(Functional)- There is confusion regarding the tab name in the Creation Engine left panel (1.Elements, 2.Layers, 3.Components); the basic logic for the tab name is missing | high | Edwin
35 | 704 | Creation Engine-Canvas Editor(Functional)- Deleted pages or menus still display in the Canvas Editor section | high | Edwin
36 | 705 | Creation Engine-Canvas Editor(Functional)- There is no option to revert the applied Layout-Right panel | high | Edwin
37 | 706 | Creation Engine-Canvas Editor(Functional)- The user is unable to resize or maximize the already minimized field | high | Edwin
38 | 707 | Creation Engine-Canvas Editor(Functional)- The user cannot add new pages or menus as the top menu | high | Edwin
39 | 708 | Creation Engine-Canvas Editor(Functional)- There is no toast message displayed when a page is deleted | high | Edwin
40 | 709 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the logo in the | high | Edwin
41 | 710 | Creation Engine-Canvas Editor(Functional)- The user cannot edit the progress bar or table element in the Canvas Editor | high | Edwin
42 | 711 | Creation Engine-Layer Tab(Functional)- The updated menu/page value is not displayed in the Layers section-left panel. | high | Edwin
43 | 712 | Creation Engine-Elements Tab(Functional)- There is confusion between the Basic Elements and Form sections in the Element tab-left panel. | high | Edwin
44 | 713 | Creation Engine-Canvas Editor(Functional)- The user is unable to add elements in the second tab (Tabbar components) of the Canvas Editor | high | Edwin
45 | 714 | Creation Engine-Canvas Editor(Functional)- The dashboard button is displayed as clicked, but the user cannot change the view mode after adding the Layout-Right panel. | medium | Edwin
46 | 715 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the page/menu background color in the canvas editor | high | Edwin
47 | 716 | Creation Engine-Canvas Editor(Functional)- Resizing does not work in the page/menu within the canvas editor | high | Edwin
48 | 717 | Creation Engine-Canvas Editor(Functional)- The user is unable to view the entire element after adding multiple templates in the canvas editor | high | Edwin
49 | 718 | Creation Engine-Canvas Editor(Functional)- The Save & Load section is don't want available in the right-side panel | high | Edwin
50 | 719 | Creation Engine-Right Panel(Functional)- The user can link any available page/menu to any field or element | high | Edwin
51 | 720 | Creation Engine-Components Tab(Functional)- Unable to save the New component in Components tab | high | Edwin
52 | 721 | Creation Engine-Components Tab(Functional)- In the Preview section, display the Code also along with element UI (Create the Circle Loader) | critical | Edwin
53 | 722 | Creation Engine-Components Tab(Functional)- Some of the element not create the by AI(Createthe 10 sort icon) | high | Edwin
54 | 723 | Creation Engine-Components Tab(Functional)- Unable to perform paste the values in Ai chat field | medium | Edwin
55 | 724 | Creation Engine-Components Tab(Functional)- Create New Components pop up getting close when click away from the pop up | medium | Edwin
56 | 725 | Creation Engine-Components Tab(Functional)- When user send the message as hi then chat field display the Hi related elememnt code | medium | Edwin
57 | 726 | Creation Engine-Components Tab(Functional)- The pop up getting close when user click the get help dropdown | high | Edwin
58 | 727 | Creation Engine-Components Tab(Functional)- Updated existing components is not display the updated code | medium | Edwin
59 | 728 | Creation Engine-Components Tab(Functional)- Two different pop up display for Component create and Edit, user can getting confuse a lot of edit the component for existing elemet and create the component using ai | high | Edwin
60 | 729 | Creation Engine-Components Tab(Functional)- Image Element preview is display with error | high | Edwin
61 | 747 | Creation Engine-Right panel(Functional)- Drag-and-drop functionality in the Image Library Right Panel is not working | high | Edwin
62 | 748 | Creation Engine-Right panel(Functional)- No success message is displayed after deleting an uploaded image in the Image Library Right Panel | medium | Edwin
63 | 749 | Creation Engine-Right panel(Functional)- A user can upload files larger than 10 MB | high | Edwin
64 | 750 | Creation Engine-Right panel(Functional)- The system does not present the correct error message when uploading a <> JSON file | high | Edwin
65 | 751 | Creation Engine-Right panel(Functional)- Edit element Basic Styles are not functioning properly | high | Edwin
66 | 752 | Creation Engine-Right panel(Functional)- An unwanted Export Canvas section is shown in the Right Panel | high | Edwin
67 | 753 | Creation Engine-Layers Tab(UI/UX)- The Layers Tab appears second, but the system does not clearly explain why it is unable to drag and drop components | medium | Edwin
68 | 754 | Creation Engine-Layers Tab(UI/UX)- No message is shown prompting the user to create Pages/menus first before add the elements | medium | Edwin
69 | 755 | Creation Engine-Canvas Editor(UI/UX)- When resizing large word content, it collapses, causing display issues. | medium | Edwin
70 | 756 | Creation Engine-Canvas Editor(UI/UX)- The H1-heading appears as a pixelated label name | medium | Edwin
71 | 757 | Creation Engine-Canvas Editor(UI/UX)- The system fails to display H2, H3, and other elements | medium | Edwin
72 | 758 | Creation Engine-Canvas Editor(UI/UX)- The element category appears confusing, requiring users to rearrange both the element and its name | medium | Edwin
73 | 759 | Creation Engine-Canvas Editor(UI/UX)- Unwanted Image Elements are visible in the Basic Elements section | medium | Edwin
74 | 760 | Creation Engine-Canvas Editor(UI/UX)- The Close/Clear icon is visible in the Layout Components section-right panel, but the section can only be accessed once the user clears it | low | Edwin
75 | 761 | Creation Engine-Canvas Editor(UI/UX)- Two instances of the name "Simplita" are shown in the Creation Engine | medium | Edwin
76 | 762 | Creation Engine-Canvas Editor(UI/UX)- The unwanted Layers section is visible in the Layers tab | high | Edwin
77 | 763 | Creation Engine-Canvas Editor(UI/UX)- No tooltips or help tips are available for any icons | medium | Edwin
78 | 764 | Creation Engine-Canvas Editor(UI/UX)- The "Two columns" element does not display correctly in the Canvas editor | medium | Edwin
79 | 765 | Creation Engine-Canvas Editor(UI/UX)- Unwanted double quotes appear when adding any element to the canvas editor | medium | Edwin
80 | 766 | Creation Engine-Canvas Editor(UI/UX)- An unnecessary icon is displayed next to the Undo & Redo buttons in the header | medium | Edwin
81 | 767 | Creation Engine-Canvas Editor(UI/UX)- An unwanted navigation label appears after adding the Layout-Right panel | low | Edwin
82 | 768 | Creation Engine-Canvas Editor(UI/UX)- An empty circle appears before the Sign-In button after adding the Layout-Right panel | medium | Edwin
83 | 769 | Creation Engine-Canvas Editor(UI/UX)- The top menu is displayed in the middle of the page after adding the Layout-Right panel | medium | Edwin
84 | 770 | Creation Engine-Canvas Editor(UI/UX)- When dragging and dropping a button element in the Canvas editor, the button appears as a normal label | medium | Edwin
85 | 771 | Creation Engine-Canvas Editor(UI/UX)- The button element appears in two sections in the Components section on the left panel | medium | Edwin
86 | 772 | Creation Engine-Canvas Editor(UI/UX)- By default, all page/menu checkboxes are selected after clicking "Apply Layout," but the "Select All" checkbox appears unselected. | medium | Edwin
87 | 773 | Creation Engine-Component Tab(UI/UX)- Ai Assistant feature is displayed as a regular label name | medium | Edwin
88 | 774 | Creation Engine-Component Tab(UI/UX)- No error message appears when the user leaves the Component name field empty in the Components tab | medium | Edwin
89 | 775 | Creation Engine-Component Tab(UI/UX)- The header displays as "Component HTML*" but AI also generates other technologies | low | Edwin
90 | 776 | Creation Engine-Component Tab(UI/UX)- The tool/help tip for the Close icon in the Create New Component's popup is not visible | low | Edwin
91 | 777 | Creation Engine-Component Tab(UI/UX)- The field is labeled as Components Name, but should be labeled as Elements Name | medium | Edwin
92 | 778 | Creation Engine-Component Tab(UI/UX)- The chat field icon is missing in existing element pop up | medium | Edwin
93 | 779 | Creation Engine-Component Tab(UI/UX)- The element edit popup does not show the correct title | medium | Edwin
94 | 780 | Creation Engine-Component Tab(UI/UX)- The Click me button code is displayed as a label name | medium | Edwin
95 | 781 | Creation Engine-Component Tab(UI/UX)- The multiselect dropdown does not show any values | medium | Edwin
96 | 782 | Creation Engine-Component Tab(UI/UX)- Multiple sidebar navigation options are displayed in the Navigation Section | medium | Edwin
97 | 783 | Creation Engine-Header(UI/UX)- The menu/page dropdown collapse under the dashboard layout header, partially hiding its values | medium | Edwin
98 | 793 | Creation Engine-Right panel(UI/UX)- All section features are open by default (plus symbol enabled), and only the section header is shown by default | medium | Edwin
99 | 796 | Creation Engine-Right Tab(UI/UX)- The Layout Components section header appears in a distinct color | low | Edwin
100 | 730 | Creation Engine-Theme Tab(Functional)- Cancel applied theme function is not available for Theme tab | high | PeriyaSedhu
101 | 731 | Creation Engine-Theme Tab(Functional)- AI generate the Christmas's theme, but there is any properer user expect output is not receive | high | PeriyaSedhu
102 | 732 | Creation Engine-Theme Tab(Functional)- The secondary colour is not apply in the canvas editor page | high | PeriyaSedhu
103 | 733 | Creation Engine-Theme Tab(Functional)- User unable to delete the cretaed Theme | high | PeriyaSedhu
104 | 734 | Creation Engine-Theme Tab(Functional)- There is no success message display when user creates the new theme | high | PeriyaSedhu
105 | 735 | Creation Engine-Theme Tab(Functional)- User unable to delete the cretaed Theme | high | PeriyaSedhu
106 | 736 | Creation Engine-Theme Tab(Functional)- Fonts edit features is not working | high | PeriyaSedhu
107 | 737 | Creation Engine-Theme Tab(Functional)- Unable to change the text colour | high | PeriyaSedhu
108 | 738 | Creation Engine-Theme Tab(Functional)- System not display the updated success message when update the theme | high | PeriyaSedhu
109 | 739 | Creation Engine-Theme Tab(Functional)- Added theme color is not reflected the middle of the page, it hs refelect only in the side bar | high | PeriyaSedhu
110 | 740 | Creation Engine-Theme Tab(Functional)- The background theme is not reflect which is work for only Dashboard layout is applied | critical | PeriyaSedhu
111 | 741 | Creation Engine-Theme Tab(Functional)- User unable toadd the theme based on the menu/page, the theme going to add all menu/page, even which menu not include with layout | high | PeriyaSedhu
112 | 742 | Creation Engine-Theme Tab(Functional)- Theme is not override when user add the new along with existing colour for any field/element | high | PeriyaSedhu
113 | 743 | Creation Engine-Theme Tab(Functional)- User unable to add the Ai created Theme | critical | PeriyaSedhu
114 | 744 | Creation Engine-Theme Tab(Functional)- System not allow to upload 1 mb file | high | PeriyaSedhu
115 | 745 | Creation Engine-Theme Tab(Functional)- System not display proper error message when user upload <> JSON file | high | PeriyaSedhu
116 | 746 | Creation Engine-Theme Tab(Functional)- In that available Edit Theme panel the Background colour only update the app, other that no feature is not working | high | PeriyaSedhu
117 | 784 | Creation Engine-Theme Tab(UI/UX)- The Theme tab is not readily accessible to end users and does not appear by default | low | PeriyaSedhu
118 | 785 | Creation Engine-Theme Tab(UI/UX)- Some themes do not display their name/title | medium | PeriyaSedhu
119 | 786 | Creation Engine-Theme Tab(UI/UX)- The top navbar theme not getting change when a new theme is added | medium | PeriyaSedhu
120 | 788 | Creation Engine-Theme Tab(UI/UX)- The tool/help tip is not visible in the Theme tab | low | PeriyaSedhu
121 | 790 | Creation Engine-Theme Tab(UI/UX)- There is a mismatch between the theme name and its color in the Theme tab, showing "Light" but rendering black | medium | PeriyaSedhu