## Sheet2
Internal Preview Page
S.NO | Bug ID. | Description | Severity | Assigned To
1 | 857 | Internal Preview(Functional)- Without add the Layout the created app is not display in the Internal Preview page | critical | Vinoth
2 | 858 | Internal Preview(UI/UX)- The Menu name is not display as Internal Preview | high | Vinoth
3 | 859 | Internal Preview(Functional)- Deleted Menu/Pages display in Internal Preview page | high | Vinoth
4 | 860 | Internal Preview(Functional)- Created login page also display as menu in Internal preview | high | Vinoth
5 | 861 | Internal Preview(Functional)- Duplicate Progress bar display in Internal Preview page | high | Vinoth
6 | 862 | Internal Preview(Functional)- System not display the Added search box, Filter is not display in Internal Preview page | high | Vinoth
7 | 863 | Internal Preview(Functional)- First displayed menu based page content not display when navigate to Internal Preview page | high | Vinoth
8 | 864 | Internal Preview(Functional)- User can save the components for multiple time, system not display any information message for this issue | medium | Vinoth
9 | 865 | Internal Preview(UI/UX)- There is no Tool/Help tip is not display in the Internal Preview page | medium | Vinoth
10 | 866 | Internal Preview(UI/UX)- Page Header is not display in the Internal Preview page | high | Vinoth
11 | 867 | Internal Preview(UI/UX)- Dual error message display in Internal Preview page when the validation added for the field | high | Vinoth
12 | 868 | Internal Preview(UI/UX)- User unable to click the First check box in Tab bar section | medium | Vinoth
13 | 869 | Internal Preview(UI/UX)- The menu item on the dashboard is selected, yet no corresponding components are shown | medium | Vinoth