## Pivot_Chart for Bug List
| Count of Severity | Column Labels
S.NO. | Row Labels | critical | high | low | medium | Grand Total | Resourse
1 | Admin Engine |  | 11 | 1 | 14 | 26 | Sai
2 | Authentication Engine | 2 | 15 | 5 | 9 | 31 | PeriyaSedhu
3 | Creation Engine | 7 | 69 | 7 | 38 | 121 | Edwin
4 | DB Engine | 2 | 25 | 1 | 13 | 41 | saravana
5 | Deployment Engine | 1 | 9 |  | 7 | 17 | Sai
6 | Internal Preview | 1 | 8 |  | 4 | 13 | Vinoth
7 | Rules Engine | 3 | 23 | 1 | 9 | 36 | Edwin
| Grand Total | 16 | 160 | 15 | 94 | 285

## Bug List
S.NO | Module name | Bug ID. | Description | Severity | Assigned To
1 | Authentication Engine | 620 | Login Page(Functional)- The "Forgot Password" feature is not functioning as expect | high | PeriyaSedhu
2 | Authentication Engine | 621 | Login Page(Functional)- A misleading error message appears when users enter an invalid email and attempt to sign in | high | PeriyaSedhu
3 | Authentication Engine | 622 | Login Page(Functional)- Sign-In Data Carrying Over to Sign-Up Tab: Fields in the Sign-In tab persist when navigating to Sign-Up | high | PeriyaSedhu
4 | Authentication Engine | 623 | Login Page(Functional)- Users are unable to update their existing credentials | high | PeriyaSedhu
5 | Authentication Engine | 624 | Login Page(Functional)- The Terms & Conditions pop-up does not appear when clicking the hyperlink | high | PeriyaSedhu
6 | Authentication Engine | 625 | Login Page(Functional)- Forgot Password" is displayed as a label instead of a clickable hyperlink | medium | PeriyaSedhu
7 | Authentication Engine | 626 | Login Page(Functional)- Basic Email validation error is not display in Reset Password pop up | high | PeriyaSedhu
8 | Authentication Engine | 627 | Login Page(Functional)- Unwanted page display when user click the rest password Link in received mail | high | PeriyaSedhu
9 | Authentication Engine | 628 | Login Page(Functional)- Reset Password pop up getting close when click outside the Reset Password pop-up | high | PeriyaSedhu
10 | Authentication Engine | 629 | Login Page(Functional)- Email Field Permits Invalid Special Characters, Allowing Fake or Improper Account Registration | high | PeriyaSedhu
11 | Authentication Engine | 630 | Login Page(Functional)- User try to create new account with max character missguidance error message display | high | PeriyaSedhu
12 | Authentication Engine | 631 | Login Page(Functional)- The Email ID and Password fields accept more than 500 characters, exceeding standard input limits | high | PeriyaSedhu
13 | Authentication Engine | 635 | Login Page(Functional)- The Password field allows users to save with more than 50 characters and even create an account with a 72-character password | high | PeriyaSedhu
14 | Authentication Engine | 637 | Login Page(Functional)- The proper validation error message is missing for Password field when user skip the field | high | PeriyaSedhu
15 | Authentication Engine | 638 | Login Page(Functional)- No Error Message display When click the Creating an Account button Without Email & Password | high | PeriyaSedhu
16 | Authentication Engine | 639 | Login Page(Functional)- The Reset Password email does not contain any reference to Simplita.ai, making it unclear where the email is coming from | high | PeriyaSedhu
17 | Authentication Engine | 640 | Login Page(Functional)- The error message continues to display even after entering a valid value, following an initial invalid input | medium | PeriyaSedhu
18 | Authentication Engine | 641 | Login Page(UI/UX)- Login success message is not displayed correctly | medium | PeriyaSedhu
19 | Authentication Engine | 642 | Login Page(UI/UX)- Label displayed as "Email ID" instead of "Email ID." (Dot missing in "ID.") | low | PeriyaSedhu
20 | Authentication Engine | 643 | Login Page(UI/UX)- Tooltip/help text missing for "Show Password" option | medium | PeriyaSedhu
21 | Authentication Engine | 644 | Login Page(UI/UX)- The Email ID and Password fields do not indicate they are required fields | medium | PeriyaSedhu
22 | Authentication Engine | 645 | Login Page(UI/UX)- The password suggestion error message does not disappear unless all conditions are met | medium | PeriyaSedhu
23 | Authentication Engine | 646 | Login Page(UI/UX)- The login page background does not meet design expectations. | medium | PeriyaSedhu
24 | Authentication Engine | 647 | Login Page(UI/UX)- Simplita.ai logo & company name should be display as bold but currently appear in normal text | low | PeriyaSedhu
25 | Authentication Engine | 648 | Login Page(UI/UX)- Sign-Up page is missing the Username field | low | PeriyaSedhu
26 | Authentication Engine | 649 | Login Page(UI/UX)- There is missmatch between Email ID.lable name and placeholder | low | PeriyaSedhu
27 | Authentication Engine | 650 | Login Page(UI/UX)- Duplicate Error Messages Shown for Invalid Email Entry | low | PeriyaSedhu
28 | Authentication Engine | 651 | Login Page(UI/UX)- There is an inconsistency in label names on the Sign In/Sign Up page. The email field is labeled as "Email ID," while the Reset password pop-up displays "Email Address" | medium | PeriyaSedhu
29 | Authentication Engine | 652 | Login Page(UI/UX)- Cancel button display as Label name in Reset password pop-up | medium | PeriyaSedhu
30 | Authentication Engine | 666 | Login Page(Functional)- Unable to click the "Create Account" button on the Sign-Up page, when give valid value and move the Sign up tab | critical | PeriyaSedhu
31 | Authentication Engine | 667 | Login Page(Functional)- User unable to create the new user with valid credtial | critical | PeriyaSedhu
32 | Creation Engine | 669 | Creation Engine-Canvas Editor(Functional)- Canvas Editor display the existing project details when a new project is created by the user | critical | Edwin
33 | Creation Engine | 670 | Creation Engine-Canvas Editor(Functional)- The drag and drop function fails when the user creates a new project for the first time | high | Edwin
34 | Creation Engine | 672 | Creation Engine-Canvas Editor(Functional)- The "Create app using chat" feature doesn't work when a new project is created for the first time | high | Edwin
35 | Creation Engine | 673 | Creation Engine-Canvas Editor(Functional)- Without the app layout, users cannot view the app in preview mode | high | Edwin
36 | Creation Engine | 674 | Creation Engine-Layers Tab(Functional)- The deleted menu name continues to display in another screen backend and database | high | Edwin
37 | Creation Engine | 675 | Creation Engine-Canvas Editor(Functional)- The drag and drop function is not operating smoothly | high | Edwin
38 | Creation Engine | 676 | Creation Engine-Canvas Editor(Functional)- The user cannot see small and simple words when the inline editing feature is enabled | high | Edwin
39 | Creation Engine | 677 | Creation Engine-Canvas Editor(Functional)- The resize feature does not meet current market standards | high | Edwin
40 | Creation Engine | 678 | Creation Engine-Canvas Editor(Functional)- The element drag and drop feature isn't working within the structure of the div | high | Edwin
41 | Creation Engine | 679 | Creation Engine-Canvas Editor(Functional)- The system auto-saves once an element is resized, but it doesn't complete the auto-save process before the user attempts to resize again | high | Edwin
42 | Creation Engine | 680 | Creation Engine-Canvas Editor(Functional)- Unwanted components are displayed in the Basic Elements section | high | Edwin
43 | Creation Engine | 681 | Creation Engine-Canvas Editor(Functional)- When a user adds spaces in the Heading div, unwanted and confusing content displays in the canvas. | high | Edwin
44 | Creation Engine | 682 | Creation Engine-Canvas Editor(Functional)- There is no height resize option available for any element | high | Edwin
45 | Creation Engine | 683 | Creation Engine-Right panel(Functional)- The right-side panel shows two confusing layouts section values | high | Edwin
46 | Creation Engine | 684 | Creation Engine-Canvas Editor(Functional)- By default, the font size and color do not display when the user clicks the settings button in any element | high | Edwin
47 | Creation Engine | 685 | Creation Engine-Layers Tab(Functional)- The menu create field allows more than 500 characters | high | Edwin
48 | Creation Engine | 686 | Creation Engine-Layers Tab(Functional)- The delete icon is not visible when more than 10 characters are entered in the menu create field | high | Edwin
49 | Creation Engine | 687 | Creation Engine-Layers Tab(Functional)- The delete icon does not display for a single menu available, and there is no instruction explaining why the delete icon is missing | medium | Edwin
50 | Creation Engine | 688 | Creation Engine-Layers Tab(Functional)- Unwanted layers section is displayed in the layers tab | high | Edwin
51 | Creation Engine | 689 | Creation Engine-Canvas Editor(Functional)- Three save options in the Creation Engine cause confusion for the end user | high | Edwin
52 | Creation Engine | 690 | Creation Engine-Right panel(Functional)- The unwanted validation section displays in the Creation right panel | high | Edwin
53 | Creation Engine | 691 | Creation Engine-Elements Tab(Functional)- Multiple top navigation bar elements are displayed in the Layout-Component section | medium | Edwin
54 | Creation Engine | 692 | Creation Engine-Canvas Editor(Functional)- The user is unable to create top menus or pages; only side menus or pages are available | critical | Edwin
55 | Creation Engine | 693 | Creation Engine-Canvas Editor(Functional)- The user cannot clear or delete multiple elements on one page | high | Edwin
56 | Creation Engine | 694 | Creation Engine-Canvas Editor(Functional)- The user cannot add new content or words using the container-layout elements | high | Edwin
57 | Creation Engine | 695 | Creation Engine-Canvas Editor(Functional)- The user cannot add any element after the fixed layout with the sidebar layout element section is added | high | Edwin
58 | Creation Engine | 696 | Creation Engine-Canvas Editor(Functional)- Two layout sections display when the fixed layout is added to the left panel, which creates confusion | critical | Edwin
59 | Creation Engine | 697 | Creation Engine-Canvas Editor(Functional)- The user cannot create any single element for Menu-2 after the fixed layout is added using the left panel | critical | Edwin
60 | Creation Engine | 698 | Creation Engine-Canvas Editor(Functional)- The user is unable to update the color after the layout is added | high | Edwin
61 | Creation Engine | 699 | Creation Engine-Canvas Editor(Functional)- The updated layout does not display in the canvas editor | high | Edwin
62 | Creation Engine | 700 | Creation Engine-Canvas Editor(Functional)- The user cannot delete layout content that was added using the right panel | high | Edwin
63 | Creation Engine | 701 | Creation Engine-Elements Tab(Functional)- Only basic master page related fields and elements are displayed in the elements section | high | Edwin
64 | Creation Engine | 702 | Creation Engine-Layers Tab(Functional)- When the user adds a page, there is no success message displayed | high | Edwin
65 | Creation Engine | 703 | Creation Engine-Left Panel(Functional)- There is confusion regarding the tab name in the Creation Engine left panel (1.Elements, 2.Layers, 3.Components); the basic logic for the tab name is missing | high | Edwin
66 | Creation Engine | 704 | Creation Engine-Canvas Editor(Functional)- Deleted pages or menus still display in the Canvas Editor section | high | Edwin
67 | Creation Engine | 705 | Creation Engine-Canvas Editor(Functional)- There is no option to revert the applied Layout-Right panel | high | Edwin
68 | Creation Engine | 706 | Creation Engine-Canvas Editor(Functional)- The user is unable to resize or maximize the already minimized field | high | Edwin
69 | Creation Engine | 707 | Creation Engine-Canvas Editor(Functional)- The user cannot add new pages or menus as the top menu | high | Edwin
70 | Creation Engine | 708 | Creation Engine-Canvas Editor(Functional)- There is no toast message displayed when a page is deleted | high | Edwin
71 | Creation Engine | 709 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the logo in the | high | Edwin
72 | Creation Engine | 710 | Creation Engine-Canvas Editor(Functional)- The user cannot edit the progress bar or table element in the Canvas Editor | high | Edwin
73 | Creation Engine | 711 | Creation Engine-Layer Tab(Functional)- The updated menu/page value is not displayed in the Layers section-left panel. | high | Edwin
74 | Creation Engine | 712 | Creation Engine-Elements Tab(Functional)- There is confusion between the Basic Elements and Form sections in the Element tab-left panel. | high | Edwin
75 | Creation Engine | 713 | Creation Engine-Canvas Editor(Functional)- The user is unable to add elements in the second tab (Tabbar components) of the Canvas Editor | high | Edwin
76 | Creation Engine | 714 | Creation Engine-Canvas Editor(Functional)- The dashboard button is displayed as clicked, but the user cannot change the view mode after adding the Layout-Right panel. | medium | Edwin
77 | Creation Engine | 715 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the page/menu background color in the canvas editor | high | Edwin
78 | Creation Engine | 716 | Creation Engine-Canvas Editor(Functional)- Resizing does not work in the page/menu within the canvas editor | high | Edwin
79 | Creation Engine | 717 | Creation Engine-Canvas Editor(Functional)- The user is unable to view the entire element after adding multiple templates in the canvas editor | high | Edwin
80 | Creation Engine | 718 | Creation Engine-Canvas Editor(Functional)- The Save & Load section is don't want available in the right-side panel | high | Edwin
81 | Creation Engine | 719 | Creation Engine-Right Panel(Functional)- The user can link any available page/menu to any field or element | high | Edwin
82 | Creation Engine | 720 | Creation Engine-Components Tab(Functional)- Unable to save the New component in Components tab | high | Edwin
83 | Creation Engine | 721 | Creation Engine-Components Tab(Functional)- In the Preview section, display the Code also along with element UI (Create the Circle Loader) | critical | Edwin
84 | Creation Engine | 722 | Creation Engine-Components Tab(Functional)- Some of the element not create the by AI(Createthe 10 sort icon) | high | Edwin
85 | Creation Engine | 723 | Creation Engine-Components Tab(Functional)- Unable to perform paste the values in Ai chat field | medium | Edwin
86 | Creation Engine | 724 | Creation Engine-Components Tab(Functional)- Create New Components pop up getting close when click away from the pop up | medium | Edwin
87 | Creation Engine | 725 | Creation Engine-Components Tab(Functional)- When user send the message as hi then chat field display the Hi related elememnt code | medium | Edwin
88 | Creation Engine | 726 | Creation Engine-Components Tab(Functional)- The pop up getting close when user click the get help dropdown | high | Edwin
89 | Creation Engine | 727 | Creation Engine-Components Tab(Functional)- Updated existing components is not display the updated code | medium | Edwin
90 | Creation Engine | 728 | Creation Engine-Components Tab(Functional)- Two different pop up display for Component create and Edit, user can getting confuse a lot of edit the component for existing elemet and create the component using ai | high | Edwin
91 | Creation Engine | 729 | Creation Engine-Components Tab(Functional)- Image Element preview is display with error | high | Edwin
92 | Creation Engine | 747 | Creation Engine-Right panel(Functional)- Drag-and-drop functionality in the Image Library Right Panel is not working | high | Edwin
93 | Creation Engine | 748 | Creation Engine-Right panel(Functional)- No success message is displayed after deleting an uploaded image in the Image Library Right Panel | medium | Edwin
94 | Creation Engine | 749 | Creation Engine-Right panel(Functional)- A user can upload files larger than 10 MB | high | Edwin
95 | Creation Engine | 750 | Creation Engine-Right panel(Functional)- The system does not present the correct error message when uploading a <> JSON file | high | Edwin
96 | Creation Engine | 751 | Creation Engine-Right panel(Functional)- Edit element Basic Styles are not functioning properly | high | Edwin
97 | Creation Engine | 752 | Creation Engine-Right panel(Functional)- An unwanted Export Canvas section is shown in the Right Panel | high | Edwin
98 | Creation Engine | 753 | Creation Engine-Layers Tab(UI/UX)- The Layers Tab appears second, but the system does not clearly explain why it is unable to drag and drop components | medium | Edwin
99 | Creation Engine | 754 | Creation Engine-Layers Tab(UI/UX)- No message is shown prompting the user to create Pages/menus first before add the elements | medium | Edwin
100 | Creation Engine | 755 | Creation Engine-Canvas Editor(UI/UX)- When resizing large word content, it collapses, causing display issues. | medium | Edwin
101 | Creation Engine | 756 | Creation Engine-Canvas Editor(UI/UX)- The H1-heading appears as a pixelated label name | medium | Edwin
102 | Creation Engine | 757 | Creation Engine-Canvas Editor(UI/UX)- The system fails to display H2, H3, and other elements | medium | Edwin
103 | Creation Engine | 758 | Creation Engine-Canvas Editor(UI/UX)- The element category appears confusing, requiring users to rearrange both the element and its name | medium | Edwin
104 | Creation Engine | 759 | Creation Engine-Canvas Editor(UI/UX)- Unwanted Image Elements are visible in the Basic Elements section | medium | Edwin
105 | Creation Engine | 760 | Creation Engine-Canvas Editor(UI/UX)- The Close/Clear icon is visible in the Layout Components section-right panel, but the section can only be accessed once the user clears it | low | Edwin
106 | Creation Engine | 761 | Creation Engine-Canvas Editor(UI/UX)- Two instances of the name "Simplita" are shown in the Creation Engine | medium | Edwin
107 | Creation Engine | 762 | Creation Engine-Canvas Editor(UI/UX)- The unwanted Layers section is visible in the Layers tab | high | Edwin
108 | Creation Engine | 763 | Creation Engine-Canvas Editor(UI/UX)- No tooltips or help tips are available for any icons | medium | Edwin
109 | Creation Engine | 764 | Creation Engine-Canvas Editor(UI/UX)- The "Two columns" element does not display correctly in the Canvas editor | medium | Edwin
110 | Creation Engine | 765 | Creation Engine-Canvas Editor(UI/UX)- Unwanted double quotes appear when adding any element to the canvas editor | medium | Edwin
111 | Creation Engine | 766 | Creation Engine-Canvas Editor(UI/UX)- An unnecessary icon is displayed next to the Undo & Redo buttons in the header | medium | Edwin
112 | Creation Engine | 767 | Creation Engine-Canvas Editor(UI/UX)- An unwanted navigation label appears after adding the Layout-Right panel | low | Edwin
113 | Creation Engine | 768 | Creation Engine-Canvas Editor(UI/UX)- An empty circle appears before the Sign-In button after adding the Layout-Right panel | medium | Edwin
114 | Creation Engine | 769 | Creation Engine-Canvas Editor(UI/UX)- The top menu is displayed in the middle of the page after adding the Layout-Right panel | medium | Edwin
115 | Creation Engine | 770 | Creation Engine-Canvas Editor(UI/UX)- When dragging and dropping a button element in the Canvas editor, the button appears as a normal label | medium | Edwin
116 | Creation Engine | 771 | Creation Engine-Canvas Editor(UI/UX)- The button element appears in two sections in the Components section on the left panel | medium | Edwin
117 | Creation Engine | 772 | Creation Engine-Canvas Editor(UI/UX)- By default, all page/menu checkboxes are selected after clicking "Apply Layout," but the "Select All" checkbox appears unselected. | medium | Edwin
118 | Creation Engine | 773 | Creation Engine-Component Tab(UI/UX)- Ai Assistant feature is displayed as a regular label name | medium | Edwin
119 | Creation Engine | 774 | Creation Engine-Component Tab(UI/UX)- No error message appears when the user leaves the Component name field empty in the Components tab | medium | Edwin
120 | Creation Engine | 775 | Creation Engine-Component Tab(UI/UX)- The header displays as "Component HTML*" but AI also generates other technologies | low | Edwin
121 | Creation Engine | 776 | Creation Engine-Component Tab(UI/UX)- The tool/help tip for the Close icon in the Create New Component's popup is not visible | low | Edwin
122 | Creation Engine | 777 | Creation Engine-Component Tab(UI/UX)- The field is labeled as Components Name, but should be labeled as Elements Name | medium | Edwin
123 | Creation Engine | 778 | Creation Engine-Component Tab(UI/UX)- The chat field icon is missing in existing element pop up | medium | Edwin
124 | Creation Engine | 779 | Creation Engine-Component Tab(UI/UX)- The element edit popup does not show the correct title | medium | Edwin
125 | Creation Engine | 780 | Creation Engine-Component Tab(UI/UX)- The Click me button code is displayed as a label name | medium | Edwin
126 | Creation Engine | 781 | Creation Engine-Component Tab(UI/UX)- The multiselect dropdown does not show any values | medium | Edwin
127 | Creation Engine | 782 | Creation Engine-Component Tab(UI/UX)- Multiple sidebar navigation options are displayed in the Navigation Section | medium | Edwin
128 | Creation Engine | 783 | Creation Engine-Header(UI/UX)- The menu/page dropdown collapse under the dashboard layout header, partially hiding its values | medium | Edwin
129 | Creation Engine | 793 | Creation Engine-Right panel(UI/UX)- All section features are open by default (plus symbol enabled), and only the section header is shown by default | medium | Edwin
130 | Creation Engine | 796 | Creation Engine-Right Tab(UI/UX)- The Layout Components section header appears in a distinct color | low | Edwin
131 | Creation Engine | 730 | Creation Engine-Theme Tab(Functional)- Cancel applied theme function is not available for Theme tab | high | PeriyaSedhu
132 | Creation Engine | 731 | Creation Engine-Theme Tab(Functional)- AI generate the Christmas's theme, but there is any properer user expect output is not receive | high | PeriyaSedhu
133 | Creation Engine | 732 | Creation Engine-Theme Tab(Functional)- The secondary colour is not apply in the canvas editor page | high | PeriyaSedhu
134 | Creation Engine | 733 | Creation Engine-Theme Tab(Functional)- User unable to delete the cretaed Theme | high | PeriyaSedhu
135 | Creation Engine | 734 | Creation Engine-Theme Tab(Functional)- There is no success message display when user creates the new theme | high | PeriyaSedhu
136 | Creation Engine | 735 | Creation Engine-Theme Tab(Functional)- User unable to delete the cretaed Theme | high | PeriyaSedhu
137 | Creation Engine | 736 | Creation Engine-Theme Tab(Functional)- Fonts edit features is not working | high | PeriyaSedhu
138 | Creation Engine | 737 | Creation Engine-Theme Tab(Functional)- Unable to change the text colour | high | PeriyaSedhu
139 | Creation Engine | 738 | Creation Engine-Theme Tab(Functional)- System not display the updated success message when update the theme | high | PeriyaSedhu
140 | Creation Engine | 739 | Creation Engine-Theme Tab(Functional)- Added theme color is not reflected the middle of the page, it hs refelect only in the side bar | high | PeriyaSedhu
141 | Creation Engine | 740 | Creation Engine-Theme Tab(Functional)- The background theme is not reflect which is work for only Dashboard layout is applied | critical | PeriyaSedhu
142 | Creation Engine | 741 | Creation Engine-Theme Tab(Functional)- User unable toadd the theme based on the menu/page, the theme going to add all menu/page, even which menu not include with layout | high | PeriyaSedhu
143 | Creation Engine | 742 | Creation Engine-Theme Tab(Functional)- Theme is not override when user add the new along with existing colour for any field/element | high | PeriyaSedhu
144 | Creation Engine | 743 | Creation Engine-Theme Tab(Functional)- User unable to add the Ai created Theme | critical | PeriyaSedhu
145 | Creation Engine | 744 | Creation Engine-Theme Tab(Functional)- System not allow to upload 1 mb file | high | PeriyaSedhu
146 | Creation Engine | 745 | Creation Engine-Theme Tab(Functional)- System not display proper error message when user upload <> JSON file | high | PeriyaSedhu
147 | Creation Engine | 746 | Creation Engine-Theme Tab(Functional)- In that available Edit Theme panel the Background colour only update the app, other that no feature is not working | high | PeriyaSedhu
148 | Creation Engine | 784 | Creation Engine-Theme Tab(UI/UX)- The Theme tab is not readily accessible to end users and does not appear by default | low | PeriyaSedhu
149 | Creation Engine | 785 | Creation Engine-Theme Tab(UI/UX)- Some themes do not display their name/title | medium | PeriyaSedhu
150 | Creation Engine | 786 | Creation Engine-Theme Tab(UI/UX)- The top navbar theme not getting change when a new theme is added | medium | PeriyaSedhu
151 | Creation Engine | 788 | Creation Engine-Theme Tab(UI/UX)- The tool/help tip is not visible in the Theme tab | low | PeriyaSedhu
152 | Creation Engine | 790 | Creation Engine-Theme Tab(UI/UX)- There is a mismatch between the theme name and its color in the Theme tab, showing "Light" but rendering black | medium | PeriyaSedhu
153 | Internal Preview | 857 | Internal Preview(Functional)- Without add the Layout the created app is not display in the Internal Preview page | critical | Vinoth
154 | Internal Preview | 858 | Internal Preview(UI/UX)- The Menu name is not display as Internal Preview | high | Vinoth
155 | Internal Preview | 859 | Internal Preview(Functional)- Deleted Menu/Pages display in Internal Preview page | high | Vinoth
156 | Internal Preview | 860 | Internal Preview(Functional)- Created login page also display as menu in Internal preview | high | Vinoth
157 | Internal Preview | 861 | Internal Preview(Functional)- Duplicate Progress bar display in Internal Preview page | high | Vinoth
158 | Internal Preview | 862 | Internal Preview(Functional)- System not display the Added search box, Filter is not display in Internal Preview page | high | Vinoth
159 | Internal Preview | 863 | Internal Preview(Functional)- First displayed menu based page content not display when navigate to Internal Preview page | high | Vinoth
160 | Internal Preview | 864 | Internal Preview(Functional)- User can save the components for multiple time, system not display any information message for this issue | medium | Vinoth
161 | Internal Preview | 865 | Internal Preview(UI/UX)- There is no Tool/Help tip is not display in the Internal Preview page | medium | Vinoth
162 | Internal Preview | 866 | Internal Preview(UI/UX)- Page Header is not display in the Internal Preview page | high | Vinoth
163 | Internal Preview | 867 | Internal Preview(UI/UX)- Dual error message display in Internal Preview page when the validation added for the field | high | Vinoth
164 | Internal Preview | 868 | Internal Preview(UI/UX)- User unable to click the First check box in Tab bar section | medium | Vinoth
165 | Internal Preview | 869 | Internal Preview(UI/UX)- The menu item on the dashboard is selected, yet no corresponding components are shown | medium | Vinoth
166 | DB Engine | 971 | DB Engine(Functional)- When user click the Remove table icon then system display the error message | high | saravana
167 | DB Engine | 975 | DB Engine(Functional)- The DB engine generate the multiple column for single element radio button | high | saravana
168 | DB Engine | 978 | DB Engine(Functional)- Multiple tables are not generated by the multi-tab field; only one combined table is produced | high | saravana
169 | DB Engine | 979 | DB Engine(Functional)- Inconsistent field names in AI-generated columns may confuse end users; align them clearly | high | saravana
170 | DB Engine | 981 | DB Engine(Functional)- There is no confirmation message when user click the remove column | medium | saravana
171 | DB Engine | 982 | DB Engine(Functional)- Unable to update the table name at the single stretch | medium | saravana
172 | DB Engine | 983 | DB Engine(Functional)- The 'Set a Foreign Key' feature includes the current table as a selectable option, which isn't useful | high | saravana
173 | DB Engine | 984 | DB Engine(Functional)- User unable to update the column data types | high | saravana
174 | DB Engine | 985 | DB Engine(Functional)- User can create the column with 500 characters | high | saravana
175 | DB Engine | 986 | DB Engine(Functional)- Given column name value not getting clear when user click the add new button | medium | saravana
176 | DB Engine | 987 | DB Engine(Functional)- System not display any success message when ai generate the schema | medium | saravana
177 | DB Engine | 988 | DB Engine(Functional)- Given data type value not getting clear when user click the add new button | medium | saravana
178 | DB Engine | 989 | DB Engine(UI/UX)- Export Schema and Json viewer button name display partially | low | saravana
179 | DB Engine | 990 | DB Engine(Functional)- Column name required message not display in below the column name field | medium | saravana
180 | DB Engine | 991 | DB Engine(Functional)- User can delete the primary key column | high | saravana
181 | DB Engine | 992 | DB Engine(Functional)- System display the error message when click the any option in Export schema button without save the schema | high | saravana
182 | DB Engine | 993 | DB Engine(Functional)- System throw the error message when click the Add new table button without add the ai generate schema | critical | saravana
183 | DB Engine | 994 | DB Engine(Functional)- Ai getting generate schema for the deleted page also | critical | saravana
184 | DB Engine | 995 | DB Engine(Functional)- System allow to set the multiple primary key for single table | high | saravana
185 | DB Engine | 996 | DB Engine(Functional)- Multiple column delete getting delete while delete the single column | high | saravana
186 | DB Engine | 997 | DB Engine(Functional)- The system does not allow assigning both a primary key and a foreign key to the same column | high | saravana
187 | DB Engine | 998 | DB Engine(Functional)- System unable to create the new column in Tables section | high | saravana
188 | DB Engine | 999 | DB Engine(UI/UX)- Save column button display as lable name it is not display as button | medium | saravana
189 | DB Engine | 1000 | DB Engine(Functional)- Column name display as undefined when update the data type for primary key column | high | saravana
190 | DB Engine | 1001 | DB Engine(Functional)- Not able to select the check box for new column add section | high | saravana
191 | DB Engine | 1002 | DB Engine(Functional)- Delete success message is not display when user delete the column | high | saravana
192 | DB Engine | 1005 | DB Engine(Functional)- When a column is changed from 'Not Required' to 'Required' in the edit section, any previously available data in that column gets removed and the column vanishes | high | saravana
193 | DB Engine | 1006 | DB Engine(Functional)- Export Schema file display unwanted dummy value when user click the button | high | saravana
194 | DB Engine | 1007 | DB Engine(Functional)- Api Generator display exiting api when user delete the existing table | high | saravana
195 | DB Engine | 1008 | DB Engine(Functional)- Read, Write and Delete feature is not working in Credentials tab-API Generator | high | saravana
196 | DB Engine | 1010 | DB Engine(UI/UX)- Mismatch module name display for Database Engine | medium | saravana
197 | DB Engine | 1012 | DB Engine(Functional)- Unwanted Back to Top icon display and also it have hide the other needed button also | medium | saravana
198 | DB Engine | 1013 | DB Engine(Functional)- Duplicate Close icon display in Schema Change Analysis pop up | medium | saravana
199 | DB Engine | 1014 | DB Engine(UI/UX)- Unwanted Will Add icon display in Schema Change Analysis pop up | medium | saravana
200 | DB Engine | 1015 | DB Engine(Functional)- The Schema Change Analysis pop up getting close when user click the away from the pop up | medium | saravana
201 | DB Engine | 1017 | DB Engine(Functional)- Created schema not display in table section, it have display only the user click the refresh icon in browser | high | saravana
202 | DB Engine | 1018 | DB Engine(Functional)- Er Diagram created relation ship mapping not reflect in Table page | high | saravana
203 | DB Engine | 1019 | DB Engine(Functional)- Chat section is not create any kind of feature | high | saravana
204 | DB Engine | 1020 | DB Engine(Functional)- Created relation ship mapping not getting auto save, there is no any save button available for ER Diagram page | high | saravana
205 | DB Engine | 1021 | Migration Engine(Functional)- The system allow only to upload the .sql type file | high | saravana
206 | DB Engine | 1022 | Migration Engine(Functional)- System allow to upload than more 50 mb file | medium | saravana
207 | Rules Engine | 915 | Rules Engine(Functional)- The Success message is not display when user add the Condition and Calculation | medium | Edwin
208 | Rules Engine | 916 | Rules Engine(Functional)- User unable to see the existing added Condition and Calculation | high | Edwin
209 | Rules Engine | 917 | Rules Engine(Functional)- User unable to add the Condition and Calculation for the app without click the middle panel element | high | Edwin
210 | Rules Engine | 918 | Rules Engine(Functional)- User can delete the middle panel element using Keyboard shortcut | critical | Edwin
211 | Rules Engine | 919 | Rules Engine(Functional)- The Right panel dropdown display only the All Form value | medium | Edwin
212 | Rules Engine | 920 | Rules Engine(Functional)- "Field value" condition feature is not working fine | high | Edwin
213 | Rules Engine | 921 | Rules Engine(Functional)- Deleted success message is not display when delete the Conditions/Calculation | medium | Edwin
214 | Rules Engine | 922 | Rules Engine(Functional)- User can edit the any Label name and alos the page/menu name | high | Edwin
215 | Rules Engine | 923 | Rules Engine(Functional)- Unwanted field value condition is display in condition added function | high | Edwin
216 | Rules Engine | 924 | Rules Engine(Functional)-The same creation engine top header display in Rules, there is no purpose for the header in Rules engine | high | Edwin
217 | Rules Engine | 925 | Rules Engine(Functional)- User unable to add Conditions and Calculations in rules engine when click the any div(Header &Menu) <> label name or field | critical | Edwin
218 | Rules Engine | 926 | Rules Engine(Functional)- The radio button validation is not display in Validation menu | high | Edwin
219 | Rules Engine | 927 | Rules Engine(Functional)- Test validation display field display as text field for dropdown | high | Edwin
220 | Rules Engine | 928 | Rules Engine(Functional)- Number only allowed validation is missing in Validation section | high | Edwin
221 | Rules Engine | 929 | Rules Engine(Functional)- Dropdown field validation is not up to the standard | high | Edwin
222 | Rules Engine | 930 | Rules Engine(Functional)- By default some of the basic validation is not be display when user click the element | medium | Edwin
223 | Rules Engine | 931 | Rules Engine(Functional)- The password field validation is still being displayed in the Rules Engine, even after the field—originally created as a password type—is updated and renamed to “XYZ.” | high | Edwin
224 | Rules Engine | 932 | Rules Engine(Functional)- System not display the vaidation field section when user click the field div in middle panel | high | Edwin
225 | Rules Engine | 933 | Rules Engine(Functional)- System not display the vaidation field section when user click the field div in middle panel | high | Edwin
226 | Rules Engine | 934 | Rules Engine(Functional)- Action field display as empty when user select maths calculation in Condition Type | high | Edwin
227 | Rules Engine | 935 | Rules Engine(Functional)- The Success message is not display when user add the validation | high | Edwin
228 | Rules Engine | 936 | Rules Engine(Functional)- The Success message is not display when user add the Automation workflow | high | Edwin
229 | Rules Engine | 937 | Rules Engine(Functional)- The condition node is not in the working status, the node display any others fields | critical | Edwin
230 | Rules Engine | 938 | Rules Engine(Functional)- System not display the Maths calculation and Automated received Mail | high | Edwin
231 | Rules Engine | 939 | Rules Engine(Functional)- There is no option to validate the config mail is wright or not | high | Edwin
232 | Rules Engine | 940 | Rules Engine(Functional)- User can Run the Automatin flow without create the Scenario | high | Edwin
233 | Rules Engine | 941 | Rules Engine(Functional)- The Automatin workflow only display the Email only, basicly we need to display the 4 to 5 node | high | Edwin
234 | Rules Engine | 942 | Rules Engine(Functional)- Maths operation node is not display any field | high | Edwin
235 | Rules Engine | 943 | Rules Engine(UI/UX)- Two button display for create the conditions and Calculations but the feature added in single section | medium | Edwin
236 | Rules Engine | 944 | Rules Engine(UI/UX)- Confused Test validation field available in Validation Section | high | Edwin
237 | Rules Engine | 945 | Rules Engine(UI/UX)- User unable to change the date field format | medium | Edwin
238 | Rules Engine | 946 | Rules Engine(UI/UX)- The password label and its input type are displayed as collapsed in the interface | medium | Edwin
239 | Rules Engine | 947 | Rules Engine(UI/UX)- The max characters field should only accept numeric values, but it currently allows only the letter "e," which seems to be a validation issue | medium | Edwin
240 | Rules Engine | 948 | Rules Engine(UI/UX)- The summarize text label display partially in condition section | low | Edwin
241 | Rules Engine | 949 | Rules Engine(UI/UX)- The Scenario workflow is not start easily access for non-tech user | medium | Edwin
242 | Rules Engine | 950 | Rules Engine(UI/UX)- Unwanted Setting option is display in middle panel when user click the element | high | Edwin
243 | Deployment Engine | 1045 | Deployment Engine(Functional)- The deployed app is only displaying the form page; the rest of the application is not visible | critical | Sai
244 | Deployment Engine | 1046 | Deployment Engine(Functional)- Exported data is currently missing from the Docker Exports section | high | Sai
245 | Deployment Engine | 1047 | Deployment Engine(Functional)- The app cannot be deployed without saving the component, and the system shows a confusing error message | high | Sai
246 | Deployment Engine | 1048 | Deployment Engine(UI/UX)- The Deployment Engine menu is not easily accessible | medium | Sai
247 | Deployment Engine | 1049 | Deployment Engine(UI/UX)- Deployment header name is not display when navigate the page | medium | Sai
248 | Deployment Engine | 1050 | Deployment Engine(Functional)- The application deployed is showing intermittent blinking behavior without a consistent pattern | high | Sai
249 | Deployment Engine | 1051 | Deployment Engine(Functional)- The system displays a "Failed with code" error message when using an app apart from any combined template | high | Sai
250 | Deployment Engine | 1052 | Deployment Engine(Functional)- The deployed app is only displaying the form page; the rest of the application is not visible | high | Sai
251 | Deployment Engine | 1053 | Deployment Engine(Functional)- The "Build App" button remains active and clickable repeatedly, despite no modifications being made to the app | high | Sai
252 | Deployment Engine | 1054 | Deployment Engine(Functional)- The system displays an error message during the app build process, but it doesn’t provide a clear reason for the failure | high | Sai
253 | Deployment Engine | 1055 | Deployment Engine(Functional)- User unable to move any page in deployed app | high | Sai
254 | Deployment Engine | 1056 | Deployment Engine(UI/UX)- There are no tooltips/helptips displayed anywhere on the page | medium | Sai
255 | Deployment Engine | 1057 | Deployment Engine(UI/UX)- Avg. Duration not display value in Deployment History pop up | high | Sai
256 | Deployment Engine | 1058 | Deployment Engine(UI/UX)- Success Rate display mismatch value in Deployment History pop up | medium | Sai
257 | Deployment Engine | 1059 | Deployment Engine(UI/UX)- Version column display same value display for multiple row values | medium | Sai
258 | Deployment Engine | 1060 | Deployment Engine(UI/UX)- Duration & Actions not display value in Deployment History pop up | medium | Sai
259 | Deployment Engine | 1061 | Deployment Engine(UI/UX)- Currently I have deploy only one app but there is 2 values display in Deployment History pop up | medium | Sai
260 | Admin Engine | 1108 | Admin Engine(UI/UX)- The Admin Mode is not easily discoverable for non-technical users in deployed app | medium | sai
261 | Admin Engine | 1109 | Admin Engine(UI/UX)- Unwanted "Main Menu" label display in the header | low | sai
262 | Admin Engine | 1110 | Admin Engine(UI/UX)- The Button name display as list grid header in dashboard | medium | sai
263 | Admin Engine | 1111 | Admin Engine(UI/UX)- Any of the chart or list grid is not display in the Dashboard | medium | sai
264 | Admin Engine | 1112 | Admin Engine(Functional)- The Edit Role Hierarchy feature is not working | high | sai
265 | Admin Engine | 1113 | Admin Engine(Functional)- The Username field allow more than 500 charaters | medium | sai
266 | Admin Engine | 1114 | Admin Engine(Functional)- The proper Email validation is not display in the Users create page | high | sai
267 | Admin Engine | 1115 | Admin Engine(Functional)- The common validation required validation is not display in any of the master page | medium | sai
268 | Admin Engine | 1116 | Admin Engine(Functional)- The Roles field fails to display as a dropdown when the total role values exceed 50 entries. | high | sai
269 | Admin Engine | 1117 | Admin Engine(UI/UX)- Superuser field is not display as one of the Create User field | medium | sai
270 | Admin Engine | 1118 | Admin Engine(Functional)- Password show icon is not display in create User page | medium | sai
271 | Admin Engine | 1119 | Admin Engine(Functional)- Data Export option is not available for any of the master list grid | high | sai
272 | Admin Engine | 1120 | Admin Engine(Functional)- The proper error message is not display in edit user pop up | medium | sai
273 | Admin Engine | 1121 | Admin Engine(UI/UX)- The Column header alignment display improperly when change the Showing count dropdown values | medium | sai
274 | Admin Engine | 1122 | Admin Engine(UI/UX)- Unwanted url content display in delete confirmation pop-up | medium | sai
275 | Admin Engine | 1123 | Admin Engine(Functional)- Success message is display when user click the Save changes button without add any changes | medium | sai
276 | Admin Engine | 1124 | Admin Engine(Functional)- Grid is not displaying any records (UI shows empty), but bulk delete still deletes all records | medium | sai
277 | Admin Engine | 1125 | Admin Engine(Functional)- The search bar displays as an unusually lengthy field. It should have a standard width aligned with other UI elements | medium | sai
278 | Admin Engine | 1126 | Admin Engine(Functional)- The Admin Engine User module is visible for access, but the login page is not loading or available in the deployed application | high | sai
279 | Admin Engine | 1127 | Admin Engine(Functional)- Pagination showing count display feature is not display in Roles master page | high | sai
280 | Admin Engine | 1128 | Admin Engine(Functional)- All check box getting select only when click the View only check box | medium | sai
281 | Admin Engine | 1129 | Admin Engine(Functional)- System display the error message when delete the roles record | high | sai
282 | Admin Engine | 1130 | Admin Engine(Functional)- Test connection feature is not working | high | sai
283 | Admin Engine | 1131 | Admin Engine(Functional)- Users are able to set an inactive integration record as the default | high | sai
284 | Admin Engine | 1132 | Admin Engine(Functional)- Users are able to assign the 'Default' status to multiple integration records | high | sai
285 | Admin Engine | 1133 | Admin Engine(Functional)- The sort feature is not available for any master page | high | sai