## Testing Types
S.No. | Testing Types | Status
1 | Test Case Preparation | YTS
2 | Smoke Testing | YTS
3 | Functionalo Testing | YTS
4 | Bug Posting | YTS
5 | Bug Verification | YTS
6 | Closure Testing | YTS
S.No. | Module Name | Test Case Status | Testing Status | Bug Count | Remarks
1 | Authentication | Done | Done | 31 | 1. Login Page & Workspace is Testing Complete 2. Auth Login Template page smoke test fail
2 | Creation Engine(Theme) | Done | Done | 121
3 | Internal Preview | Done | Done | 13
4 | DB& Migration Engine | Done | Done | 41
5 | Rules Engine | Done | Done | 36
6 | Deployment Engine | Done | Done | 17
7 | Admin Engine | Done | Done | 26
8 | Testing Engine | Done | YTS (Module is not suite for Testing) | 0 | The execution of end-user automation tests is not proceeding as expected because of certain blockers listed in the issue tracker.
9 | Analytics Engine | Done | YTS (Module is not suite for Testing) | 0 | Currently, the Analytics Engine works only inside the app; it does not support deployment of the app with the analytics page.
10 | Secure Engine | Done | YTS (Module is not suite for Testing) | 0 | The module is currently not available on the test server URL.
11 | E-Commerce Engine | YTS | YTS (Module is not suite for Testing) | 0 | The test server currently displays the UI, but the backend features are non-functional
12 | Bpmn Process | YTS | YTS (Module is not suite for Testing) | 0 | Only the basic CRED operations are currently available on the test server URL; the corresponding BPMN process is missing or not properly implemented
| Total |  |  | 285
Reports(Functional)- The Reports page shows no E2E‑US results after applying the date filte
Precondition:
The user’s US records are present in the E2E phase for particular date
Steps to Reproduce:
1. Load the PMS web app
2. Perform login the app with valid(Admin) cred
3. Navigate to Reports module
4. Apply any valid date filter( in this date range have the US in E2E phase)
5. Check that particular available US is display in this reports list grid
Actual result:
The Reports page shows no E2E‑US results after applying the date filter, even though data is available for the selected date
Expected result:
Display all matching E2E‑US records in the table (no empty state)

## Sheet1
Title: Demo |  |  | Location: Google Meet (https://meet.google.com/peq-dzwp-pkc)
Date: 3rd March 2025 |  |  | Organizer: Stanley
Time: 6:00 PM – 7:45 PM
Attendees
Dr. Saravanan Sir, Tamizh, Stanley, Karthik, Moorthy, Lakshmanan
S.No. | Agenda | Discussed | Description | Owners
1 | Demo To Be Provided | Yes | Team provided the demo on the features planned for 3rd March.
2 | Engine Enhancements | Yes | Rules Engine: The JSON content currently generates frontend interaction code. It should also be converted into backend code using Python. Process BPMN:1. Currently, only the process header is created. Multiple process connections are needed to support specific tasks. 2. Modify access control for the Process module. Cart Engine: Transform the payment engine to include a cart section. Users should be able to add products to the cart, and payment should be treated as one of the modules.
3 | Performance | Yes | Ensure the host supports multiple users simultaneously without lag or access issues.
4 | Genreral comments | Yes | All modules/engines should be accessible to any authorized person working with the system, regardless of module ownership.
5 | Next Plan | Yes |  |  |  |  | 83
202
Title: Demo |  |  | Location: Google Meet (https://meet.google.com/peq-dzwp-pkc)
Date: 12th May 2025 |  |  | Organizer: Stanley
Time: 6:00 PM – 7:45 PM
Attendees
Dr. Saravanan Sir, Tamizh, Stanley, Karthik, Moorthy, Lakshmanan
S.No. | Agenda | Discussed | Description | Owners
1 | Demo To Be Provided | Yes | Team provided the demo on the features planned for 12th March.
2 | Engine Enhancements | Yes | Rules Engine: 1. To be change the all frontent end component should be display in rules, user can can the entire elements using rules engine becuase of all the elements code have in Rules EngineTo make changes, all frontend components should be shown through the Rules Engine, enabling users to control each element, since all the code resides within the engine. 2. The created node details should be display in Edit/ View mode also 3. The output should be displayed within the same page, and a plug-and-play output feature should also be added to that page. Process BPMN: 1. The delete and edit options must work correctly, and module access should be available in the same way as it is in the other engine. 2. To ensure the module updates automatically, it should reflect changes made in other modules and features of the app. Creation Engine: All bugs and features should be developed and resolved according to the feature checklist and the associated comments. Analtics Engine: The analytics code generation issue must be fixed prior to the upcoming demo.
| General Comments for Simplita.ai ap | Yes | 1.The team should make note of and document all challenges encountered while replicating the SG.HR wireframe and developing the app. 2. The SG.HR app was developed by the team with all 32 pages integrated into one app, replicating the structure based on the provided wireframe. 3.The existing features should be prioritized for end-to-end functionality, with comprehensive testing to verify their performance.
3 | Simplita.ai Code | Yes | 1. The functionality of our Simplita.ai code should align with the features present in the application. 2. Our Simplita.ai code must deliver a stable, error-free application. --Currently, the issue is that the AI-generated code tends to hallucinate scenarios when creating the app. 3. Simplita.ai should perform actions in the same way a human operator would, without generating new code. 4. The development of Simplita.ai should include real-time updates, with every task the AI performs reflected in the history log. The content shown during app creation should directly correspond to backend operations.
4 | Ai Agency builder | Yes | 1. The team should create an AI agent that acts as a commander, managing and directing other AIs to develop applications. This allows users to generate their own AI agent to build apps using AI. 2. A specific AI agent will be assigned the responsibility of building the application.and The key point is that the app-building agent can be created by the user. 4. By using RAG (Retrieval-Augmented Generation), we can simplify the code analysis process and significantly reduce the time it takes for the AI to understand our code.
5 | UI/UX | Yes | UI development should be initiated in parallel as the team builds the SG.HR app with Simplita. | Deepan
S.NO | Module name | Bug ID. | Description | Severity | Assigned To
1 | Authentication Engine | 620 | Login Page(Functional)- The "Forgot Password" feature is not functioning as expect | high | PeriyaSedhu
2 | Authentication Engine | 621 | Login Page(Functional)- A misleading error message appears when users enter an invalid email and attempt to sign in | high | PeriyaSedhu
3 | Authentication Engine | 622 | Login Page(Functional)- Sign-In Data Carrying Over to Sign-Up Tab: Fields in the Sign-In tab persist when navigating to Sign-Up | high | PeriyaSedhu
4 | Authentication Engine | 623 | Login Page(Functional)- Users are unable to update their existing credentials | high | PeriyaSedhu
5 | Authentication Engine | 624 | Login Page(Functional)- The Terms & Conditions pop-up does not appear when clicking the hyperlink | high | PeriyaSedhu
6 | Authentication Engine | 625 | Login Page(Functional)- Forgot Password" is displayed as a label instead of a clickable hyperlink | medium | PeriyaSedhu
7 | Authentication Engine | 626 | Login Page(Functional)- Basic Email validation error is not display in Reset Password pop up | high | PeriyaSedhu
8 | Authentication Engine | 627 | Login Page(Functional)- Unwanted page display when user click the rest password Link in received mail | high | PeriyaSedhu
9 | Authentication Engine | 628 | Login Page(Functional)- Reset Password pop up getting close when click outside the Reset Password pop-up | high | PeriyaSedhu
10 | Authentication Engine | 629 | Login Page(Functional)- Email Field Permits Invalid Special Characters, Allowing Fake or Improper Account Registration | high | PeriyaSedhu
11 | Authentication Engine | 630 | Login Page(Functional)- User try to create new account with max character missguidance error message display | high | PeriyaSedhu
12 | Authentication Engine | 631 | Login Page(Functional)- The Email ID and Password fields accept more than 500 characters, exceeding standard input limits | high | PeriyaSedhu
13 | Authentication Engine | 635 | Login Page(Functional)- The Password field allows users to save with more than 50 characters and even create an account with a 72-character password | high | PeriyaSedhu
14 | Authentication Engine | 637 | Login Page(Functional)- The proper validation error message is missing for Password field when user skip the field | high | PeriyaSedhu
15 | Authentication Engine | 638 | Login Page(Functional)- No Error Message display When click the Creating an Account button Without Email & Password | high | PeriyaSedhu
16 | Authentication Engine | 639 | Login Page(Functional)- The Reset Password email does not contain any reference to Simplita.ai, making it unclear where the email is coming from | high | PeriyaSedhu
17 | Authentication Engine | 640 | Login Page(Functional)- The error message continues to display even after entering a valid value, following an initial invalid input | medium | PeriyaSedhu
18 | Authentication Engine | 641 | Login Page(UI/UX)- Login success message is not displayed correctly | medium | PeriyaSedhu
19 | Authentication Engine | 642 | Login Page(UI/UX)- Label displayed as "Email ID" instead of "Email ID." (Dot missing in "ID.") | low | PeriyaSedhu
20 | Authentication Engine | 643 | Login Page(UI/UX)- Tooltip/help text missing for "Show Password" option | medium | PeriyaSedhu
21 | Authentication Engine | 644 | Login Page(UI/UX)- The Email ID and Password fields do not indicate they are required fields | medium | PeriyaSedhu
22 | Authentication Engine | 645 | Login Page(UI/UX)- The password suggestion error message does not disappear unless all conditions are met | medium | PeriyaSedhu
23 | Authentication Engine | 646 | Login Page(UI/UX)- The login page background does not meet design expectations. | medium | PeriyaSedhu
24 | Authentication Engine | 647 | Login Page(UI/UX)- Simplita.ai logo & company name should be display as bold but currently appear in normal text | low | PeriyaSedhu
25 | Authentication Engine | 648 | Login Page(UI/UX)- Sign-Up page is missing the Username field | low | PeriyaSedhu
26 | Authentication Engine | 649 | Login Page(UI/UX)- There is missmatch between Email ID.lable name and placeholder | low | PeriyaSedhu
27 | Authentication Engine | 650 | Login Page(UI/UX)- Duplicate Error Messages Shown for Invalid Email Entry | low | PeriyaSedhu
28 | Authentication Engine | 651 | Login Page(UI/UX)- There is an inconsistency in label names on the Sign In/Sign Up page. The email field is labeled as "Email ID," while the Reset password pop-up displays "Email Address" | medium | PeriyaSedhu
29 | Authentication Engine | 652 | Login Page(UI/UX)- Cancel button display as Label name in Reset password pop-up | medium | PeriyaSedhu
30 | Authentication Engine | 666 | Login Page(Functional)- Unable to click the "Create Account" button on the Sign-Up page, when give valid value and move the Sign up tab | critical | PeriyaSedhu
31 | Authentication Engine | 667 | Login Page(Functional)- User unable to create the new user with valid credtial | critical | PeriyaSedhu
32 | Creation Engine | 669 | Creation Engine-Canvas Editor(Functional)- Canvas Editor display the existing project details when a new project is created by the user | critical | Edwin
33 | Creation Engine | 670 | Creation Engine-Canvas Editor(Functional)- The drag and drop function fails when the user creates a new project for the first time | high | Edwin
34 | Creation Engine | 672 | Creation Engine-Canvas Editor(Functional)- The "Create app using chat" feature doesn't work when a new project is created for the first time | high | Edwin
35 | Creation Engine | 673 | Creation Engine-Canvas Editor(Functional)- Without the app layout, users cannot view the app in preview mode | high | Edwin
36 | Creation Engine | 674 | Creation Engine-Layers Tab(Functional)- The deleted menu name continues to display in another screen backend and database | high | Edwin
37 | Creation Engine | 675 | Creation Engine-Canvas Editor(Functional)- The drag and drop function is not operating smoothly | high | Edwin
38 | Creation Engine | 676 | Creation Engine-Canvas Editor(Functional)- The user cannot see small and simple words when the inline editing feature is enabled | high | Edwin
39 | Creation Engine | 677 | Creation Engine-Canvas Editor(Functional)- The resize feature does not meet current market standards | high | Edwin
40 | Creation Engine | 678 | Creation Engine-Canvas Editor(Functional)- The element drag and drop feature isn't working within the structure of the div | high | Edwin
41 | Creation Engine | 679 | Creation Engine-Canvas Editor(Functional)- The system auto-saves once an element is resized, but it doesn't complete the auto-save process before the user attempts to resize again | high | Edwin
42 | Creation Engine | 680 | Creation Engine-Canvas Editor(Functional)- Unwanted components are displayed in the Basic Elements section | high | Edwin
43 | Creation Engine | 681 | Creation Engine-Canvas Editor(Functional)- When a user adds spaces in the Heading div, unwanted and confusing content displays in the canvas. | high | Edwin
44 | Creation Engine | 682 | Creation Engine-Canvas Editor(Functional)- There is no height resize option available for any element | high | Edwin
45 | Creation Engine | 683 | Creation Engine-Right panel(Functional)- The right-side panel shows two confusing layouts section values | high | Edwin
46 | Creation Engine | 684 | Creation Engine-Canvas Editor(Functional)- By default, the font size and color do not display when the user clicks the settings button in any element | high | Edwin
47 | Creation Engine | 685 | Creation Engine-Layers Tab(Functional)- The menu create field allows more than 500 characters | high | Edwin
48 | Creation Engine | 686 | Creation Engine-Layers Tab(Functional)- The delete icon is not visible when more than 10 characters are entered in the menu create field | high | Edwin
49 | Creation Engine | 687 | Creation Engine-Layers Tab(Functional)- The delete icon does not display for a single menu available, and there is no instruction explaining why the delete icon is missing | medium | Edwin
50 | Creation Engine | 688 | Creation Engine-Layers Tab(Functional)- Unwanted layers section is displayed in the layers tab | high | Edwin
51 | Creation Engine | 689 | Creation Engine-Canvas Editor(Functional)- Three save options in the Creation Engine cause confusion for the end user | high | Edwin
52 | Creation Engine | 690 | Creation Engine-Right panel(Functional)- The unwanted validation section displays in the Creation right panel | high | Edwin
53 | Creation Engine | 691 | Creation Engine-Elements Tab(Functional)- Multiple top navigation bar elements are displayed in the Layout-Component section | medium | Edwin
54 | Creation Engine | 692 | Creation Engine-Canvas Editor(Functional)- The user is unable to create top menus or pages; only side menus or pages are available | critical | Edwin
55 | Creation Engine | 693 | Creation Engine-Canvas Editor(Functional)- The user cannot clear or delete multiple elements on one page | high | Edwin
56 | Creation Engine | 694 | Creation Engine-Canvas Editor(Functional)- The user cannot add new content or words using the container-layout elements | high | Edwin
57 | Creation Engine | 695 | Creation Engine-Canvas Editor(Functional)- The user cannot add any element after the fixed layout with the sidebar layout element section is added | high | Edwin
58 | Creation Engine | 696 | Creation Engine-Canvas Editor(Functional)- Two layout sections display when the fixed layout is added to the left panel, which creates confusion | critical | Edwin
59 | Creation Engine | 697 | Creation Engine-Canvas Editor(Functional)- The user cannot create any single element for Menu-2 after the fixed layout is added using the left panel | critical | Edwin
60 | Creation Engine | 698 | Creation Engine-Canvas Editor(Functional)- The user is unable to update the color after the layout is added | high | Edwin
61 | Creation Engine | 699 | Creation Engine-Canvas Editor(Functional)- The updated layout does not display in the canvas editor | high | Edwin
62 | Creation Engine | 700 | Creation Engine-Canvas Editor(Functional)- The user cannot delete layout content that was added using the right panel | high | Edwin
63 | Creation Engine | 701 | Creation Engine-Elements Tab(Functional)- Only basic master page related fields and elements are displayed in the elements section | high | Edwin
64 | Creation Engine | 702 | Creation Engine-Layers Tab(Functional)- When the user adds a page, there is no success message displayed | high | Edwin
65 | Creation Engine | 703 | Creation Engine-Left Panel(Functional)- There is confusion regarding the tab name in the Creation Engine left panel (1.Elements, 2.Layers, 3.Components); the basic logic for the tab name is missing | high | Edwin
66 | Creation Engine | 704 | Creation Engine-Canvas Editor(Functional)- Deleted pages or menus still display in the Canvas Editor section | high | Edwin
67 | Creation Engine | 705 | Creation Engine-Canvas Editor(Functional)- There is no option to revert the applied Layout-Right panel | high | Edwin
68 | Creation Engine | 706 | Creation Engine-Canvas Editor(Functional)- The user is unable to resize or maximize the already minimized field | high | Edwin
69 | Creation Engine | 707 | Creation Engine-Canvas Editor(Functional)- The user cannot add new pages or menus as the top menu | high | Edwin
70 | Creation Engine | 708 | Creation Engine-Canvas Editor(Functional)- There is no toast message displayed when a page is deleted | high | Edwin
71 | Creation Engine | 709 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the logo in the | high | Edwin
72 | Creation Engine | 710 | Creation Engine-Canvas Editor(Functional)- The user cannot edit the progress bar or table element in the Canvas Editor | high | Edwin
73 | Creation Engine | 711 | Creation Engine-Layer Tab(Functional)- The updated menu/page value is not displayed in the Layers section-left panel. | high | Edwin
74 | Creation Engine | 712 | Creation Engine-Elements Tab(Functional)- There is confusion between the Basic Elements and Form sections in the Element tab-left panel. | high | Edwin
75 | Creation Engine | 713 | Creation Engine-Canvas Editor(Functional)- The user is unable to add elements in the second tab (Tabbar components) of the Canvas Editor | high | Edwin
76 | Creation Engine | 714 | Creation Engine-Canvas Editor(Functional)- The dashboard button is displayed as clicked, but the user cannot change the view mode after adding the Layout-Right panel. | medium | Edwin
77 | Creation Engine | 715 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the page/menu background color in the canvas editor | high | Edwin
78 | Creation Engine | 716 | Creation Engine-Canvas Editor(Functional)- Resizing does not work in the page/menu within the canvas editor | high | Edwin
79 | Creation Engine | 717 | Creation Engine-Canvas Editor(Functional)- The user is unable to view the entire element after adding multiple templates in the canvas editor | high | Edwin
80 | Creation Engine | 718 | Creation Engine-Canvas Editor(Functional)- The Save & Load section is don't want available in the right-side panel | high | Edwin
81 | Creation Engine | 719 | Creation Engine-Right Panel(Functional)- The user can link any available page/menu to any field or element | high | Edwin
82 | Creation Engine | 720 | Creation Engine-Components Tab(Functional)- Unable to save the New component in Components tab | high | Edwin
83 | Creation Engine | 721 | Creation Engine-Components Tab(Functional)- In the Preview section, display the Code also along with element UI (Create the Circle Loader) | critical | Edwin
84 | Creation Engine | 722 | Creation Engine-Components Tab(Functional)- Some of the element not create the by AI(Createthe 10 sort icon) | high | Edwin
85 | Creation Engine | 723 | Creation Engine-Components Tab(Functional)- Unable to perform paste the values in Ai chat field | medium | Edwin
86 | Creation Engine | 724 | Creation Engine-Components Tab(Functional)- Create New Components pop up getting close when click away from the pop up | medium | Edwin
87 | Creation Engine | 725 | Creation Engine-Components Tab(Functional)- When user send the message as hi then chat field display the Hi related elememnt code | medium | Edwin
88 | Creation Engine | 726 | Creation Engine-Components Tab(Functional)- The pop up getting close when user click the get help dropdown | high | Edwin
89 | Creation Engine | 727 | Creation Engine-Components Tab(Functional)- Updated existing components is not display the updated code | medium | Edwin
90 | Creation Engine | 728 | Creation Engine-Components Tab(Functional)- Two different pop up display for Component create and Edit, user can getting confuse a lot of edit the component for existing elemet and create the component using ai | high | Edwin
91 | Creation Engine | 729 | Creation Engine-Components Tab(Functional)- Image Element preview is display with error | high | Edwin
92 | Creation Engine | 747 | Creation Engine-Right panel(Functional)- Drag-and-drop functionality in the Image Library Right Panel is not working | high | Edwin
93 | Creation Engine | 748 | Creation Engine-Right panel(Functional)- No success message is displayed after deleting an uploaded image in the Image Library Right Panel | medium | Edwin
94 | Creation Engine | 749 | Creation Engine-Right panel(Functional)- A user can upload files larger than 10 MB | high | Edwin
95 | Creation Engine | 750 | Creation Engine-Right panel(Functional)- The system does not present the correct error message when uploading a <> JSON file | high | Edwin
96 | Creation Engine | 751 | Creation Engine-Right panel(Functional)- Edit element Basic Styles are not functioning properly | high | Edwin
97 | Creation Engine | 752 | Creation Engine-Right panel(Functional)- An unwanted Export Canvas section is shown in the Right Panel | high | Edwin
98 | Creation Engine | 753 | Creation Engine-Layers Tab(UI/UX)- The Layers Tab appears second, but the system does not clearly explain why it is unable to drag and drop components | medium | Edwin
99 | Creation Engine | 754 | Creation Engine-Layers Tab(UI/UX)- No message is shown prompting the user to create Pages/menus first before add the elements | medium | Edwin
100 | Creation Engine | 755 | Creation Engine-Canvas Editor(UI/UX)- When resizing large word content, it collapses, causing display issues. | medium | Edwin
101 | Creation Engine | 756 | Creation Engine-Canvas Editor(UI/UX)- The H1-heading appears as a pixelated label name | medium | Edwin
102 | Creation Engine | 757 | Creation Engine-Canvas Editor(UI/UX)- The system fails to display H2, H3, and other elements | medium | Edwin
103 | Creation Engine | 758 | Creation Engine-Canvas Editor(UI/UX)- The element category appears confusing, requiring users to rearrange both the element and its name | medium | Edwin
104 | Creation Engine | 759 | Creation Engine-Canvas Editor(UI/UX)- Unwanted Image Elements are visible in the Basic Elements section | medium | Edwin
105 | Creation Engine | 760 | Creation Engine-Canvas Editor(UI/UX)- The Close/Clear icon is visible in the Layout Components section-right panel, but the section can only be accessed once the user clears it | low | Edwin
106 | Creation Engine | 761 | Creation Engine-Canvas Editor(UI/UX)- Two instances of the name "Simplita" are shown in the Creation Engine | medium | Edwin
107 | Creation Engine | 762 | Creation Engine-Canvas Editor(UI/UX)- The unwanted Layers section is visible in the Layers tab | high | Edwin
108 | Creation Engine | 763 | Creation Engine-Canvas Editor(UI/UX)- No tooltips or help tips are available for any icons | medium | Edwin
109 | Creation Engine | 764 | Creation Engine-Canvas Editor(UI/UX)- The "Two columns" element does not display correctly in the Canvas editor | medium | Edwin
110 | Creation Engine | 765 | Creation Engine-Canvas Editor(UI/UX)- Unwanted double quotes appear when adding any element to the canvas editor | medium | Edwin
111 | Creation Engine | 766 | Creation Engine-Canvas Editor(UI/UX)- An unnecessary icon is displayed next to the Undo & Redo buttons in the header | medium | Edwin
112 | Creation Engine | 767 | Creation Engine-Canvas Editor(UI/UX)- An unwanted navigation label appears after adding the Layout-Right panel | low | Edwin
113 | Creation Engine | 768 | Creation Engine-Canvas Editor(UI/UX)- An empty circle appears before the Sign-In button after adding the Layout-Right panel | medium | Edwin
114 | Creation Engine | 769 | Creation Engine-Canvas Editor(UI/UX)- The top menu is displayed in the middle of the page after adding the Layout-Right panel | medium | Edwin
115 | Creation Engine | 770 | Creation Engine-Canvas Editor(UI/UX)- When dragging and dropping a button element in the Canvas editor, the button appears as a normal label | medium | Edwin
116 | Creation Engine | 771 | Creation Engine-Canvas Editor(UI/UX)- The button element appears in two sections in the Components section on the left panel | medium | Edwin
117 | Creation Engine | 772 | Creation Engine-Canvas Editor(UI/UX)- By default, all page/menu checkboxes are selected after clicking "Apply Layout," but the "Select All" checkbox appears unselected. | medium | Edwin
118 | Creation Engine | 773 | Creation Engine-Component Tab(UI/UX)- Ai Assistant feature is displayed as a regular label name | medium | Edwin
119 | Creation Engine | 774 | Creation Engine-Component Tab(UI/UX)- No error message appears when the user leaves the Component name field empty in the Components tab | medium | Edwin
120 | Creation Engine | 775 | Creation Engine-Component Tab(UI/UX)- The header displays as "Component HTML*" but AI also generates other technologies | low | Edwin
121 | Creation Engine | 776 | Creation Engine-Component Tab(UI/UX)- The tool/help tip for the Close icon in the Create New Component's popup is not visible | low | Edwin
122 | Creation Engine | 777 | Creation Engine-Component Tab(UI/UX)- The field is labeled as Components Name, but should be labeled as Elements Name | medium | Edwin
123 | Creation Engine | 778 | Creation Engine-Component Tab(UI/UX)- The chat field icon is missing in existing element pop up | medium | Edwin
124 | Creation Engine | 779 | Creation Engine-Component Tab(UI/UX)- The element edit popup does not show the correct title | medium | Edwin
125 | Creation Engine | 780 | Creation Engine-Component Tab(UI/UX)- The Click me button code is displayed as a label name | medium | Edwin
126 | Creation Engine | 781 | Creation Engine-Component Tab(UI/UX)- The multiselect dropdown does not show any values | medium | Edwin
127 | Creation Engine | 782 | Creation Engine-Component Tab(UI/UX)- Multiple sidebar navigation options are displayed in the Navigation Section | medium | Edwin
128 | Creation Engine | 783 | Creation Engine-Header(UI/UX)- The menu/page dropdown collapse under the dashboard layout header, partially hiding its values | medium | Edwin
129 | Creation Engine | 793 | Creation Engine-Right panel(UI/UX)- All section features are open by default (plus symbol enabled), and only the section header is shown by default | medium | Edwin
130 | Creation Engine | 796 | Creation Engine-Right Tab(UI/UX)- The Layout Components section header appears in a distinct color | low | Edwin
131 | Creation Engine | 730 | Creation Engine-Theme Tab(Functional)- Cancel applied theme function is not available for Theme tab | high | PeriyaSedhu
132 | Creation Engine | 731 | Creation Engine-Theme Tab(Functional)- AI generate the Christmas's theme, but there is any properer user expect output is not receive | high | PeriyaSedhu
133 | Creation Engine | 732 | Creation Engine-Theme Tab(Functional)- The secondary colour is not apply in the canvas editor page | high | PeriyaSedhu
134 | Creation Engine | 733 | Creation Engine-Theme Tab(Functional)- User unable to delete the cretaed Theme | high | PeriyaSedhu
135 | Creation Engine | 734 | Creation Engine-Theme Tab(Functional)- There is no success message display when user creates the new theme | high | PeriyaSedhu
136 | Creation Engine | 735 | Creation Engine-Theme Tab(Functional)- User unable to delete the cretaed Theme | high | PeriyaSedhu
137 | Creation Engine | 736 | Creation Engine-Theme Tab(Functional)- Fonts edit features is not working | high | PeriyaSedhu
138 | Creation Engine | 737 | Creation Engine-Theme Tab(Functional)- Unable to change the text colour | high | PeriyaSedhu
139 | Creation Engine | 738 | Creation Engine-Theme Tab(Functional)- System not display the updated success message when update the theme | high | PeriyaSedhu
140 | Creation Engine | 739 | Creation Engine-Theme Tab(Functional)- Added theme color is not reflected the middle of the page, it hs refelect only in the side bar | high | PeriyaSedhu
141 | Creation Engine | 740 | Creation Engine-Theme Tab(Functional)- The background theme is not reflect which is work for only Dashboard layout is applied | critical | PeriyaSedhu
142 | Creation Engine | 741 | Creation Engine-Theme Tab(Functional)- User unable toadd the theme based on the menu/page, the theme going to add all menu/page, even which menu not include with layout | high | PeriyaSedhu
143 | Creation Engine | 742 | Creation Engine-Theme Tab(Functional)- Theme is not override when user add the new along with existing colour for any field/element | high | PeriyaSedhu
144 | Creation Engine | 743 | Creation Engine-Theme Tab(Functional)- User unable to add the Ai created Theme | critical | PeriyaSedhu
145 | Creation Engine | 744 | Creation Engine-Theme Tab(Functional)- System not allow to upload 1 mb file | high | PeriyaSedhu
146 | Creation Engine | 745 | Creation Engine-Theme Tab(Functional)- System not display proper error message when user upload <> JSON file | high | PeriyaSedhu
147 | Creation Engine | 746 | Creation Engine-Theme Tab(Functional)- In that available Edit Theme panel the Background colour only update the app, other that no feature is not working | high | PeriyaSedhu
148 | Creation Engine | 784 | Creation Engine-Theme Tab(UI/UX)- The Theme tab is not readily accessible to end users and does not appear by default | low | PeriyaSedhu
149 | Creation Engine | 785 | Creation Engine-Theme Tab(UI/UX)- Some themes do not display their name/title | medium | PeriyaSedhu
150 | Creation Engine | 786 | Creation Engine-Theme Tab(UI/UX)- The top navbar theme not getting change when a new theme is added | medium | PeriyaSedhu
151 | Creation Engine | 788 | Creation Engine-Theme Tab(UI/UX)- The tool/help tip is not visible in the Theme tab | low | PeriyaSedhu
152 | Creation Engine | 790 | Creation Engine-Theme Tab(UI/UX)- There is a mismatch between the theme name and its color in the Theme tab, showing "Light" but rendering black | medium | PeriyaSedhu
153 | Internal Preview | 857 | Internal Preview(Functional)- Without add the Layout the created app is not display in the Internal Preview page | critical | Vinoth
154 | Internal Preview | 858 | Internal Preview(UI/UX)- The Menu name is not display as Internal Preview | high | Vinoth
155 | Internal Preview | 859 | Internal Preview(Functional)- Deleted Menu/Pages display in Internal Preview page | high | Vinoth
156 | Internal Preview | 860 | Internal Preview(Functional)- Created login page also display as menu in Internal preview | high | Vinoth
157 | Internal Preview | 861 | Internal Preview(Functional)- Duplicate Progress bar display in Internal Preview page | high | Vinoth
158 | Internal Preview | 862 | Internal Preview(Functional)- System not display the Added search box, Filter is not display in Internal Preview page | high | Vinoth
159 | Internal Preview | 863 | Internal Preview(Functional)- First displayed menu based page content not display when navigate to Internal Preview page | high | Vinoth
160 | Internal Preview | 864 | Internal Preview(Functional)- User can save the components for multiple time, system not display any information message for this issue | medium | Vinoth
161 | Internal Preview | 865 | Internal Preview(UI/UX)- There is no Tool/Help tip is not display in the Internal Preview page | medium | Vinoth
162 | Internal Preview | 866 | Internal Preview(UI/UX)- Page Header is not display in the Internal Preview page | high | Vinoth
163 | Internal Preview | 867 | Internal Preview(UI/UX)- Dual error message display in Internal Preview page when the validation added for the field | high | Vinoth
164 | Internal Preview | 868 | Internal Preview(UI/UX)- User unable to click the First check box in Tab bar section | medium | Vinoth
165 | Internal Preview | 869 | Internal Preview(UI/UX)- The menu item on the dashboard is selected, yet no corresponding components are shown | medium | Vinoth
166 | DB Engine | 971 | DB Engine(Functional)- When user click the Remove table icon then system display the error message | high | saravana
167 | DB Engine | 975 | DB Engine(Functional)- The DB engine generate the multiple column for single element radio button | high | saravana
168 | DB Engine | 978 | DB Engine(Functional)- Multiple tables are not generated by the multi-tab field; only one combined table is produced | high | saravana
169 | DB Engine | 979 | DB Engine(Functional)- Inconsistent field names in AI-generated columns may confuse end users; align them clearly | high | saravana
170 | DB Engine | 981 | DB Engine(Functional)- There is no confirmation message when user click the remove column | medium | saravana
171 | DB Engine | 982 | DB Engine(Functional)- Unable to update the table name at the single stretch | medium | saravana
172 | DB Engine | 983 | DB Engine(Functional)- The 'Set a Foreign Key' feature includes the current table as a selectable option, which isn't useful | high | saravana
173 | DB Engine | 984 | DB Engine(Functional)- User unable to update the column data types | high | saravana
174 | DB Engine | 985 | DB Engine(Functional)- User can create the column with 500 characters | high | saravana
175 | DB Engine | 986 | DB Engine(Functional)- Given column name value not getting clear when user click the add new button | medium | saravana
176 | DB Engine | 987 | DB Engine(Functional)- System not display any success message when ai generate the schema | medium | saravana
177 | DB Engine | 988 | DB Engine(Functional)- Given data type value not getting clear when user click the add new button | medium | saravana
178 | DB Engine | 989 | DB Engine(UI/UX)- Export Schema and Json viewer button name display partially | low | saravana
179 | DB Engine | 990 | DB Engine(Functional)- Column name required message not display in below the column name field | medium | saravana
180 | DB Engine | 991 | DB Engine(Functional)- User can delete the primary key column | high | saravana
181 | DB Engine | 992 | DB Engine(Functional)- System display the error message when click the any option in Export schema button without save the schema | high | saravana
182 | DB Engine | 993 | DB Engine(Functional)- System throw the error message when click the Add new table button without add the ai generate schema | critical | saravana
183 | DB Engine | 994 | DB Engine(Functional)- Ai getting generate schema for the deleted page also | critical | saravana
184 | DB Engine | 995 | DB Engine(Functional)- System allow to set the multiple primary key for single table | high | saravana
185 | DB Engine | 996 | DB Engine(Functional)- Multiple column delete getting delete while delete the single column | high | saravana
186 | DB Engine | 997 | DB Engine(Functional)- The system does not allow assigning both a primary key and a foreign key to the same column | high | saravana
187 | DB Engine | 998 | DB Engine(Functional)- System unable to create the new column in Tables section | high | saravana
188 | DB Engine | 999 | DB Engine(UI/UX)- Save column button display as lable name it is not display as button | medium | saravana
189 | DB Engine | 1000 | DB Engine(Functional)- Column name display as undefined when update the data type for primary key column | high | saravana
190 | DB Engine | 1001 | DB Engine(Functional)- Not able to select the check box for new column add section | high | saravana
191 | DB Engine | 1002 | DB Engine(Functional)- Delete success message is not display when user delete the column | high | saravana
192 | DB Engine | 1005 | DB Engine(Functional)- When a column is changed from 'Not Required' to 'Required' in the edit section, any previously available data in that column gets removed and the column vanishes | high | saravana
193 | DB Engine | 1006 | DB Engine(Functional)- Export Schema file display unwanted dummy value when user click the button | high | saravana
194 | DB Engine | 1007 | DB Engine(Functional)- Api Generator display exiting api when user delete the existing table | high | saravana
195 | DB Engine | 1008 | DB Engine(Functional)- Read, Write and Delete feature is not working in Credentials tab-API Generator | high | saravana
196 | DB Engine | 1010 | DB Engine(UI/UX)- Mismatch module name display for Database Engine | medium | saravana
197 | DB Engine | 1012 | DB Engine(Functional)- Unwanted Back to Top icon display and also it have hide the other needed button also | medium | saravana
198 | DB Engine | 1013 | DB Engine(Functional)- Duplicate Close icon display in Schema Change Analysis pop up | medium | saravana
199 | DB Engine | 1014 | DB Engine(UI/UX)- Unwanted Will Add icon display in Schema Change Analysis pop up | medium | saravana
200 | DB Engine | 1015 | DB Engine(Functional)- The Schema Change Analysis pop up getting close when user click the away from the pop up | medium | saravana
201 | DB Engine | 1017 | DB Engine(Functional)- Created schema not display in table section, it have display only the user click the refresh icon in browser | high | saravana
202 | DB Engine | 1018 | DB Engine(Functional)- Er Diagram created relation ship mapping not reflect in Table page | high | saravana
203 | DB Engine | 1019 | DB Engine(Functional)- Chat section is not create any kind of feature | high | saravana
204 | DB Engine | 1020 | DB Engine(Functional)- Created relation ship mapping not getting auto save, there is no any save button available for ER Diagram page | high | saravana
205 | DB Engine | 1021 | Migration Engine(Functional)- The system allow only to upload the .sql type file | high | saravana
206 | DB Engine | 1022 | Migration Engine(Functional)- System allow to upload than more 50 mb file | medium | saravana
207 | Rules Engine | 915 | Rules Engine(Functional)- The Success message is not display when user add the Condition and Calculation | medium | Edwin
208 | Rules Engine | 916 | Rules Engine(Functional)- User unable to see the existing added Condition and Calculation | high | Edwin
209 | Rules Engine | 917 | Rules Engine(Functional)- User unable to add the Condition and Calculation for the app without click the middle panel element | high | Edwin
210 | Rules Engine | 918 | Rules Engine(Functional)- User can delete the middle panel element using Keyboard shortcut | critical | Edwin
211 | Rules Engine | 919 | Rules Engine(Functional)- The Right panel dropdown display only the All Form value | medium | Edwin
212 | Rules Engine | 920 | Rules Engine(Functional)- "Field value" condition feature is not working fine | high | Edwin
213 | Rules Engine | 921 | Rules Engine(Functional)- Deleted success message is not display when delete the Conditions/Calculation | medium | Edwin
214 | Rules Engine | 922 | Rules Engine(Functional)- User can edit the any Label name and alos the page/menu name | high | Edwin
215 | Rules Engine | 923 | Rules Engine(Functional)- Unwanted field value condition is display in condition added function | high | Edwin
216 | Rules Engine | 924 | Rules Engine(Functional)-The same creation engine top header display in Rules, there is no purpose for the header in Rules engine | high | Edwin
217 | Rules Engine | 925 | Rules Engine(Functional)- User unable to add Conditions and Calculations in rules engine when click the any div(Header &Menu) <> label name or field | critical | Edwin
218 | Rules Engine | 926 | Rules Engine(Functional)- The radio button validation is not display in Validation menu | high | Edwin
219 | Rules Engine | 927 | Rules Engine(Functional)- Test validation display field display as text field for dropdown | high | Edwin
220 | Rules Engine | 928 | Rules Engine(Functional)- Number only allowed validation is missing in Validation section | high | Edwin
221 | Rules Engine | 929 | Rules Engine(Functional)- Dropdown field validation is not up to the standard | high | Edwin
222 | Rules Engine | 930 | Rules Engine(Functional)- By default some of the basic validation is not be display when user click the element | medium | Edwin
223 | Rules Engine | 931 | Rules Engine(Functional)- The password field validation is still being displayed in the Rules Engine, even after the field—originally created as a password type—is updated and renamed to “XYZ.” | high | Edwin
224 | Rules Engine | 932 | Rules Engine(Functional)- System not display the vaidation field section when user click the field div in middle panel | high | Edwin
225 | Rules Engine | 933 | Rules Engine(Functional)- System not display the vaidation field section when user click the field div in middle panel | high | Edwin
226 | Rules Engine | 934 | Rules Engine(Functional)- Action field display as empty when user select maths calculation in Condition Type | high | Edwin
227 | Rules Engine | 935 | Rules Engine(Functional)- The Success message is not display when user add the validation | high | Edwin
228 | Rules Engine | 936 | Rules Engine(Functional)- The Success message is not display when user add the Automation workflow | high | Edwin
229 | Rules Engine | 937 | Rules Engine(Functional)- The condition node is not in the working status, the node display any others fields | critical | Edwin
230 | Rules Engine | 938 | Rules Engine(Functional)- System not display the Maths calculation and Automated received Mail | high | Edwin
231 | Rules Engine | 939 | Rules Engine(Functional)- There is no option to validate the config mail is wright or not | high | Edwin
232 | Rules Engine | 940 | Rules Engine(Functional)- User can Run the Automatin flow without create the Scenario | high | Edwin
233 | Rules Engine | 941 | Rules Engine(Functional)- The Automatin workflow only display the Email only, basicly we need to display the 4 to 5 node | high | Edwin
234 | Rules Engine | 942 | Rules Engine(Functional)- Maths operation node is not display any field | high | Edwin
235 | Rules Engine | 943 | Rules Engine(UI/UX)- Two button display for create the conditions and Calculations but the feature added in single section | medium | Edwin
236 | Rules Engine | 944 | Rules Engine(UI/UX)- Confused Test validation field available in Validation Section | high | Edwin
237 | Rules Engine | 945 | Rules Engine(UI/UX)- User unable to change the date field format | medium | Edwin
238 | Rules Engine | 946 | Rules Engine(UI/UX)- The password label and its input type are displayed as collapsed in the interface | medium | Edwin
239 | Rules Engine | 947 | Rules Engine(UI/UX)- The max characters field should only accept numeric values, but it currently allows only the letter "e," which seems to be a validation issue | medium | Edwin
240 | Rules Engine | 948 | Rules Engine(UI/UX)- The summarize text label display partially in condition section | low | Edwin
241 | Rules Engine | 949 | Rules Engine(UI/UX)- The Scenario workflow is not start easily access for non-tech user | medium | Edwin
242 | Rules Engine | 950 | Rules Engine(UI/UX)- Unwanted Setting option is display in middle panel when user click the element | high | Edwin
243 | Deployment Engine | 1045 | Deployment Engine(Functional)- The deployed app is only displaying the form page; the rest of the application is not visible | critical | Sai
244 | Deployment Engine | 1046 | Deployment Engine(Functional)- Exported data is currently missing from the Docker Exports section | high | Sai
245 | Deployment Engine | 1047 | Deployment Engine(Functional)- The app cannot be deployed without saving the component, and the system shows a confusing error message | high | Sai
246 | Deployment Engine | 1048 | Deployment Engine(UI/UX)- The Deployment Engine menu is not easily accessible | medium | Sai
247 | Deployment Engine | 1049 | Deployment Engine(UI/UX)- Deployment header name is not display when navigate the page | medium | Sai
248 | Deployment Engine | 1050 | Deployment Engine(Functional)- The application deployed is showing intermittent blinking behavior without a consistent pattern | high | Sai
249 | Deployment Engine | 1051 | Deployment Engine(Functional)- The system displays a "Failed with code" error message when using an app apart from any combined template | high | Sai
250 | Deployment Engine | 1052 | Deployment Engine(Functional)- The deployed app is only displaying the form page; the rest of the application is not visible | high | Sai
251 | Deployment Engine | 1053 | Deployment Engine(Functional)- The "Build App" button remains active and clickable repeatedly, despite no modifications being made to the app | high | Sai
252 | Deployment Engine | 1054 | Deployment Engine(Functional)- The system displays an error message during the app build process, but it doesn’t provide a clear reason for the failure | high | Sai
253 | Deployment Engine | 1055 | Deployment Engine(Functional)- User unable to move any page in deployed app | high | Sai
254 | Deployment Engine | 1056 | Deployment Engine(UI/UX)- There are no tooltips/helptips displayed anywhere on the page | medium | Sai
255 | Deployment Engine | 1057 | Deployment Engine(UI/UX)- Avg. Duration not display value in Deployment History pop up | high | Sai
256 | Deployment Engine | 1058 | Deployment Engine(UI/UX)- Success Rate display mismatch value in Deployment History pop up | medium | Sai
257 | Deployment Engine | 1059 | Deployment Engine(UI/UX)- Version column display same value display for multiple row values | medium | Sai
258 | Deployment Engine | 1060 | Deployment Engine(UI/UX)- Duration & Actions not display value in Deployment History pop up | medium | Sai
259 | Deployment Engine | 1061 | Deployment Engine(UI/UX)- Currently I have deploy only one app but there is 2 values display in Deployment History pop up | medium | Sai
260 | Admin Engine | 1108 | Admin Engine(UI/UX)- The Admin Mode is not easily discoverable for non-technical users in deployed app | medium | sai
261 | Admin Engine | 1109 | Admin Engine(UI/UX)- Unwanted "Main Menu" label display in the header | low | sai
262 | Admin Engine | 1110 | Admin Engine(UI/UX)- The Button name display as list grid header in dashboard | medium | sai
263 | Admin Engine | 1111 | Admin Engine(UI/UX)- Any of the chart or list grid is not display in the Dashboard | medium | sai
264 | Admin Engine | 1112 | Admin Engine(Functional)- The Edit Role Hierarchy feature is not working | high | sai
265 | Admin Engine | 1113 | Admin Engine(Functional)- The Username field allow more than 500 charaters | medium | sai
266 | Admin Engine | 1114 | Admin Engine(Functional)- The proper Email validation is not display in the Users create page | high | sai
267 | Admin Engine | 1115 | Admin Engine(Functional)- The common validation required validation is not display in any of the master page | medium | sai
268 | Admin Engine | 1116 | Admin Engine(Functional)- The Roles field fails to display as a dropdown when the total role values exceed 50 entries. | high | sai
269 | Admin Engine | 1117 | Admin Engine(UI/UX)- Superuser field is not display as one of the Create User field | medium | sai
270 | Admin Engine | 1118 | Admin Engine(Functional)- Password show icon is not display in create User page | medium | sai
271 | Admin Engine | 1119 | Admin Engine(Functional)- Data Export option is not available for any of the master list grid | high | sai
272 | Admin Engine | 1120 | Admin Engine(Functional)- The proper error message is not display in edit user pop up | medium | sai
273 | Admin Engine | 1121 | Admin Engine(UI/UX)- The Column header alignment display improperly when change the Showing count dropdown values | medium | sai
274 | Admin Engine | 1122 | Admin Engine(UI/UX)- Unwanted url content display in delete confirmation pop-up | medium | sai
275 | Admin Engine | 1123 | Admin Engine(Functional)- Success message is display when user click the Save changes button without add any changes | medium | sai
276 | Admin Engine | 1124 | Admin Engine(Functional)- Grid is not displaying any records (UI shows empty), but bulk delete still deletes all records | medium | sai
277 | Admin Engine | 1125 | Admin Engine(Functional)- The search bar displays as an unusually lengthy field. It should have a standard width aligned with other UI elements | medium | sai
278 | Admin Engine | 1126 | Admin Engine(Functional)- The Admin Engine User module is visible for access, but the login page is not loading or available in the deployed application | high | sai
279 | Admin Engine | 1127 | Admin Engine(Functional)- Pagination showing count display feature is not display in Roles master page | high | sai
280 | Admin Engine | 1128 | Admin Engine(Functional)- All check box getting select only when click the View only check box | medium | sai
281 | Admin Engine | 1129 | Admin Engine(Functional)- System display the error message when delete the roles record | high | sai
282 | Admin Engine | 1130 | Admin Engine(Functional)- Test connection feature is not working | high | sai
283 | Admin Engine | 1131 | Admin Engine(Functional)- Users are able to set an inactive integration record as the default | high | sai
284 | Admin Engine | 1132 | Admin Engine(Functional)- Users are able to assign the 'Default' status to multiple integration records | high | sai
285 | Admin Engine | 1133 | Admin Engine(Functional)- The sort feature is not available for any master page | high | sai
S.NO | Module name | Bug ID. | Description | Severity | Posible for bug fix | Status
1 | Authentication Engine | 641 | Login Page(UI/UX)- Login success message is not displayed correctly | medium | Yes | Done
2 | Authentication Engine | 642 | Login Page(UI/UX)- Label displayed as "Email ID" instead of "Email ID." (Dot missing in "ID.") | low | Yes | Done
3 | Authentication Engine | 643 | Login Page(UI/UX)- Tooltip/help text missing for "Show Password" option | medium | Yes | Done
4 | Authentication Engine | 644 | Login Page(UI/UX)- The Email ID and Password fields do not indicate they are required fields | medium | Yes | Done
5 | Authentication Engine | 645 | Login Page(UI/UX)- The password suggestion error message does not disappear unless all conditions are met | medium | Yes | Done
6 | Authentication Engine | 646 | Login Page(UI/UX)- The login page background does not meet design expectations. | medium | Yes | Done
7 | Authentication Engine | 647 | Login Page(UI/UX)- Simplita.ai logo & company name should be display as bold but currently appear in normal text | low | Yes | Done
8 | Authentication Engine | 648 | Login Page(UI/UX)- Sign-Up page is missing the Username field | low | Yes | Done
9 | Authentication Engine | 649 | Login Page(UI/UX)- There is missmatch between Email ID.lable name and placeholder | low | Yes | Done
10 | Authentication Engine | 650 | Login Page(UI/UX)- Duplicate Error Messages Shown for Invalid Email Entry | low | Yes | Done
11 | Authentication Engine | 651 | Login Page(UI/UX)- There is an inconsistency in label names on the Sign In/Sign Up page. The email field is labeled as "Email ID," while the Reset password pop-up displays "Email Address" | medium | Yes | Done
12 | Authentication Engine | 652 | Login Page(UI/UX)- Cancel button display as Label name in Reset password pop-up | medium | Yes | Done
13 | Creation Engine | 753 | Creation Engine-Layers Tab(UI/UX)- The Layers Tab appears second, but the system does not clearly explain why it is unable to drag and drop components | medium | No
14 | Creation Engine | 754 | Creation Engine-Layers Tab(UI/UX)- No message is shown prompting the user to create Pages/menus first before add the elements | medium | No
15 | Creation Engine | 755 | Creation Engine-Canvas Editor(UI/UX)- When resizing large word content, it collapses, causing display issues. | medium | No
16 | Creation Engine | 756 | Creation Engine-Canvas Editor(UI/UX)- The H1-heading appears as a pixelated label name | medium | No
17 | Creation Engine | 757 | Creation Engine-Canvas Editor(UI/UX)- The system fails to display H2, H3, and other elements | medium | No
18 | Creation Engine | 758 | Creation Engine-Canvas Editor(UI/UX)- The element category appears confusing, requiring users to rearrange both the element and its name | medium | No
19 | Creation Engine | 759 | Creation Engine-Canvas Editor(UI/UX)- Unwanted Image Elements are visible in the Basic Elements section | medium | No
20 | Creation Engine | 760 | Creation Engine-Canvas Editor(UI/UX)- The Close/Clear icon is visible in the Layout Components section-right panel, but the section can only be accessed once the user clears it | low | Yes
21 | Creation Engine | 761 | Creation Engine-Canvas Editor(UI/UX)- Two instances of the name "Simplita" are shown in the Creation Engine | medium | Yes
22 | Creation Engine | 762 | Creation Engine-Canvas Editor(UI/UX)- The unwanted Layers section is visible in the Layers tab | high | Yes
23 | Creation Engine | 763 | Creation Engine-Canvas Editor(UI/UX)- No tooltips or help tips are available for any icons | medium | Yes
24 | Creation Engine | 764 | Creation Engine-Canvas Editor(UI/UX)- The "Two columns" element does not display correctly in the Canvas editor | medium | No
25 | Creation Engine | 765 | Creation Engine-Canvas Editor(UI/UX)- Unwanted double quotes appear when adding any element to the canvas editor | medium | No
26 | Creation Engine | 766 | Creation Engine-Canvas Editor(UI/UX)- An unnecessary icon is displayed next to the Undo & Redo buttons in the header | medium | No
27 | Creation Engine | 767 | Creation Engine-Canvas Editor(UI/UX)- An unwanted navigation label appears after adding the Layout-Right panel | low | No
28 | Creation Engine | 768 | Creation Engine-Canvas Editor(UI/UX)- An empty circle appears before the Sign-In button after adding the Layout-Right panel | medium | No
29 | Creation Engine | 769 | Creation Engine-Canvas Editor(UI/UX)- The top menu is displayed in the middle of the page after adding the Layout-Right panel | medium | No
30 | Creation Engine | 770 | Creation Engine-Canvas Editor(UI/UX)- When dragging and dropping a button element in the Canvas editor, the button appears as a normal label | medium | No
31 | Creation Engine | 771 | Creation Engine-Canvas Editor(UI/UX)- The button element appears in two sections in the Components section on the left panel | medium | No
32 | Creation Engine | 772 | Creation Engine-Canvas Editor(UI/UX)- By default, all page/menu checkboxes are selected after clicking "Apply Layout," but the "Select All" checkbox appears unselected. | medium | Yes
33 | Creation Engine | 773 | Creation Engine-Component Tab(UI/UX)- Ai Assistant feature is displayed as a regular label name | medium | No
34 | Creation Engine | 774 | Creation Engine-Component Tab(UI/UX)- No error message appears when the user leaves the Component name field empty in the Components tab | medium | No
35 | Creation Engine | 775 | Creation Engine-Component Tab(UI/UX)- The header displays as "Component HTML*" but AI also generates other technologies | low | No
36 | Creation Engine | 776 | Creation Engine-Component Tab(UI/UX)- The tool/help tip for the Close icon in the Create New Component's popup is not visible | low | Yes
37 | Creation Engine | 777 | Creation Engine-Component Tab(UI/UX)- The field is labeled as Components Name, but should be labeled as Elements Name | medium | Yes
38 | Creation Engine | 778 | Creation Engine-Component Tab(UI/UX)- The chat field icon is missing in existing element pop up | medium | No
39 | Creation Engine | 779 | Creation Engine-Component Tab(UI/UX)- The element edit popup does not show the correct title | medium | No
40 | Creation Engine | 780 | Creation Engine-Component Tab(UI/UX)- The Click me button code is displayed as a label name | medium | No
41 | Creation Engine | 781 | Creation Engine-Component Tab(UI/UX)- The multiselect dropdown does not show any values | medium | Yes
42 | Creation Engine | 782 | Creation Engine-Component Tab(UI/UX)- Multiple sidebar navigation options are displayed in the Navigation Section | medium | No
43 | Creation Engine | 783 | Creation Engine-Header(UI/UX)- The menu/page dropdown collapse under the dashboard layout header, partially hiding its values | medium | No
44 | Creation Engine | 793 | Creation Engine-Right panel(UI/UX)- All section features are open by default (plus symbol enabled), and only the section header is shown by default | medium | No
45 | Creation Engine | 796 | Creation Engine-Right Tab(UI/UX)- The Layout Components section header appears in a distinct color | low | No
46 | Creation Engine | 784 | Creation Engine-Theme Tab(UI/UX)- The Theme tab is not readily accessible to end users and does not appear by default | low | Yes
47 | Creation Engine | 785 | Creation Engine-Theme Tab(UI/UX)- Some themes do not display their name/title | medium | No
48 | Creation Engine | 786 | Creation Engine-Theme Tab(UI/UX)- The top navbar theme not getting change when a new theme is added | medium | No
49 | Creation Engine | 788 | Creation Engine-Theme Tab(UI/UX)- The tool/help tip is not visible in the Theme tab | low | Yes
50 | Creation Engine | 790 | Creation Engine-Theme Tab(UI/UX)- There is a mismatch between the theme name and its color in the Theme tab, showing "Light" but rendering black | medium | No
51 | Internal Preview | 858 | Internal Preview(UI/UX)- The Menu name is not display as Internal Preview | high | No
52 | Internal Preview | 865 | Internal Preview(UI/UX)- There is no Tool/Help tip is not display in the Internal Preview page | medium | No
53 | Internal Preview | 866 | Internal Preview(UI/UX)- Page Header is not display in the Internal Preview page | high | No
54 | Internal Preview | 867 | Internal Preview(UI/UX)- Dual error message display in Internal Preview page when the validation added for the field | high | No
55 | Internal Preview | 868 | Internal Preview(UI/UX)- User unable to click the First check box in Tab bar section | medium | No
56 | Internal Preview | 869 | Internal Preview(UI/UX)- The menu item on the dashboard is selected, yet no corresponding components are shown | medium | No
57 | DB Engine | 989 | DB Engine(UI/UX)- Export Schema and Json viewer button name display partially | low | No
58 | DB Engine | 999 | DB Engine(UI/UX)- Save column button display as lable name it is not display as button | medium | No
59 | DB Engine | 1010 | DB Engine(UI/UX)- Mismatch module name display for Database Engine | medium | Yes
60 | DB Engine | 1014 | DB Engine(UI/UX)- Unwanted Will Add icon display in Schema Change Analysis pop up | medium | No
61 | Rules Engine | 943 | Rules Engine(UI/UX)- Two button display for create the conditions and Calculations but the feature added in single section | medium | No
62 | Rules Engine | 944 | Rules Engine(UI/UX)- Confused Test validation field available in Validation Section | high | No
63 | Rules Engine | 945 | Rules Engine(UI/UX)- User unable to change the date field format | medium | No
64 | Rules Engine | 946 | Rules Engine(UI/UX)- The password label and its input type are displayed as collapsed in the interface | medium | No
65 | Rules Engine | 947 | Rules Engine(UI/UX)- The max characters field should only accept numeric values, but it currently allows only the letter "e," which seems to be a validation issue | medium | No
66 | Rules Engine | 948 | Rules Engine(UI/UX)- The summarize text label display partially in condition section | low | No
67 | Rules Engine | 949 | Rules Engine(UI/UX)- The Scenario workflow is not start easily access for non-tech user | medium | No
68 | Rules Engine | 950 | Rules Engine(UI/UX)- Unwanted Setting option is display in middle panel when user click the element | high | No
69 | Deployment Engine | 1048 | Deployment Engine(UI/UX)- The Deployment Engine menu is not easily accessible | medium | No
70 | Deployment Engine | 1049 | Deployment Engine(UI/UX)- Deployment header name is not display when navigate the page | medium | Yes
71 | Deployment Engine | 1056 | Deployment Engine(UI/UX)- There are no tooltips/helptips displayed anywhere on the page | medium | Yes
72 | Deployment Engine | 1057 | Deployment Engine(UI/UX)- Avg. Duration not display value in Deployment History pop up | high | No
73 | Deployment Engine | 1058 | Deployment Engine(UI/UX)- Success Rate display mismatch value in Deployment History pop up | medium | No
74 | Deployment Engine | 1059 | Deployment Engine(UI/UX)- Version column display same value display for multiple row values | medium | No
75 | Deployment Engine | 1060 | Deployment Engine(UI/UX)- Duration & Actions not display value in Deployment History pop up | medium | No
76 | Deployment Engine | 1061 | Deployment Engine(UI/UX)- Currently I have deploy only one app but there is 2 values display in Deployment History pop up | medium | No
77 | Admin Engine | 1108 | Admin Engine(UI/UX)- The Admin Mode is not easily discoverable for non-technical users in deployed app | medium | No
78 | Admin Engine | 1109 | Admin Engine(UI/UX)- Unwanted "Main Menu" label display in the header | low | No
79 | Admin Engine | 1110 | Admin Engine(UI/UX)- The Button name display as list grid header in dashboard | medium | No
80 | Admin Engine | 1111 | Admin Engine(UI/UX)- Any of the chart or list grid is not display in the Dashboard | medium | No
81 | Admin Engine | 1117 | Admin Engine(UI/UX)- Superuser field is not display as one of the Create User field | medium | No
82 | Admin Engine | 1121 | Admin Engine(UI/UX)- The Column header alignment display improperly when change the Showing count dropdown values | medium | No
83 | Admin Engine | 1122 | Admin Engine(UI/UX)- Unwanted url content display in delete confirmation pop-up | medium | Yes
|  | Bug ID. | PMS Meeting Noted Issues Description | Severity
|  | 1 | Unable to open any MoM when login as a user | Critical
|  | 2 | Unable to edit the created record | Critical
|  | 3 | The Add point is not working in new mode | High
|  | 4 | Unable to delete the created MoM record | High
|  | 5 | The process mentioned in the discussion points was not clearly added, which could lead to confusion. | Medium
|  | 6 | Unable to add Assignee data and due date in new mode | High
|  | 7 | Unable to give the Action Items values in New mode | High
|  | 8 | Unable to add bulk data in at a single strecth | High
|  | 9 | Duration (minutes) field display the minus symbol | High

## Testing Engine Imp
Date | Reported By | Issue | Sub-issue Type | Description
4/30/2025 | Lakshmanan | Unable to execute the Automation testing: Logi Feature | Login Page is one of the major blocker for Autimation Execution | Ther is challenges to login the end user app, once they create their own app and try to Testing their created app
4/30/2025 | Lakshmanan | Unable to execute the Automation testing: Project Selection | There have multiple project available for the end user | Ther is challenges to Select the project in Workspace module, which project the end user working on most recenet created app
4/30/2025 | Lakshmanan | Unable to execute the Automation testing: Multiple Preview page | Multiple Preview available | Multiple Preview page display now for our app, There is no confirm which preview have the backend connection, there have lots of confustion i this, 2. Also the Curenmt external Preview taking too much steps to access the link/button 3. Once click the External Preview the System display the Error message
Issues and impact for Automation Script execution using Testing Engine:
1. While executing the automation script for an end-user-created app, we’re unable to log in with their credentials. Even when credentials are available, the predefined login script must be run every time this impact lots of Test script, which interrupts the execution of the actual app testing script
2. Currently, the Workspace module requires users to manually select their existing project, which poses a significant blocker for automation execution. If the user has multiple projects and selects the wrong one (i.e., not the one just created), the automation script will fail. There is also no clear way to verify if the selected project is the correct one.
Act as a technical writer specialized in software documentation. Create a comprehensive, beginner-friendly user manual for the Authentication Engine in our application. Include the following sections:
1. Module Overview – Describe what the Authentication Engine is and where it fits in the application.
2. Purpose – Explain why this module exists and what core problems it solves.
3. Key Features – List and describe the main functionalities included in this module.
4. Use Cases – Explain how this module is typically used by end-users or app builders.
5. Value for App Creation – Describe how this module contributes to building custom applications using our platform (e.g., flexibility, extensibility, integration support).
6. Key Points to Remember – Highlight any important tips, constraints, or usage recommendations.
7. Recommended Reference Docs – Suggest the main document(s) or resources that end-users should read to understand and use this module effectively.
Make the tone clear, instructional, and user-friendly. Use examples, if appropriate.

## Test plan
Testing Plan: Authentication Engine & Workspace
S.No. | Test Activities | Objective | Scope | Estimated Duration | Deliverables
1 | Test Case Preparation | Prepare comprehensive test scenarios, test cases, and acceptance criteria covering the entire functionality of the Creation Engine module. | Identification and documentation of functional requirements. Detailed test scenarios including positive, negative, and boundary cases. Validation criteria and expected outcomes clearly defined. | 30 Minutes | Comprehensive Test Case Document Test Scenarios List with acceptance criteria
2 | Smoke Testing | Quickly verify basic functionalities and ensure the system is stable enough for more detailed testing. | 1)Login and logout functionality 2)Basic authentication workflow 3)Session initialization and termination 4)Workspace access validation | 30 Minutes | Smoke Test Report Identification of critical blockers (if any)
3 | Functional Testing (Manual) | Thoroughly validate each feature and functional requirement manually to ensure the Authentication Engine and Workspace behave correctly as per design specifications. | 1)User Registration Process 2)Login validations (correct/incorrect credentials handling) 3)Password reset functionality 4)Account locking/unlocking mechanism 5)User permissions and role validations 6)Session management and security 7)Error message and user notifications validation 8)Workspace creation, management, and access controls 9)Boundary conditions and edge-case scenarios | 4 Hours | Detailed Functional Test Cases Functional Test Execution Report Defect/Bug Report with severity and priority labels
Testing Plan: Creation Engine
S.No. | Test Activities | Objective | Scope | Estimated Duration | Deliverables
1 | Test Case Preparation | Prepare comprehensive test scenarios, test cases, and acceptance criteria covering the entire functionality of the Creation Engine module. | Identification and documentation of functional requirements. Detailed test scenarios including positive, negative, and boundary cases. Validation criteria and expected outcomes clearly defined. | 30 Minutes | Comprehensive Test Case Document Test Scenarios List with acceptance criteria
2 | Smoke Testing | Quickly assess the basic functionality and stability of the Creation Engine, ensuring the module is suitable for detailed functional testing. | 1)Launch and initial load of Creation Engine UI 2)Basic functionality checks (form creation, editing, deletion) 3)Navigation validation within the Creation Engine workflow | 1 Hour | Smoke Test Report Identification of critical blockers (if any)
3 | Functional Testing (Manual) | Conduct detailed manual validation of all functionalities within the Creation Engine to verify adherence to specified requirements and to identify defects or improvements. | 1)Creation and customization of forms 2)Validation of drag-and-drop functionality 3)Field-level validations and constraints 4)Saving, editing, and deleting forms and form templates 5)Integration points (if any) with other modules like Authentication and Workspace 6)Error handling, messaging, and user feedback verification 7)Performance checks (response time, loading, etc.) 8)Security checks (permissions, data validation, unauthorized access attempts) | 5 Hours | 1)Functional Test Execution Report 2)Defect Log (with defect description, severity, priority, and status) 3)Recommendations for improvements or enhancements, if applicable
Testing Plan: Component Generator
S.No. | Test Activities | Objective | Scope | Estimated Duration | Deliverables
1 | Test Case Preparation | Prepare comprehensive test scenarios, test cases, and acceptance criteria covering the entire functionality of the Creation Engine module. | Identification and documentation of functional requirements. Detailed test scenarios including positive, negative, and boundary cases. Validation criteria and expected outcomes clearly defined. | 30 Minutes | Comprehensive Test Case Document Test Scenarios List with acceptance criteria
2 | Smoke Testing | Verify essential functionalities to confirm basic stability of the Component Generator module before conducting detailed testing. | 1)Basic component creation functionality. 2)Verification of component rendering and initialization. 3)Basic validations of UI interactions. | 30 Minutes | 1)Smoke Test Report 20Identification of critical blockers (if any)
3 | Functional Testing (Manual) | Manually validate all core and extended functionalities of the Component Generator, ensuring it meets all specified requirements and quality standards. | 1)Component creation and customization workflows 2)Validation of input fields and parameters 3)User interface responsiveness and interactions 4)Boundary condition checks and error handling 5)Integration testing with other relevant modules (if applicable) 6)Verification of data persistence and state management | 3 Hours | 1)Detailed Test Case Execution Report 2)Defect Report with clear categorization of issues (severity and priority)
Testing Plan: Code View
S.No. | Test Activities | Objective | Scope | Estimated Duration | Deliverables
1 | Test Case Preparation | Prepare comprehensive test scenarios, test cases, and acceptance criteria covering the entire functionality of the Creation Engine module. | Identification and documentation of functional requirements. Detailed test scenarios including positive, negative, and boundary cases. Validation criteria and expected outcomes clearly defined. | 30 Minutes | Comprehensive Test Case Document Test Scenarios List with acceptance criteria
2 | Smoke Testing | Quickly confirm the stability and basic functionality of the Code View module, ensuring it's ready for in-depth functional testing. | 1Initial loading and rendering of code editor/viewer. 2)Basic interaction validations (e.g., copy, paste, editing). 30Simple checks for syntax highlighting and line numbering. | 30 Minutes | 1)Smoke Test Report 20Identification of critical blockers (if any)
3 | Functional Testing (Manual) | Manually verify the detailed functionality of the Code View module to ensure comprehensive adherence to specified requirements. | 1)Detailed code rendering and syntax highlighting accuracy. 2)Testing for editing functionalities (insert, delete, modify code). 3)Validation of line numbering and scrolling functionalities. 4)Search functionality within the code viewer/editor. 5)Error handling for invalid inputs or unsupported formats. 6)Performance assessment (loading speed, responsiveness). 70Cross-browser compatibility tests (if web-based). | 2.5 Hours | 1)Comprehensive Functional Test Execution Report 2)Detailed Defect Report outlining severity, priority, and recommendations
Testing Plan: Deployment Engine
S.No. | Test Activities | Objective | Scope | Estimated Duration | Deliverables
1 | Test Case Preparation | Prepare comprehensive test scenarios, test cases, and acceptance criteria covering the entire functionality of the Creation Engine module. | Identification and documentation of functional requirements. Detailed test scenarios including positive, negative, and boundary cases. Validation criteria and expected outcomes clearly defined. | 30 Minutes | Comprehensive Test Case Document Test Scenarios List with acceptance criteria
2 | Smoke Testing | Verify the critical functionalities of the Deployment Engine quickly, ensuring basic stability before conducting more detailed tests. | 1Basic deployment functionality checks (initiate, pause, cancel deployments). 2)Initial validation of deployment status indicators. 3)Preliminary verification of system accessibility and UI responsiveness. | 1 Hour | 1)Smoke Test Report 20Identification of critical blockers (if any)
3 | Functional Testing (Manual) | Execute comprehensive manual tests to validate all functional requirements of the Deployment Engine, ensuring reliable and accurate deployments. | 1)Detailed deployment workflow validation (create, execute, rollback deployments). 2)Verification of deployment status reporting accuracy. 3)Error handling and system recovery testing. 4)User permission checks and deployment approval workflow. 5)Integration and compatibility checks with other system components. 6)Performance evaluation under various load scenarios. 7)Security testing for deployment-related permissions and access control. 8)Boundary condition testing (maximum/minimum deployment thresholds). | 5 Hours | 1)Detailed Functional Test Execution Report 2)Defect Tracking Document (severity, priority, resolution suggestions)
Testing Plan: Testing Engine
S.No. | Test Activities | Objective | Scope | Estimated Duration | Deliverables
1 | Test Case Preparation | Prepare comprehensive test scenarios, test cases, and acceptance criteria covering the entire functionality of the Creation Engine module. | Identification and documentation of functional requirements. Detailed test scenarios including positive, negative, and boundary cases. Validation criteria and expected outcomes clearly defined. | 30 Minutes | Comprehensive Test Case Document Test Scenarios List with acceptance criteria
2 | Smoke Testing | Verify the critical functionalities of the Deployment Engine quickly, ensuring basic stability before conducting more detailed tests. | 1Initial loading and basic functionality checks of the Testing Engine interface. 2)Validation of basic test execution capabilities. 3)Preliminary checks for test report generation and display. | 30 Minutes | 1)Smoke Test Report 20Identification of critical blockers (if any)
3 | Functional Testing (Manual) | Perform in-depth manual testing to comprehensively validate the functionality of the Testing Engine module, ensuring all specified requirements are accurately implemented. | 1)Test case creation and management workflow verification 2)Execution and result logging functionalities 3)Manual test execution and validation of expected versus actual outcomes 4)Test scenario management and updating capabilities 5)Error handling and edge-case scenario validation 6)Integration with other modules like Authentication and Creation Engine (if applicable) 7)Usability and user experience evaluations 8)Verification of data accuracy and completeness in test reports | 3 Hours | 1)Comprehensive Functional Testing Report 2)Defect Log detailing issues with severity, priority, and suggested resolutions

## Pivot_Chart for Bug
| Count of Severity | Column Labels
S.NO. | Row Labels | critical | high | low | medium | Grand Total
1 | Admin Engine |  | 11 | 1 | 14 | 26
| Sai |  | 11 | 1 | 14 | 26
2 | Authentication Engine | 2 | 15 | 5 | 9 | 31
| PeriyaSedhu | 2 | 15 | 5 | 9 | 31
3 | Creation Engine | 7 | 69 | 7 | 38 | 121
| Edwin | 5 | 54 | 5 | 35 | 99
| PeriyaSedhu | 2 | 15 | 2 | 3 | 22
4 | DB Engine | 2 | 25 | 1 | 13 | 41
| saravana | 2 | 25 | 1 | 13 | 41
5 | Deployment Engine | 1 | 9 |  | 7 | 17
| Sai | 1 | 9 |  | 7 | 17
6 | Internal Preview | 1 | 8 |  | 4 | 13
| Vinoth | 1 | 8 |  | 4 | 13
7 | Rules Engine | 3 | 23 | 1 | 9 | 36
| Edwin | 3 | 23 | 1 | 9 | 36
| Grand Total | 16 | 160 | 15 | 94 | 285
S.NO. | Row Labels | Critical | High | Low | Medium | Grand Total
1 | Admin Engine |  | 11 | 1 | 14 | 26
| Sai |  | 11 | 1 | 14 | 26
2 | Authentication Engine | 2 | 15 | 5 | 9 | 31
| PeriyaSedhu | 2 | 15 | 5 | 9 | 31
3 | Creation Engine | 7 | 69 | 7 | 38 | 121
| Edwin | 5 | 54 | 5 | 35 | 99
| PeriyaSedhu | 2 | 15 | 2 | 3 | 22
4 | DB Engine | 2 | 25 | 1 | 13 | 41
| saravana | 2 | 25 | 1 | 13 | 41
5 | Deployment Engine | 1 | 9 |  | 7 | 17
| Sai | 1 | 9 |  | 7 | 17
6 | Internal Preview | 1 | 8 |  | 4 | 13
| Vinoth | 1 | 8 |  | 4 | 13
7 | Rules Engine | 3 | 23 | 1 | 9 | 36
| Edwin | 3 | 23 | 1 | 9 | 36
| Grand Total | 16 | 160 | 15 | 94 | 285

## Bug List
S.NO | Module name | Bug ID. | Description | Severity | Assigned To
1 | Authentication Engine | 620 | Login Page(Functional)- The "Forgot Password" feature is not functioning as expect | high | PeriyaSedhu
2 | Authentication Engine | 621 | Login Page(Functional)- A misleading error message appears when users enter an invalid email and attempt to sign in | high | PeriyaSedhu
3 | Authentication Engine | 622 | Login Page(Functional)- Sign-In Data Carrying Over to Sign-Up Tab: Fields in the Sign-In tab persist when navigating to Sign-Up | high | PeriyaSedhu
4 | Authentication Engine | 623 | Login Page(Functional)- Users are unable to update their existing credentials | high | PeriyaSedhu
5 | Authentication Engine | 624 | Login Page(Functional)- The Terms & Conditions pop-up does not appear when clicking the hyperlink | high | PeriyaSedhu
6 | Authentication Engine | 625 | Login Page(Functional)- Forgot Password" is displayed as a label instead of a clickable hyperlink | medium | PeriyaSedhu
7 | Authentication Engine | 626 | Login Page(Functional)- Basic Email validation error is not display in Reset Password pop up | high | PeriyaSedhu
8 | Authentication Engine | 627 | Login Page(Functional)- Unwanted page display when user click the rest password Link in received mail | high | PeriyaSedhu
9 | Authentication Engine | 628 | Login Page(Functional)- Reset Password pop up getting close when click outside the Reset Password pop-up | high | PeriyaSedhu
10 | Authentication Engine | 629 | Login Page(Functional)- Email Field Permits Invalid Special Characters, Allowing Fake or Improper Account Registration | high | PeriyaSedhu
11 | Authentication Engine | 630 | Login Page(Functional)- User try to create new account with max character missguidance error message display | high | PeriyaSedhu
12 | Authentication Engine | 631 | Login Page(Functional)- The Email ID and Password fields accept more than 500 characters, exceeding standard input limits | high | PeriyaSedhu
13 | Authentication Engine | 635 | Login Page(Functional)- The Password field allows users to save with more than 50 characters and even create an account with a 72-character password | high | PeriyaSedhu
14 | Authentication Engine | 637 | Login Page(Functional)- The proper validation error message is missing for Password field when user skip the field | high | PeriyaSedhu
15 | Authentication Engine | 638 | Login Page(Functional)- No Error Message display When click the Creating an Account button Without Email & Password | high | PeriyaSedhu
16 | Authentication Engine | 639 | Login Page(Functional)- The Reset Password email does not contain any reference to Simplita.ai, making it unclear where the email is coming from | high | PeriyaSedhu
17 | Authentication Engine | 640 | Login Page(Functional)- The error message continues to display even after entering a valid value, following an initial invalid input | medium | PeriyaSedhu
18 | Authentication Engine | 641 | Login Page(UI/UX)- Login success message is not displayed correctly | medium | PeriyaSedhu
19 | Authentication Engine | 642 | Login Page(UI/UX)- Label displayed as "Email ID" instead of "Email ID." (Dot missing in "ID.") | low | PeriyaSedhu
20 | Authentication Engine | 643 | Login Page(UI/UX)- Tooltip/help text missing for "Show Password" option | medium | PeriyaSedhu
21 | Authentication Engine | 644 | Login Page(UI/UX)- The Email ID and Password fields do not indicate they are required fields | medium | PeriyaSedhu
22 | Authentication Engine | 645 | Login Page(UI/UX)- The password suggestion error message does not disappear unless all conditions are met | medium | PeriyaSedhu
23 | Authentication Engine | 646 | Login Page(UI/UX)- The login page background does not meet design expectations. | medium | PeriyaSedhu
24 | Authentication Engine | 647 | Login Page(UI/UX)- Simplita.ai logo & company name should be display as bold but currently appear in normal text | low | PeriyaSedhu
25 | Authentication Engine | 648 | Login Page(UI/UX)- Sign-Up page is missing the Username field | low | PeriyaSedhu
26 | Authentication Engine | 649 | Login Page(UI/UX)- There is missmatch between Email ID.lable name and placeholder | low | PeriyaSedhu
27 | Authentication Engine | 650 | Login Page(UI/UX)- Duplicate Error Messages Shown for Invalid Email Entry | low | PeriyaSedhu
28 | Authentication Engine | 651 | Login Page(UI/UX)- There is an inconsistency in label names on the Sign In/Sign Up page. The email field is labeled as "Email ID," while the Reset password pop-up displays "Email Address" | medium | PeriyaSedhu
29 | Authentication Engine | 652 | Login Page(UI/UX)- Cancel button display as Label name in Reset password pop-up | medium | PeriyaSedhu
30 | Authentication Engine | 666 | Login Page(Functional)- Unable to click the "Create Account" button on the Sign-Up page, when give valid value and move the Sign up tab | critical | PeriyaSedhu
31 | Authentication Engine | 667 | Login Page(Functional)- User unable to create the new user with valid credtial | critical | PeriyaSedhu
32 | Creation Engine | 669 | Creation Engine-Canvas Editor(Functional)- Canvas Editor display the existing project details when a new project is created by the user | critical | Edwin
33 | Creation Engine | 670 | Creation Engine-Canvas Editor(Functional)- The drag and drop function fails when the user creates a new project for the first time | high | Edwin
34 | Creation Engine | 672 | Creation Engine-Canvas Editor(Functional)- The "Create app using chat" feature doesn't work when a new project is created for the first time | high | Edwin
35 | Creation Engine | 673 | Creation Engine-Canvas Editor(Functional)- Without the app layout, users cannot view the app in preview mode | high | Edwin
36 | Creation Engine | 674 | Creation Engine-Layers Tab(Functional)- The deleted menu name continues to display in another screen backend and database | high | Edwin
37 | Creation Engine | 675 | Creation Engine-Canvas Editor(Functional)- The drag and drop function is not operating smoothly | high | Edwin
38 | Creation Engine | 676 | Creation Engine-Canvas Editor(Functional)- The user cannot see small and simple words when the inline editing feature is enabled | high | Edwin
39 | Creation Engine | 677 | Creation Engine-Canvas Editor(Functional)- The resize feature does not meet current market standards | high | Edwin
40 | Creation Engine | 678 | Creation Engine-Canvas Editor(Functional)- The element drag and drop feature isn't working within the structure of the div | high | Edwin
41 | Creation Engine | 679 | Creation Engine-Canvas Editor(Functional)- The system auto-saves once an element is resized, but it doesn't complete the auto-save process before the user attempts to resize again | high | Edwin
42 | Creation Engine | 680 | Creation Engine-Canvas Editor(Functional)- Unwanted components are displayed in the Basic Elements section | high | Edwin
43 | Creation Engine | 681 | Creation Engine-Canvas Editor(Functional)- When a user adds spaces in the Heading div, unwanted and confusing content displays in the canvas. | high | Edwin
44 | Creation Engine | 682 | Creation Engine-Canvas Editor(Functional)- There is no height resize option available for any element | high | Edwin
45 | Creation Engine | 683 | Creation Engine-Right panel(Functional)- The right-side panel shows two confusing layouts section values | high | Edwin
46 | Creation Engine | 684 | Creation Engine-Canvas Editor(Functional)- By default, the font size and color do not display when the user clicks the settings button in any element | high | Edwin
47 | Creation Engine | 685 | Creation Engine-Layers Tab(Functional)- The menu create field allows more than 500 characters | high | Edwin
48 | Creation Engine | 686 | Creation Engine-Layers Tab(Functional)- The delete icon is not visible when more than 10 characters are entered in the menu create field | high | Edwin
49 | Creation Engine | 687 | Creation Engine-Layers Tab(Functional)- The delete icon does not display for a single menu available, and there is no instruction explaining why the delete icon is missing | medium | Edwin
50 | Creation Engine | 688 | Creation Engine-Layers Tab(Functional)- Unwanted layers section is displayed in the layers tab | high | Edwin
51 | Creation Engine | 689 | Creation Engine-Canvas Editor(Functional)- Three save options in the Creation Engine cause confusion for the end user | high | Edwin
52 | Creation Engine | 690 | Creation Engine-Right panel(Functional)- The unwanted validation section displays in the Creation right panel | high | Edwin
53 | Creation Engine | 691 | Creation Engine-Elements Tab(Functional)- Multiple top navigation bar elements are displayed in the Layout-Component section | medium | Edwin
54 | Creation Engine | 692 | Creation Engine-Canvas Editor(Functional)- The user is unable to create top menus or pages; only side menus or pages are available | critical | Edwin
55 | Creation Engine | 693 | Creation Engine-Canvas Editor(Functional)- The user cannot clear or delete multiple elements on one page | high | Edwin
56 | Creation Engine | 694 | Creation Engine-Canvas Editor(Functional)- The user cannot add new content or words using the container-layout elements | high | Edwin
57 | Creation Engine | 695 | Creation Engine-Canvas Editor(Functional)- The user cannot add any element after the fixed layout with the sidebar layout element section is added | high | Edwin
58 | Creation Engine | 696 | Creation Engine-Canvas Editor(Functional)- Two layout sections display when the fixed layout is added to the left panel, which creates confusion | critical | Edwin
59 | Creation Engine | 697 | Creation Engine-Canvas Editor(Functional)- The user cannot create any single element for Menu-2 after the fixed layout is added using the left panel | critical | Edwin
60 | Creation Engine | 698 | Creation Engine-Canvas Editor(Functional)- The user is unable to update the color after the layout is added | high | Edwin
61 | Creation Engine | 699 | Creation Engine-Canvas Editor(Functional)- The updated layout does not display in the canvas editor | high | Edwin
62 | Creation Engine | 700 | Creation Engine-Canvas Editor(Functional)- The user cannot delete layout content that was added using the right panel | high | Edwin
63 | Creation Engine | 701 | Creation Engine-Elements Tab(Functional)- Only basic master page related fields and elements are displayed in the elements section | high | Edwin
64 | Creation Engine | 702 | Creation Engine-Layers Tab(Functional)- When the user adds a page, there is no success message displayed | high | Edwin
65 | Creation Engine | 703 | Creation Engine-Left Panel(Functional)- There is confusion regarding the tab name in the Creation Engine left panel (1.Elements, 2.Layers, 3.Components); the basic logic for the tab name is missing | high | Edwin
66 | Creation Engine | 704 | Creation Engine-Canvas Editor(Functional)- Deleted pages or menus still display in the Canvas Editor section | high | Edwin
67 | Creation Engine | 705 | Creation Engine-Canvas Editor(Functional)- There is no option to revert the applied Layout-Right panel | high | Edwin
68 | Creation Engine | 706 | Creation Engine-Canvas Editor(Functional)- The user is unable to resize or maximize the already minimized field | high | Edwin
69 | Creation Engine | 707 | Creation Engine-Canvas Editor(Functional)- The user cannot add new pages or menus as the top menu | high | Edwin
70 | Creation Engine | 708 | Creation Engine-Canvas Editor(Functional)- There is no toast message displayed when a page is deleted | high | Edwin
71 | Creation Engine | 709 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the logo in the | high | Edwin
72 | Creation Engine | 710 | Creation Engine-Canvas Editor(Functional)- The user cannot edit the progress bar or table element in the Canvas Editor | high | Edwin
73 | Creation Engine | 711 | Creation Engine-Layer Tab(Functional)- The updated menu/page value is not displayed in the Layers section-left panel. | high | Edwin
74 | Creation Engine | 712 | Creation Engine-Elements Tab(Functional)- There is confusion between the Basic Elements and Form sections in the Element tab-left panel. | high | Edwin
75 | Creation Engine | 713 | Creation Engine-Canvas Editor(Functional)- The user is unable to add elements in the second tab (Tabbar components) of the Canvas Editor | high | Edwin
76 | Creation Engine | 714 | Creation Engine-Canvas Editor(Functional)- The dashboard button is displayed as clicked, but the user cannot change the view mode after adding the Layout-Right panel. | medium | Edwin
77 | Creation Engine | 715 | Creation Engine-Canvas Editor(Functional)- The user is unable to change the page/menu background color in the canvas editor | high | Edwin
78 | Creation Engine | 716 | Creation Engine-Canvas Editor(Functional)- Resizing does not work in the page/menu within the canvas editor | high | Edwin
79 | Creation Engine | 717 | Creation Engine-Canvas Editor(Functional)- The user is unable to view the entire element after adding multiple templates in the canvas editor | high | Edwin
80 | Creation Engine | 718 | Creation Engine-Canvas Editor(Functional)- The Save & Load section is don't want available in the right-side panel | high | Edwin
81 | Creation Engine | 719 | Creation Engine-Right Panel(Functional)- The user can link any available page/menu to any field or element | high | Edwin
82 | Creation Engine | 720 | Creation Engine-Components Tab(Functional)- Unable to save the New component in Components tab | high | Edwin
83 | Creation Engine | 721 | Creation Engine-Components Tab(Functional)- In the Preview section, display the Code also along with element UI (Create the Circle Loader) | critical | Edwin
84 | Creation Engine | 722 | Creation Engine-Components Tab(Functional)- Some of the element not create the by AI(Createthe 10 sort icon) | high | Edwin
85 | Creation Engine | 723 | Creation Engine-Components Tab(Functional)- Unable to perform paste the values in Ai chat field | medium | Edwin
86 | Creation Engine | 724 | Creation Engine-Components Tab(Functional)- Create New Components pop up getting close when click away from the pop up | medium | Edwin
87 | Creation Engine | 725 | Creation Engine-Components Tab(Functional)- When user send the message as hi then chat field display the Hi related elememnt code | medium | Edwin
88 | Creation Engine | 726 | Creation Engine-Components Tab(Functional)- The pop up getting close when user click the get help dropdown | high | Edwin
89 | Creation Engine | 727 | Creation Engine-Components Tab(Functional)- Updated existing components is not display the updated code | medium | Edwin
90 | Creation Engine | 728 | Creation Engine-Components Tab(Functional)- Two different pop up display for Component create and Edit, user can getting confuse a lot of edit the component for existing elemet and create the component using ai | high | Edwin
91 | Creation Engine | 729 | Creation Engine-Components Tab(Functional)- Image Element preview is display with error | high | Edwin
92 | Creation Engine | 747 | Creation Engine-Right panel(Functional)- Drag-and-drop functionality in the Image Library Right Panel is not working | high | Edwin
93 | Creation Engine | 748 | Creation Engine-Right panel(Functional)- No success message is displayed after deleting an uploaded image in the Image Library Right Panel | medium | Edwin
94 | Creation Engine | 749 | Creation Engine-Right panel(Functional)- A user can upload files larger than 10 MB | high | Edwin
95 | Creation Engine | 750 | Creation Engine-Right panel(Functional)- The system does not present the correct error message when uploading a <> JSON file | high | Edwin
96 | Creation Engine | 751 | Creation Engine-Right panel(Functional)- Edit element Basic Styles are not functioning properly | high | Edwin
97 | Creation Engine | 752 | Creation Engine-Right panel(Functional)- An unwanted Export Canvas section is shown in the Right Panel | high | Edwin
98 | Creation Engine | 753 | Creation Engine-Layers Tab(UI/UX)- The Layers Tab appears second, but the system does not clearly explain why it is unable to drag and drop components | medium | Edwin
99 | Creation Engine | 754 | Creation Engine-Layers Tab(UI/UX)- No message is shown prompting the user to create Pages/menus first before add the elements | medium | Edwin
100 | Creation Engine | 755 | Creation Engine-Canvas Editor(UI/UX)- When resizing large word content, it collapses, causing display issues. | medium | Edwin
101 | Creation Engine | 756 | Creation Engine-Canvas Editor(UI/UX)- The H1-heading appears as a pixelated label name | medium | Edwin
102 | Creation Engine | 757 | Creation Engine-Canvas Editor(UI/UX)- The system fails to display H2, H3, and other elements | medium | Edwin
103 | Creation Engine | 758 | Creation Engine-Canvas Editor(UI/UX)- The element category appears confusing, requiring users to rearrange both the element and its name | medium | Edwin
104 | Creation Engine | 759 | Creation Engine-Canvas Editor(UI/UX)- Unwanted Image Elements are visible in the Basic Elements section | medium | Edwin
105 | Creation Engine | 760 | Creation Engine-Canvas Editor(UI/UX)- The Close/Clear icon is visible in the Layout Components section-right panel, but the section can only be accessed once the user clears it | low | Edwin
106 | Creation Engine | 761 | Creation Engine-Canvas Editor(UI/UX)- Two instances of the name "Simplita" are shown in the Creation Engine | medium | Edwin
107 | Creation Engine | 762 | Creation Engine-Canvas Editor(UI/UX)- The unwanted Layers section is visible in the Layers tab | high | Edwin
108 | Creation Engine | 763 | Creation Engine-Canvas Editor(UI/UX)- No tooltips or help tips are available for any icons | medium | Edwin
109 | Creation Engine | 764 | Creation Engine-Canvas Editor(UI/UX)- The "Two columns" element does not display correctly in the Canvas editor | medium | Edwin
110 | Creation Engine | 765 | Creation Engine-Canvas Editor(UI/UX)- Unwanted double quotes appear when adding any element to the canvas editor | medium | Edwin
111 | Creation Engine | 766 | Creation Engine-Canvas Editor(UI/UX)- An unnecessary icon is displayed next to the Undo & Redo buttons in the header | medium | Edwin
112 | Creation Engine | 767 | Creation Engine-Canvas Editor(UI/UX)- An unwanted navigation label appears after adding the Layout-Right panel | low | Edwin
113 | Creation Engine | 768 | Creation Engine-Canvas Editor(UI/UX)- An empty circle appears before the Sign-In button after adding the Layout-Right panel | medium | Edwin
114 | Creation Engine | 769 | Creation Engine-Canvas Editor(UI/UX)- The top menu is displayed in the middle of the page after adding the Layout-Right panel | medium | Edwin
115 | Creation Engine | 770 | Creation Engine-Canvas Editor(UI/UX)- When dragging and dropping a button element in the Canvas editor, the button appears as a normal label | medium | Edwin
116 | Creation Engine | 771 | Creation Engine-Canvas Editor(UI/UX)- The button element appears in two sections in the Components section on the left panel | medium | Edwin
117 | Creation Engine | 772 | Creation Engine-Canvas Editor(UI/UX)- By default, all page/menu checkboxes are selected after clicking "Apply Layout," but the "Select All" checkbox appears unselected. | medium | Edwin
118 | Creation Engine | 773 | Creation Engine-Component Tab(UI/UX)- Ai Assistant feature is displayed as a regular label name | medium | Edwin
119 | Creation Engine | 774 | Creation Engine-Component Tab(UI/UX)- No error message appears when the user leaves the Component name field empty in the Components tab | medium | Edwin
120 | Creation Engine | 775 | Creation Engine-Component Tab(UI/UX)- The header displays as "Component HTML*" but AI also generates other technologies | low | Edwin
121 | Creation Engine | 776 | Creation Engine-Component Tab(UI/UX)- The tool/help tip for the Close icon in the Create New Component's popup is not visible | low | Edwin
122 | Creation Engine | 777 | Creation Engine-Component Tab(UI/UX)- The field is labeled as Components Name, but should be labeled as Elements Name | medium | Edwin
123 | Creation Engine | 778 | Creation Engine-Component Tab(UI/UX)- The chat field icon is missing in existing element pop up | medium | Edwin
124 | Creation Engine | 779 | Creation Engine-Component Tab(UI/UX)- The element edit popup does not show the correct title | medium | Edwin
125 | Creation Engine | 780 | Creation Engine-Component Tab(UI/UX)- The Click me button code is displayed as a label name | medium | Edwin
126 | Creation Engine | 781 | Creation Engine-Component Tab(UI/UX)- The multiselect dropdown does not show any values | medium | Edwin
127 | Creation Engine | 782 | Creation Engine-Component Tab(UI/UX)- Multiple sidebar navigation options are displayed in the Navigation Section | medium | Edwin
128 | Creation Engine | 783 | Creation Engine-Header(UI/UX)- The menu/page dropdown collapse under the dashboard layout header, partially hiding its values | medium | Edwin
129 | Creation Engine | 793 | Creation Engine-Right panel(UI/UX)- All section features are open by default (plus symbol enabled), and only the section header is shown by default | medium | Edwin
130 | Creation Engine | 796 | Creation Engine-Right Tab(UI/UX)- The Layout Components section header appears in a distinct color | low | Edwin
131 | Creation Engine | 730 | Creation Engine-Theme Tab(Functional)- Cancel applied theme function is not available for Theme tab | high | PeriyaSedhu
132 | Creation Engine | 731 | Creation Engine-Theme Tab(Functional)- AI generate the Christmas's theme, but there is any properer user expect output is not receive | high | PeriyaSedhu
133 | Creation Engine | 732 | Creation Engine-Theme Tab(Functional)- The secondary colour is not apply in the canvas editor page | high | PeriyaSedhu
134 | Creation Engine | 733 | Creation Engine-Theme Tab(Functional)- User unable to delete the cretaed Theme | high | PeriyaSedhu
135 | Creation Engine | 734 | Creation Engine-Theme Tab(Functional)- There is no success message display when user creates the new theme | high | PeriyaSedhu
136 | Creation Engine | 735 | Creation Engine-Theme Tab(Functional)- User unable to delete the cretaed Theme | high | PeriyaSedhu
137 | Creation Engine | 736 | Creation Engine-Theme Tab(Functional)- Fonts edit features is not working | high | PeriyaSedhu
138 | Creation Engine | 737 | Creation Engine-Theme Tab(Functional)- Unable to change the text colour | high | PeriyaSedhu
139 | Creation Engine | 738 | Creation Engine-Theme Tab(Functional)- System not display the updated success message when update the theme | high | PeriyaSedhu
140 | Creation Engine | 739 | Creation Engine-Theme Tab(Functional)- Added theme color is not reflected the middle of the page, it hs refelect only in the side bar | high | PeriyaSedhu
141 | Creation Engine | 740 | Creation Engine-Theme Tab(Functional)- The background theme is not reflect which is work for only Dashboard layout is applied | critical | PeriyaSedhu
142 | Creation Engine | 741 | Creation Engine-Theme Tab(Functional)- User unable toadd the theme based on the menu/page, the theme going to add all menu/page, even which menu not include with layout | high | PeriyaSedhu
143 | Creation Engine | 742 | Creation Engine-Theme Tab(Functional)- Theme is not override when user add the new along with existing colour for any field/element | high | PeriyaSedhu
144 | Creation Engine | 743 | Creation Engine-Theme Tab(Functional)- User unable to add the Ai created Theme | critical | PeriyaSedhu
145 | Creation Engine | 744 | Creation Engine-Theme Tab(Functional)- System not allow to upload 1 mb file | high | PeriyaSedhu
146 | Creation Engine | 745 | Creation Engine-Theme Tab(Functional)- System not display proper error message when user upload <> JSON file | high | PeriyaSedhu
147 | Creation Engine | 746 | Creation Engine-Theme Tab(Functional)- In that available Edit Theme panel the Background colour only update the app, other that no feature is not working | high | PeriyaSedhu
148 | Creation Engine | 784 | Creation Engine-Theme Tab(UI/UX)- The Theme tab is not readily accessible to end users and does not appear by default | low | PeriyaSedhu
149 | Creation Engine | 785 | Creation Engine-Theme Tab(UI/UX)- Some themes do not display their name/title | medium | PeriyaSedhu
150 | Creation Engine | 786 | Creation Engine-Theme Tab(UI/UX)- The top navbar theme not getting change when a new theme is added | medium | PeriyaSedhu
151 | Creation Engine | 788 | Creation Engine-Theme Tab(UI/UX)- The tool/help tip is not visible in the Theme tab | low | PeriyaSedhu
152 | Creation Engine | 790 | Creation Engine-Theme Tab(UI/UX)- There is a mismatch between the theme name and its color in the Theme tab, showing "Light" but rendering black | medium | PeriyaSedhu
153 | Internal Preview | 857 | Internal Preview(Functional)- Without add the Layout the created app is not display in the Internal Preview page | critical | Vinoth
154 | Internal Preview | 858 | Internal Preview(UI/UX)- The Menu name is not display as Internal Preview | high | Vinoth
155 | Internal Preview | 859 | Internal Preview(Functional)- Deleted Menu/Pages display in Internal Preview page | high | Vinoth
156 | Internal Preview | 860 | Internal Preview(Functional)- Created login page also display as menu in Internal preview | high | Vinoth
157 | Internal Preview | 861 | Internal Preview(Functional)- Duplicate Progress bar display in Internal Preview page | high | Vinoth
158 | Internal Preview | 862 | Internal Preview(Functional)- System not display the Added search box, Filter is not display in Internal Preview page | high | Vinoth
159 | Internal Preview | 863 | Internal Preview(Functional)- First displayed menu based page content not display when navigate to Internal Preview page | high | Vinoth
160 | Internal Preview | 864 | Internal Preview(Functional)- User can save the components for multiple time, system not display any information message for this issue | medium | Vinoth
161 | Internal Preview | 865 | Internal Preview(UI/UX)- There is no Tool/Help tip is not display in the Internal Preview page | medium | Vinoth
162 | Internal Preview | 866 | Internal Preview(UI/UX)- Page Header is not display in the Internal Preview page | high | Vinoth
163 | Internal Preview | 867 | Internal Preview(UI/UX)- Dual error message display in Internal Preview page when the validation added for the field | high | Vinoth
164 | Internal Preview | 868 | Internal Preview(UI/UX)- User unable to click the First check box in Tab bar section | medium | Vinoth
165 | Internal Preview | 869 | Internal Preview(UI/UX)- The menu item on the dashboard is selected, yet no corresponding components are shown | medium | Vinoth
166 | DB Engine | 971 | DB Engine(Functional)- When user click the Remove table icon then system display the error message | high | saravana
167 | DB Engine | 975 | DB Engine(Functional)- The DB engine generate the multiple column for single element radio button | high | saravana
168 | DB Engine | 978 | DB Engine(Functional)- Multiple tables are not generated by the multi-tab field; only one combined table is produced | high | saravana
169 | DB Engine | 979 | DB Engine(Functional)- Inconsistent field names in AI-generated columns may confuse end users; align them clearly | high | saravana
170 | DB Engine | 981 | DB Engine(Functional)- There is no confirmation message when user click the remove column | medium | saravana
171 | DB Engine | 982 | DB Engine(Functional)- Unable to update the table name at the single stretch | medium | saravana
172 | DB Engine | 983 | DB Engine(Functional)- The 'Set a Foreign Key' feature includes the current table as a selectable option, which isn't useful | high | saravana
173 | DB Engine | 984 | DB Engine(Functional)- User unable to update the column data types | high | saravana
174 | DB Engine | 985 | DB Engine(Functional)- User can create the column with 500 characters | high | saravana
175 | DB Engine | 986 | DB Engine(Functional)- Given column name value not getting clear when user click the add new button | medium | saravana
176 | DB Engine | 987 | DB Engine(Functional)- System not display any success message when ai generate the schema | medium | saravana
177 | DB Engine | 988 | DB Engine(Functional)- Given data type value not getting clear when user click the add new button | medium | saravana
178 | DB Engine | 989 | DB Engine(UI/UX)- Export Schema and Json viewer button name display partially | low | saravana
179 | DB Engine | 990 | DB Engine(Functional)- Column name required message not display in below the column name field | medium | saravana
180 | DB Engine | 991 | DB Engine(Functional)- User can delete the primary key column | high | saravana
181 | DB Engine | 992 | DB Engine(Functional)- System display the error message when click the any option in Export schema button without save the schema | high | saravana
182 | DB Engine | 993 | DB Engine(Functional)- System throw the error message when click the Add new table button without add the ai generate schema | critical | saravana
183 | DB Engine | 994 | DB Engine(Functional)- Ai getting generate schema for the deleted page also | critical | saravana
184 | DB Engine | 995 | DB Engine(Functional)- System allow to set the multiple primary key for single table | high | saravana
185 | DB Engine | 996 | DB Engine(Functional)- Multiple column delete getting delete while delete the single column | high | saravana
186 | DB Engine | 997 | DB Engine(Functional)- The system does not allow assigning both a primary key and a foreign key to the same column | high | saravana
187 | DB Engine | 998 | DB Engine(Functional)- System unable to create the new column in Tables section | high | saravana
188 | DB Engine | 999 | DB Engine(UI/UX)- Save column button display as lable name it is not display as button | medium | saravana
189 | DB Engine | 1000 | DB Engine(Functional)- Column name display as undefined when update the data type for primary key column | high | saravana
190 | DB Engine | 1001 | DB Engine(Functional)- Not able to select the check box for new column add section | high | saravana
191 | DB Engine | 1002 | DB Engine(Functional)- Delete success message is not display when user delete the column | high | saravana
192 | DB Engine | 1005 | DB Engine(Functional)- When a column is changed from 'Not Required' to 'Required' in the edit section, any previously available data in that column gets removed and the column vanishes | high | saravana
193 | DB Engine | 1006 | DB Engine(Functional)- Export Schema file display unwanted dummy value when user click the button | high | saravana
194 | DB Engine | 1007 | DB Engine(Functional)- Api Generator display exiting api when user delete the existing table | high | saravana
195 | DB Engine | 1008 | DB Engine(Functional)- Read, Write and Delete feature is not working in Credentials tab-API Generator | high | saravana
196 | DB Engine | 1010 | DB Engine(UI/UX)- Mismatch module name display for Database Engine | medium | saravana
197 | DB Engine | 1012 | DB Engine(Functional)- Unwanted Back to Top icon display and also it have hide the other needed button also | medium | saravana
198 | DB Engine | 1013 | DB Engine(Functional)- Duplicate Close icon display in Schema Change Analysis pop up | medium | saravana
199 | DB Engine | 1014 | DB Engine(UI/UX)- Unwanted Will Add icon display in Schema Change Analysis pop up | medium | saravana
200 | DB Engine | 1015 | DB Engine(Functional)- The Schema Change Analysis pop up getting close when user click the away from the pop up | medium | saravana
201 | DB Engine | 1017 | DB Engine(Functional)- Created schema not display in table section, it have display only the user click the refresh icon in browser | high | saravana
202 | DB Engine | 1018 | DB Engine(Functional)- Er Diagram created relation ship mapping not reflect in Table page | high | saravana
203 | DB Engine | 1019 | DB Engine(Functional)- Chat section is not create any kind of feature | high | saravana
204 | DB Engine | 1020 | DB Engine(Functional)- Created relation ship mapping not getting auto save, there is no any save button available for ER Diagram page | high | saravana
205 | DB Engine | 1021 | Migration Engine(Functional)- The system allow only to upload the .sql type file | high | saravana
206 | DB Engine | 1022 | Migration Engine(Functional)- System allow to upload than more 50 mb file | medium | saravana
207 | Rules Engine | 915 | Rules Engine(Functional)- The Success message is not display when user add the Condition and Calculation | medium | Edwin
208 | Rules Engine | 916 | Rules Engine(Functional)- User unable to see the existing added Condition and Calculation | high | Edwin
209 | Rules Engine | 917 | Rules Engine(Functional)- User unable to add the Condition and Calculation for the app without click the middle panel element | high | Edwin
210 | Rules Engine | 918 | Rules Engine(Functional)- User can delete the middle panel element using Keyboard shortcut | critical | Edwin
211 | Rules Engine | 919 | Rules Engine(Functional)- The Right panel dropdown display only the All Form value | medium | Edwin
212 | Rules Engine | 920 | Rules Engine(Functional)- "Field value" condition feature is not working fine | high | Edwin
213 | Rules Engine | 921 | Rules Engine(Functional)- Deleted success message is not display when delete the Conditions/Calculation | medium | Edwin
214 | Rules Engine | 922 | Rules Engine(Functional)- User can edit the any Label name and alos the page/menu name | high | Edwin
215 | Rules Engine | 923 | Rules Engine(Functional)- Unwanted field value condition is display in condition added function | high | Edwin
216 | Rules Engine | 924 | Rules Engine(Functional)-The same creation engine top header display in Rules, there is no purpose for the header in Rules engine | high | Edwin
217 | Rules Engine | 925 | Rules Engine(Functional)- User unable to add Conditions and Calculations in rules engine when click the any div(Header &Menu) <> label name or field | critical | Edwin
218 | Rules Engine | 926 | Rules Engine(Functional)- The radio button validation is not display in Validation menu | high | Edwin
219 | Rules Engine | 927 | Rules Engine(Functional)- Test validation display field display as text field for dropdown | high | Edwin
220 | Rules Engine | 928 | Rules Engine(Functional)- Number only allowed validation is missing in Validation section | high | Edwin
221 | Rules Engine | 929 | Rules Engine(Functional)- Dropdown field validation is not up to the standard | high | Edwin
222 | Rules Engine | 930 | Rules Engine(Functional)- By default some of the basic validation is not be display when user click the element | medium | Edwin
223 | Rules Engine | 931 | Rules Engine(Functional)- The password field validation is still being displayed in the Rules Engine, even after the field—originally created as a password type—is updated and renamed to “XYZ.” | high | Edwin
224 | Rules Engine | 932 | Rules Engine(Functional)- System not display the vaidation field section when user click the field div in middle panel | high | Edwin
225 | Rules Engine | 933 | Rules Engine(Functional)- System not display the vaidation field section when user click the field div in middle panel | high | Edwin
226 | Rules Engine | 934 | Rules Engine(Functional)- Action field display as empty when user select maths calculation in Condition Type | high | Edwin
227 | Rules Engine | 935 | Rules Engine(Functional)- The Success message is not display when user add the validation | high | Edwin
228 | Rules Engine | 936 | Rules Engine(Functional)- The Success message is not display when user add the Automation workflow | high | Edwin
229 | Rules Engine | 937 | Rules Engine(Functional)- The condition node is not in the working status, the node display any others fields | critical | Edwin
230 | Rules Engine | 938 | Rules Engine(Functional)- System not display the Maths calculation and Automated received Mail | high | Edwin
231 | Rules Engine | 939 | Rules Engine(Functional)- There is no option to validate the config mail is wright or not | high | Edwin
232 | Rules Engine | 940 | Rules Engine(Functional)- User can Run the Automatin flow without create the Scenario | high | Edwin
233 | Rules Engine | 941 | Rules Engine(Functional)- The Automatin workflow only display the Email only, basicly we need to display the 4 to 5 node | high | Edwin
234 | Rules Engine | 942 | Rules Engine(Functional)- Maths operation node is not display any field | high | Edwin
235 | Rules Engine | 943 | Rules Engine(UI/UX)- Two button display for create the conditions and Calculations but the feature added in single section | medium | Edwin
236 | Rules Engine | 944 | Rules Engine(UI/UX)- Confused Test validation field available in Validation Section | high | Edwin
237 | Rules Engine | 945 | Rules Engine(UI/UX)- User unable to change the date field format | medium | Edwin
238 | Rules Engine | 946 | Rules Engine(UI/UX)- The password label and its input type are displayed as collapsed in the interface | medium | Edwin
239 | Rules Engine | 947 | Rules Engine(UI/UX)- The max characters field should only accept numeric values, but it currently allows only the letter "e," which seems to be a validation issue | medium | Edwin
240 | Rules Engine | 948 | Rules Engine(UI/UX)- The summarize text label display partially in condition section | low | Edwin
241 | Rules Engine | 949 | Rules Engine(UI/UX)- The Scenario workflow is not start easily access for non-tech user | medium | Edwin
242 | Rules Engine | 950 | Rules Engine(UI/UX)- Unwanted Setting option is display in middle panel when user click the element | high | Edwin
243 | Deployment Engine | 1045 | Deployment Engine(Functional)- The deployed app is only displaying the form page; the rest of the application is not visible | critical | Sai
244 | Deployment Engine | 1046 | Deployment Engine(Functional)- Exported data is currently missing from the Docker Exports section | high | Sai
245 | Deployment Engine | 1047 | Deployment Engine(Functional)- The app cannot be deployed without saving the component, and the system shows a confusing error message | high | Sai
246 | Deployment Engine | 1048 | Deployment Engine(UI/UX)- The Deployment Engine menu is not easily accessible | medium | Sai
247 | Deployment Engine | 1049 | Deployment Engine(UI/UX)- Deployment header name is not display when navigate the page | medium | Sai
248 | Deployment Engine | 1050 | Deployment Engine(Functional)- The application deployed is showing intermittent blinking behavior without a consistent pattern | high | Sai
249 | Deployment Engine | 1051 | Deployment Engine(Functional)- The system displays a "Failed with code" error message when using an app apart from any combined template | high | Sai
250 | Deployment Engine | 1052 | Deployment Engine(Functional)- The deployed app is only displaying the form page; the rest of the application is not visible | high | Sai
251 | Deployment Engine | 1053 | Deployment Engine(Functional)- The "Build App" button remains active and clickable repeatedly, despite no modifications being made to the app | high | Sai
252 | Deployment Engine | 1054 | Deployment Engine(Functional)- The system displays an error message during the app build process, but it doesn’t provide a clear reason for the failure | high | Sai
253 | Deployment Engine | 1055 | Deployment Engine(Functional)- User unable to move any page in deployed app | high | Sai
254 | Deployment Engine | 1056 | Deployment Engine(UI/UX)- There are no tooltips/helptips displayed anywhere on the page | medium | Sai
255 | Deployment Engine | 1057 | Deployment Engine(UI/UX)- Avg. Duration not display value in Deployment History pop up | high | Sai
256 | Deployment Engine | 1058 | Deployment Engine(UI/UX)- Success Rate display mismatch value in Deployment History pop up | medium | Sai
257 | Deployment Engine | 1059 | Deployment Engine(UI/UX)- Version column display same value display for multiple row values | medium | Sai
258 | Deployment Engine | 1060 | Deployment Engine(UI/UX)- Duration & Actions not display value in Deployment History pop up | medium | Sai
259 | Deployment Engine | 1061 | Deployment Engine(UI/UX)- Currently I have deploy only one app but there is 2 values display in Deployment History pop up | medium | Sai
260 | Admin Engine | 1108 | Admin Engine(UI/UX)- The Admin Mode is not easily discoverable for non-technical users in deployed app | medium | sai
261 | Admin Engine | 1109 | Admin Engine(UI/UX)- Unwanted "Main Menu" label display in the header | low | sai
262 | Admin Engine | 1110 | Admin Engine(UI/UX)- The Button name display as list grid header in dashboard | medium | sai
263 | Admin Engine | 1111 | Admin Engine(UI/UX)- Any of the chart or list grid is not display in the Dashboard | medium | sai
264 | Admin Engine | 1112 | Admin Engine(Functional)- The Edit Role Hierarchy feature is not working | high | sai
265 | Admin Engine | 1113 | Admin Engine(Functional)- The Username field allow more than 500 charaters | medium | sai
266 | Admin Engine | 1114 | Admin Engine(Functional)- The proper Email validation is not display in the Users create page | high | sai
267 | Admin Engine | 1115 | Admin Engine(Functional)- The common validation required validation is not display in any of the master page | medium | sai
268 | Admin Engine | 1116 | Admin Engine(Functional)- The Roles field fails to display as a dropdown when the total role values exceed 50 entries. | high | sai
269 | Admin Engine | 1117 | Admin Engine(UI/UX)- Superuser field is not display as one of the Create User field | medium | sai
270 | Admin Engine | 1118 | Admin Engine(Functional)- Password show icon is not display in create User page | medium | sai
271 | Admin Engine | 1119 | Admin Engine(Functional)- Data Export option is not available for any of the master list grid | high | sai
272 | Admin Engine | 1120 | Admin Engine(Functional)- The proper error message is not display in edit user pop up | medium | sai
273 | Admin Engine | 1121 | Admin Engine(UI/UX)- The Column header alignment display improperly when change the Showing count dropdown values | medium | sai
274 | Admin Engine | 1122 | Admin Engine(UI/UX)- Unwanted url content display in delete confirmation pop-up | medium | sai
275 | Admin Engine | 1123 | Admin Engine(Functional)- Success message is display when user click the Save changes button without add any changes | medium | sai
276 | Admin Engine | 1124 | Admin Engine(Functional)- Grid is not displaying any records (UI shows empty), but bulk delete still deletes all records | medium | sai
277 | Admin Engine | 1125 | Admin Engine(Functional)- The search bar displays as an unusually lengthy field. It should have a standard width aligned with other UI elements | medium | sai
278 | Admin Engine | 1126 | Admin Engine(Functional)- The Admin Engine User module is visible for access, but the login page is not loading or available in the deployed application | high | sai
279 | Admin Engine | 1127 | Admin Engine(Functional)- Pagination showing count display feature is not display in Roles master page | high | sai
280 | Admin Engine | 1128 | Admin Engine(Functional)- All check box getting select only when click the View only check box | medium | sai
281 | Admin Engine | 1129 | Admin Engine(Functional)- System display the error message when delete the roles record | high | sai
282 | Admin Engine | 1130 | Admin Engine(Functional)- Test connection feature is not working | high | sai
283 | Admin Engine | 1131 | Admin Engine(Functional)- Users are able to set an inactive integration record as the default | high | sai
284 | Admin Engine | 1132 | Admin Engine(Functional)- Users are able to assign the 'Default' status to multiple integration records | high | sai
285 | Admin Engine | 1133 | Admin Engine(Functional)- The sort feature is not available for any master page | high | sai

## Test Status
S.No. | Module Name | Testing Status | Bug Count | Remarks
1 | Authentication | Done | 31 | 1. Login Page & Workspace is Testing Complete 2. Auth Login Template page smoke test fail
2 | Creation Engine(Theme) | Done | 121 | Testing for the Creation and Thematic Engines has been successfully completed
3 | Internal Preview | Done | 13
4 | DB& Migration Engine | Done | 41
5 | Rules Engine | Done | 36
6 | Deployment Engine | Done | 17
7 | Admin Engine | Done | 26
8 | Testing Engine | YTS (The module does not meet the requirements for test execution) | 0 | The execution of end-user automation tests is not proceeding as expected because of certain blockers listed in the issue tracker.
9 | Analytics Engine | YTS (The module does not meet the requirements for test execution) | 0 | Currently, the Analytics Engine works only inside the app; it does not support deployment of the app with the analytics page.
10 | Secure Engine | YTS (The module does not meet the requirements for test execution) | 0 | The module is currently not available on the test server URL.
11 | E-Commerce Engine | YTS (The module does not meet the requirements for test execution) | 0 | The test server currently displays the UI, but the backend features are non-functional
12 | Bpmn Process | YTS (The module does not meet the requirements for test execution) | 0 | Only the basic CRED operations are currently available on the test server URL; the corresponding BPMN process is missing or not properly implemented
| Total |  | 285