## Cover Page
Test Summary_POS_Pre Invoice_Initiate Pay
VERSION NO | RELEASE DATE | CHANGE DETAILS |  | Prepared By
|  | SECTION | DESCRIPTION
1 | 2024-10-08 | Dashboard | POS_Pre Invoice_Initiate Pay | Lakshmanan.M

## Test Case Summary
Test Summary_ERP_Pre-Invoice_Initiate Pay
Product : |  | POS |  |  |  |  | Theme: | POS/Pre-Invoice Initiate Pay
Prepared By : |  | Lakshmanan. M |  |  |  |  | Prepared Date : | 2024-10-08
Date | Testing Phases | Test Case Summary |  |  |  |  | Bug Summary | [6 empty] | Bug Severity
|  | Total | Not Tested | Rejected | Executed | Execution % | New | Open | Re-Open | Closed | Rejected | Deferred | Total | Critical | High | Medium | Low | Pass % | Fail %
2024-10-01 | Smoke Testing | 10 | 0 | 0 | 10 | 100% | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 100% | 0%
2024-10-08 | Functional Testing | 122 | 0 | 0 | 122 | 100% | 12 | 0 | 0 | 0 | 0 | 0 | 13 | 2 | 5 | 2 | 3 | 89.34% | 10.66%
Note on H3: Arun Mohan: Theme indicates the Page Name or Module Name