## Oct Project List
Optical CRM
EPIC | Tasks | Sprint | Status | RAG | DEV 1 | DEV 2 | Tester | P | DEV SD | DEV ED | QA SD | QA ED | Sprint1 | 2024-09-30 | 2024-10-12
Inventory Management and Prescription Management | Develop inventory management module with detailed tracking of product-specific details. | Sprint1 | YTS |  | Sai | Sai | Lakshmanan | - | 2024-09-30 | 2024-10-12 | - | - | Sprint2 | 2024-10-07 | 2024-10-19
Customer Relationship Management and Patient Management | Develop customer relationship management module with tracking of patient history, prescription records, and appointment scheduling. | Sprint3 | YTS |  | Vinoth | Sai | Lakshmanan | - | 2024-09-14 | 2024-10-19 | - | - | Sprnt3 | 2024-10-14 | 2024-10-26
Sales and Invoicing, and Appointment Scheduling | Develop sales and invoicing module with generation of invoices, and sales tracking. | Sprint3 | YTS |  | Mosik | Sai | Lakshmanan | - | 2024-10-14 | 2024-10-19 | 2024-10-21 | 2024-11-02 | Sprnt4 | 2024-10-21 | 2024-11-02
Detailed Reporting and Marketing and Patient Communication | Develop detailed reporting module with sales and inventory tracking, and patient demographics. | Sprint1 | YTS |  | Mosik | Sai | Lakshmanan | - | 2024-09-30 | 2024-09-12 | - | - | Sprnt5 | 2024-10-14 | 2024-11-02
UI/UX Development | UI/UX Development | Sprint3 | YTS |  | Sai |  |  |  | 2024-10-14 | 2024-10-19
Prescription Module and Barcode Module | Develop prescription module with comprehensive eyewear and contact lens prescription details. Develop barcode module with generation, scanning, and management of barcodes for inventory items. | Sprint1 | YTS |  | Vinoth | Sai | Lakshmanan | - | 2024-09-30 | 2024-10-12 | - | -
SG HR Consultancy
User Story | Tasks | Sprint | Status | RAG | DEV 1 | DEV 2 | Tester | P | DEV SD | DEV ED | QA SD | QA ED
Initial Project Setup | Set up the Angular project structure. Set up the Spring Boot backend with required dependencies. | Sprint2 | YTS |  | Indira | Sedu | - | P1 | 2024-10-07 | 2024-10-12 | - | -
Database Design | Design the database schema based on business requirements | Sprint2 | YTS |  | Edwin | Indira | - | P2 | 2024-10-07 | 2024-10-12 | - | -
Secure Login System with Proper Security Constraints | Implement user authentication using Spring Security. Implement role-based access control (RBAC) for different users (e.g., Admin, HR, Employee). Secure login with JWT (JSON Web Tokens) or OAuth2. | Sprint2 | YTS |  | Sedu | Edwin | - | P3 | 2024-10-07 | 2024-10-19 | - | -
Menu & Dashboard Design | Design and implement a user-friendly Angular dashboard interface. | Sprint3 | YTS |  | Edwin | Indira | - | P4 | 2024-10-14 | 2024-10-26 | - | -
UI/UX Development in Angular | UI/UX Development in Angular | Sprint3 | YTS |  | Indira | Sedu | - | P2 | 2024-10-14 | 2024-10-26 | - | -
Initial API Development | api for client and candidate | Sprint4 | YTS |  | Sedu |  |  | P3 | 2024-10-21 | 2024-11-02
HR Module
User Story | Tasks | Sprint | Status | RAG | DEV 1 | DEV 2 | Tester | P | DEV SD | DEV ED | QA SD | QA ED
UI/UX design for the Leave Policy | New Projects | Sprint1 | YTS |  | Vinoth | - | - | - | 2024-09-30 | 2024-10-05 | 2024-10-06 | 2024-10-12
Leave Policy API Development | Compliance Checklist | Sprint1 | YTS |  | Bharathy | - | - | - | 2024-09-30 | 2024-10-12 | - | -
Leave Request Integration | Allocation of Tickets | Sprint1 | YTS |  | Edwin | - | - | - | 2024-09-30 | 2024-10-12 | - | -
Attance Verification module | Allocation of Tickets | Sprint1 | YTS |  | Mosik | - | - | - | 2024-09-30 | 2024-10-12 | 2024-10-14 | 2024-10-18
Incident Development
User Story | Tasks | Sprint | Status | RAG | DEV 1 | DEV 2 | Tester | P | DEV SD | DEV ED | QA SD | QA ED
Stock Adjustment | Warehouse Stock Adjustment |  | YTS |  | Bharathy | Edwin | - | - | - | - | - | -
Code Integration | integrated developed and tested code's |  | YTS |  | Sai | Bharathy | - | - | - | - | - | -
Ongoing Activity
User Story | Tasks | Sprint | Status | RAG | DEV 1 | DEV 2 | Tester | P | DEV SD | DEV ED | QA SD | QA ED
LCNC | Google form UI/UX design using jhipster | Sprint1 | WIP |  | Sedhu |  | - | - | 2024-10-01 | 2024-10-07 | - | -

## Impact & Help needed
S.No | Challenges | Action Needed ¦ Taken | Impacted Resources
1 | Resources engaged in ad-hoc, report related and incidents activity impacting the planned developments | Currently we see this as a recurring event, hiring the report development resource for ITSM team would address this issue | Sai, Indira, Sedhu
2 | Additional learning curve and time taken to adapt | Providing adequate support and training to scale him up. Additional quality checks and reviews are currently performed | Hari
3 | Resources aligned with ITSM job functions, impacting the planned developments | To bring in the new incumbents on par and add additional support by recruiting resources to ITSM to free Bharathy and Edwin to align them back to development activities | Bharathy, Edwin
4 | Need an additional resource for performing CI/CD activities as this is taking lot of time from our developers bandwidth impacting their development phase | To recruit a DevOps CI/CD engineer, till then we foresee deviations from the planned dates to complete the activity. We will factor additional times for these activities for the resource in future plans until we have a DevOps engineer | Sai
5 | Need to plan an ERP demo for the team (a basic workflow) to gain adequate knowledge to perform the development activity | All the resources are currently working under different modules related to ERP and it is extremely essential to close this activity at the earliest possible time | Scrum Team
6 | Leads, additional report creation and other management activities impacting the tracking of code quality check, performance, and other development activities of the developers | To free Leads from additional management tasks to focus on their primary roles to address the issues on priority and manage the product development phase efficiently | Leads

## Note
Status | RAG | Meaning
Completed |  | Completed meeting the deadline
Completed |  | Completed, but after the deadline
WIP |  | Started the development activity on time and progress is in line with the deadlines
WIP |  | The development activity started after the planned start date The development activity started on time, but we foresee the project not be completed on deadline
YTS |  | Planned date to start the development activity is passed, but yet to start
YTS |  | Planned and completion date is passed, but yet to start
YTS |  | The planned date to start the development activity is not yet commenced