## Agile Scrum Sept Project List
Epic 1: SCM Enhancements and New Developments
User Story | Tasks | Primary DEV | Secondary DEV | Tester | Priority | DEV Start Date | DEV End Date | QA Start Date | QA End Date | Dependency | Inter-dependency | Dependency Status
As a user, I need a procurement team dashboard. | Dashboard of the Procurement Team | Sedhu | - | Lakshmanan | P1 | 2024-09-04 | 2024-09-07 | 2024-09-09 | 2024-09-10 | - | No | -
As a user, I want to manage purchase prices efficiently. | Purchase Price | Hari | Indira | Lakshmanan | P2 | 2024-09-03 | 2024-09-05 | 2024-09-11 | 2024-09-12 | - | No | -
As a user, I need approvals for additional quantities. | Approvals for Additional Quantity | Bharathy | Sai | - | P3 | 2024-09-04 | 2024-09-09 | - | - | Dependent on Branch Stock Transfer module, SCM and Sales | No | WIP - 04-09-2024
As a user, I want to manage short expiry goods efficiently. | Short Expiry Goods | Indira | Bharathy | - | P4 | 2024-09-02 | 2024-09-07 | 2024-09-13 | 2024-09-14 | - | No | -
As a user, I need validation in the purchase order process. | Validation in the Purchase Order | Edwin | - | - | P5 | 2024-09-03 | 2024-09-03 | - | - | - | No | -
Epic 2: Finance Enhancements and New Developments
User Story | Tasks | Primary DEV | Secondary DEV | Tester | Priority | DEV Start Date | DEV End Date | QA Start Date | QA End Date | Dependency |  | Dependency Status
As a user, I need sales cash reconciliation improvements. | Sales Cash Reconciliation | Sedhu | - | - | P1 | 2024-09-09 | 2024-09-11 | - | - | Dependent on Branch Sales module | No | Existing feature
As a user, I want to improve the payment process. | Payment Process | Hari | Edwin | Lakshmanan | P2 | 2024-09-06 | 2024-09-13 | 2024-09-16 | 2024-09-17 | Dependent on Procrument (medicine, general), Employee salary and Expenses | No | Existing feature
As a user, I want a streamlined general ledger process. | General Ledger Master | Mosik |  | Lakshmanan | P3 | 2024-09-04 | 2024-09-18 | 2024-09-18 | 2024-09-20 | - | No | -
As a user, I want better management of the shareholder module. | Shareholder Module | Mosik | Edwin | Lakshmanan | P4 | 2024-09-19 | 2024-09-24 | 2024-09-26 | 2024-09-27 | - | No | -
As a user, I want an enhanced franchise module. | Franchise Module | Vinoth | Bharathy | - | P5 | 2024-09-10 | 2024-09-20 | - | - | - | No | -
As a user, I need to manage cash deposits more effectively. | Cash Deposit | Sai | - | - | P6 | 2024-09-10 | 2024-09-13 | - | - | Dependent on Branch Sales module | No | Existing feature
As a user, I need an enhanced petty cash register. | Petty Cash Register | Vinoth | - | - | P7 | 2024-09-04 | 2024-09-09 | - | - | - | No | -
As a user, I want to create and manage budgets effectively. | Budget | Edwin | - | - | P8 | 2024-09-04 | 2024-09-10 | - | - | - | No | -
Epic 3: IT Enhancements and New Developments
User Story | Tasks | Primary DEV | Secondary DEV | Tester | Priority | DEV Start Date | DEV End Date | QA Start Date | QA End Date | Dependency |  | Dependency Status
As a user, I want to manage new IT projects effectively. | New Projects | Sedhu | - | - | P1 | 2024-09-12 | 2024-09-17 | - | - | - | No | -
As a user, I need a compliance checklist. | Compliance Checklist | Indira | - | - | P2 | 2024-09-09 | 2024-09-16 | - | - | - | No | -
As a user, I need to allocate tickets efficiently. | Allocation of Tickets | Hari | Sedhu | Lakshmanan | P3 | 2024-09-16 | 2024-09-24 | 2024-04-23 | 2024-09-25 | - | No | -
Epic 4: Sales Enhancements and New Developments
User Story | Tasks | Primary DEV | Secondary DEV | Tester | Priority | DEV Start Date | DEV End Date | QA Start Date | QA End Date | Dependency |  | Dependency Status
As a user, I need to manage non-moving goods stock transfers. | Non-Moving Goods Stock Transfer | Indira | - | - | P1 | 2024-09-17 | 2024-09-21 | - | - | - | No | -
As a user, I want to manage customer feedbacks and grievances. | Customer Feedbacks and Grievances | Sai | - | - | P2 | 2024-09-16 | 2024-09-18 | - | - | Dependent on Sales Bill | No | Existing feature
As a user, I need to provide employee discounts efficiently. | Employee Discount | Sai | - | - | P3 | 2024-09-19 | 2024-09-26 | - | - | - | No | -
Ongoing Activity
Current Task | Tasks | Primary DEV | Secondary DEV | Tester | Priority | DEV Start Date | DEV End Date | QA Start Date | QA End Date | Dependency |  | Dependency Status
Ongoing Activity | Reports Developments and Support activities | Sai | - | - | P1 | 2024-09-03 | 2024-09-09 | - | - | - | No | -

## Sheet1
Resource | Innovation Idea's | Objective | Goals | Status | Due Date
Open
Automation suggestions
Lakshmanan | Proposal for Implementing CI/CD Notifications for Smoke Test Pass and Fail | The objective of this proposal is to enhance our CI/CD pipeline by incorporating automated notifications that alert relevant stakeholders whenever smoke tests pass or fail.This will enable quicker response times and more efficient troubleshooting, ensuring the stability and reliability of our build processes. | a)Enhance visibility into the CI/CD process by ensuring that all stakeholders are promptly notified of key events, specifically the outcomes of smoke tests. b)Provide clear and actionable communication, so that team members know exactly what steps to take following each notification, whether it’s to proceed with further testing or to address issues immediately. | Open | TBD
Simplifying ongoing activities
Hari | Essential Knowledge Transfer for Current Technologies, Tools, and Processes | The objective of the Knowledge Transfer (KT) session is to systematically share comprehensive information about the current technologies, tools, and processes in use within a project, team, or organization. This ensures that all team members or stakeholders acquire a thorough understanding of the technical landscape, enabling them to work efficiently, maintain consistency, and adapt to the existing workflows. | a)Provide a Clear Overview of the Technology Stack b)Explain the Functionality and Usage of Key Tools c)Detail the Current Processes and Workflows d)Highlight Best Practices and Standards e)Document All Knowledge for Future Reference | Close
Sharing best practices
Sai | Recommendation to Learn Prompt Engineering for Optimizing AI Interactions | In recent years, Artificial Intelligence (AI) and Natural Language Processing (NLP) models, particularly those based on large language models (LLMs) like OpenAI's GPT series, have gained significant traction in a variety of industries. One of the most critical skills in interacting effectively with these models is Prompt Engineering. | a)Understand AI Capabilities and Limitations: b)Enhance Problem-Solving and Creativity: c)Develop Adaptability Across AI Systems: | Open | TBD
Mosik | Advanced Search Techniques and Strategies for Efficient Internet Research | The objective of this topic is to equip individuals with advanced search techniques that go beyond basic keyword queries, enabling them to efficiently locate, filter, and evaluate information from the vast resources available on the internet. By mastering these strategies | a)Enhance Search Accuracy and Precision b)Optimize Use of Search Engines c)Evaluate Source Credibility and Relevance | Open | TBD
To address Pain Areas
Sai | Comprehensive Guide to Clear and Detailed Required Documentation | The objective of the Knowledge Transfer (KT) session is to systematically share comprehensive information about the current technologies, tools, and processes in use within a project, team, or organization. This ensures that all team members or stakeholders acquire a thorough understanding of the technical landscape, enabling them to work efficiently, maintain consistency, and adapt to the existing workflows. | a)Provide a Clear Overview of the Technology Stack b)Explain the Functionality and Usage of Key Tools c)Detail the Current Processes and Workflows d)Highlight Best Practices and Standards e)Document All Knowledge for Future Reference | Open | TBD